## Final Assembly constituency
Assembly constituency wise list of ongoing/proposed/O&M works | [33 empty] | (As on 31.08.23)
ਲੜੀ ਨੰ. | ਐਮ. ਐਲ ਦਾ ਨਾਂਮ | ਐਮ. ਐਲ ਦਾ ਨਾਂਮ ਅਤੇ ਫੋਨ ਨੰ. | Name of the MLA | ਕਸਬਾ ਇੰਚਾਰਜ ਅਤੇ ਫੋਨ ਨੰ. | Party | Division | Distt. |  | ਹਲਕਾ | Constituency | ਸ਼ਹਿਰ/ ਕਾਰਜਕਾਰੀ ਇੰਜੀਨੀਅਰ |  | Towns | Name of Work | Status | Name of Scheme |  | Broad Scope of Work |  |  | Tentative Cost of work (Rs Cr.) | Amount of DPR (Rs. Cr.) | Agg. Amount (Rs.Cr.) | Physcial Progress (%) | Financial progress (%) | Financial progress (Rs. Cr.) | Date of start / DPR Status | Date of completion | O&M Status |  | Name & Contact NO. |  |  | Remarks
[29 empty] | ULB/ PWSSB | Scope (W/S, Sew, STP) | EE | SDE | JE
1 | 2 | 2 |  | 3 | 3 | 3 | 3 | 6 | 4 |  | 5 |  |  | 6 | 7 | 8 |  | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 10 | 11 | 12 | 13 | 14 | 23
1 | Shri. Naresh Puri | ਸ਼੍ਰੀ ਨਰੇਸ਼ ਪੁਰੀ, 94170-09270 | Shri. Naresh Puri | ਸ਼੍ਰੀ ਅਮਿਤ ਮੰਟੂ 95782-55755 | INC | Gsp | Pathankot | 1 | ਸੂਜਾਨਪੁਰ | 1- Sujanpur | ਸੂਜਾਨਪੂਰ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Sujanpur | Sujanpur | Main Sewer, Rising Main,IPS, MPS, STP. | Proposed work | SBM-2.0 | 1) 2) 3) 4) | 1) | Main Sewer Rising Main MPS STP = 6MLD | 2.87 km 1.83 km 2No (7 &12mld) 1 No.6MLD | 35 | [5 empty] | DPR Under check at Head Office |  | ULB | W/S | Sh. Dvitesh Virdi 8728819080 | Sh. Lokinder Verma 7508348701 | Sh. Jagdeep Singh 95920-03154 | DPR under preparation stage
[6 empty] | Gsp |  | 1 | [5 empty] | WTP, Rising main and Balance water supply line |  | AMRUT 2.0- (T-1) |  | 2) | WTP New Dist.Network Raw Water Pipeline Clear Water Pipeline House Connt. | 9: 1 No.7.35 MLD 12.83 Km 5.0 Km 9.50 Km 3506 Nos.; 10: 31.06; 16: Tender Called; Scope (W/S, Sew, STP) 11: W/S; EE 12: Sh. Dvitesh Virdi; SDE 13: Sh. Lokinder Verma; JE 14: Sh. Jagdeep Singh; JE 23: DPR under preparation stage
2 | Shri. Lal Chand | ਸ਼੍ਰੀ ਲਾਲ ਚੰਦ 98150-13079 | Shri. Lal Chand |  | AAP | Gsp | Pathankot | 2 | ਬੋਹਾ | 2-Bhoa | ਬੋਹਾ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Boha | Bhoa | [6 empty] | ULB/ PWSSB 10: -; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
3 | Shri. Lal Chand | ਸ਼੍ਰੀ ਲਾਲ ਚੰਦ, 98150-13079 | Shri. Lal Chand |  | AAP | Gsp |  | 2 |  |  | ਨਿਰੋਲ ਜੈਮਲ ਸਿੰਘ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Narrot Jaimal | Nirol Jaimal Singh | Main Sewer, Rising Main,IPS , MPS, STP. | Proposed work | SBM-2.0 | 1) 2) 3) 4) | 1) | Main Sewer Rising Main MPS STP | 1.10 km 1.50 km 1 No. 7 MLD 1 No. 2MLD | 12 | [5 empty] | DPR yet to be received in Head Office |  | ULB | W/S | Sh. Dvitesh Virdi 8728819080 | Sh. Lokinder Verma 75083-48701 | Sh. Jagdeep Singh 95920-03154 | DPR under preparation stage
[6 empty] | Gsp |  | 2 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 2 | WTP Raw Water Pipeline Clear Water Pipeline House Connt. | 9: 1 No.19.95 MLD 6.0 Km 15.0 Km 1280; 10: 46.75; Scope (W/S, Sew, STP) 11: W/S; EE 12: Sh. Dvitesh Virdi; SDE 13: Sh. Lokinder Verma; JE 14: Sh. Jagdeep Singh; JE 23: DPR under preparation stage
4 | Sh.Ashwani Kumar Sharma | ਸ਼੍ਰੀ ਅਸ਼ਵਨੀ ਕੁਮਾਰ ਸ਼ਰਮਾਂ, 94174-66588 | Sh.Ashwani Kumar Sharma | ਸ਼੍ਰੀ ਵਿਭੂਤੀ ਸ਼ਰਮਾ, 9417408979 | BJP | Gsp | Pathankot | 3 | ਪਠਾਨਕੋਟ | 3- Pathankot | ਪਠਾਨਕੋਟ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Pathankot | Pathankot | Water Supply,Sew,OHSR,STP, Rising Main | Ongoing Work | AMRUT | 1) 2) 3) 4) 5) 6) 7) 8) | 1) | Water Supply Line Lateral Sewer Main sewer House Connection sew House Connection ws Tube wells OHSR STP 2.00 MLD (Adarsh Nagar) | 102.00Km 128.00 Km 13.96 km 11500 Nos 12450 Nos 21 Nos 05 NOS 1 Nos |  | 125.13 | 87.02 | 80% | 75% | 65.26 | 2016 | 31.07.23 | ULB PWSSB | W/S & Sew STP | Sh. Dvitesh Virdi 8728819080 | Sh. Lokinder Verma 75083-48701 | Sh. Jagdeep Singh 95920-03154 Sh. Dheeraj Kumar 83689-16797 | Balance works of 6 Nos Tubewells and MPS, at Jamalpur,Khanpur and STP at Adarsh Nagar to be the AMRUT2.0 | Expenditure cost increased | 74.99%
[6 empty] | Gsp |  | 3 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  |  | Drilling of Tube well Rising main | 9: 6 No. 0.400 mm; 10: 2.12; 16: Tender Called; JE 23: DPR under preparation stage
5 | Shri. Barindermeet Singh Pahra | ਸ਼੍ਰੀ ਬਰਿੰਦਰਮੀਤ ਸਿੰਘ ਪਹਾੜਾ 78840-00007 | Shri. Barindermeet Singh Pahra | ਸ਼੍ਰੀ ਰਮਨ ਬੇਹਾਲ, 9814151043 | INC | Gsp | Gurdaspur | 4 | ਗੁਰਦਾਸਪੁਰ | 4- Gurdaspur | ਗੁਰਦਾਸਪੁਰ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Gurdaspur | Gurdaspur | Prov. Water Supply and Sewerage and STP at Gurdaspur | Ongoing Work | HUDCO | 1) 2) 3) 4) 5) 6) 7) 8) 9) 10) 11) 12) | 1) | Main Sewer Lateral Sewer House Conn. Land Restoration of Road MPS Rising Main Distribution System H.C. MPS Reconditioning Tubewell OHSR | 6.30 Km 72.10 Km 4080 Nos 4 Acre 1 job 2 Nos 47.84 Km 7000 Nos 1 No 3 Nos OHSR1 No. |  | 43.05 | 16.6 | 80% | 77% | 12.2 | 2011 | 30.09.23 | ULB PWSSB | W/S Sew | Sh. Dvitesh Virdi 8728819080 | Sh. Durga Dass 85560-45385 | Smt. Manpreet Kaur 87278-26885 |  | Expenditure cost increased | 73.49%
5 | Shri. Barindermeet Singh Pahra | ਸ਼੍ਰੀ ਬਰਿੰਦਰਮੀਤ ਸਿੰਘ ਪਹਾੜਾ, 78840-00007 | Shri. Barindermeet Singh Pahra |  |  | Gsp |  | 4 | ਗੁਰਦਾਸਪੁਰ | 4- Gurdaspur | ਗੁਰਦਾਸਪੁਰ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Gurdaspur | Gurdaspur | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  |  | Drilling of Tube well Rising main OHSR (1, 0.5 LG) House connection Rehab of Dist. Network | 9: 14 No. 2.2 Km 2 No. 5000 Nos. 20 Km; 10: 23.01; EE 12: Sh. Dvitesh Virdi 8728819080; SDE 13: Sh. Durga Dass 85560-45385; JE 14: Smt. Manpreet Kaur 87278-26885; JE 23: DPR under preparation stage
[5 empty] | INC | Gsp | Gurdaspur | 4 | [5 empty] | Main Sewer, Rising Main , MPS, STP. | Proposed work | SBM-2.0 | 1) 2) 3) 4) | 1) | Main Sewer Rising Main MPS STP | 9: 3.36 km 2.67 km 1 No.(58 MLD) 1 No. (20 MLD); 10: 95; 16: DPR yet to be received in Head Office; EE 12: Sh. Dvitesh Virdi; SDE 13: Sh. Durga Dass; JE 14: Smt. Mapreet Kaur; JE 23: DPR under preparation stage
7 | Smt. Aruna Chaudhary | ਸ਼੍ਰੀਮਤੀ. ਅਰੂਣਾ ਚੋਧਰੀ 99148-00007 | Smt. Aruna Chaudhary | ਸ਼੍ਰੀ ਸਮਸ਼ੇਰ ਆਜ਼ਾਦ, 9814078581 | INC | Gsp | Gurdaspur | 5 | ਦੀਨਾ ਨਗਰ | 05- Dina Nagar | ਦੀਨਾ ਨਗਰ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Dina Nagar | Dina Nagar | Sew,STP,Rising Main,Tubewell | Ongoing Work | HUDCO | 1) 2) 3) 4) 5) | 1) | Lateral Sewer Main sewer Tube wells STP Rising Main | 34.08 Km 5.45 km 1 Nos 1 Nos 1.23 Km |  | 35.53 | 23.57 | 60% | 50% | 17.49 | 2019 | 30.09.23 | PWSSB | W/S & Sew STP | Sh. Dvitesh Virdi 8728819080 | Sh. Lokinder Verma 75083-48701 | Sh.Dharampal 88727-55520 Sh.Anil Saini 9464180496 |  |  | 74.2%
8 | Shri Partap Singh Bajwa | ਸ਼੍ਰੀ ਪਰਤਾਪ ਸਿੰਘ ਬਾਜਵਾ, 98788-70206 | Shri Partap Singh Bajwa | ਸ਼੍ਰੀ ਜਗਰੂਪ ਸਿੰਘ ਸੇਖੋ 9803589037 | INC | Asr-2 | Gurdaspur | 6 | ਧਾਲੀਵਾਲ | 6- Dhariwal | ਕਾਦੀਆਂ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Qadian | Qadian | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) | 1) 2) 3) 4) | 1) | W/S Distribution Line T.W House Conn. . | 9: W/S 18.80 KM 1 No. 1313 nos.; 10: 78.46; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/s; EE 12: Er. Harpreet Singh (8360907229); SDE 13: Er. Gurdeep Arora (8837600738); JE 14: Er. Balkaranjit Singh (7986019195); JE 23: DPR under preparation stage
8 | [5 empty] | Asr-2 |  | 6 | [6 empty] | Proposed work | SBM-2.0 | 1) 2) 3) 4) 5) 6) 7) | 2) | ii. Sewearge Main Sewer Branch Sewer House Conn. Roads MPS STP Rising Main | 9: ii. Sewearge 5.52 Km 44.43 Km 7060 nos. 76950.18 sqm 14 MLD 4MLD 250mtr.; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage | name of scheme
9 |  |  |  | ਸ਼੍ਰੀ ਜਗਰੂਪ ਸਿੰਘ ਸੇਖੋ 9803589037 | INC | Gsp | Gurdaspur | 6 | 6- Dhariwal | 6- Dhariwal | ਧਾਲੀਵਾਲ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Dhaliwal | Dhaliwal | Main Sewer, Rising Main , MPS, STP. | Proposed work | SBM-2.0 | 1) 2) 3) 4) | 1) | Main Sewer Rising Main MPS STP (2MLD & 1MLD) | 6.29 km 1.70 km 7 MLD 2Nos | 37 | [5 empty] | DPR yet to be received in Head Office |  | ULB | - | Sh. Dvitesh Virdi 8728819080 | Sh. Durga Dass 85560-45385 | Smt. Manpreet Kaur 87278-26885 | DPR under preparation stage
10 | Shri. Amansher Singh (Shery Kalsi) | ਸ਼੍ਰੀ ਅਮਨਸ਼ੇਰ ਸਿੰਘ ਸ਼ੈਰੀਕਲਸੀ 96150-00094 | Shri. Amansher Singh (Shery Kalsi) |  | AAP | Asr-2 | Gurdaspur | 7 | ਬਟਾਲਾ | 7- Batala | ਬਟਾਲਾ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Batala | Batala | Water Supply & Sewerage Work Package 1-A | Work Completed | AMRUT | 1) 2) 3) 4) 5) 6) 7) 8) | 1) | Water Supply GI Pipe - 50 o/d House Connectioin. Road Restoration Sewerage Main Sewer House Connection Road Restoration | 5.60 Km 0.90 km 661 Nos. 1 Job 16.55 Km 5.9 Km 3483 Nos. 1 Job |  | 141 | 16.34 | 100% | 88% | 12.59 | 04.03.20 | 31.03.23 | PWSSB | W/S , Sew and STP | Er. Harpreet Singh (8360907229) | Er. Gurjinder Singh (9915355229) | Er. Aman KUmar (8837796662) | Work Completed |  | 77.05%
[6 empty] | Asr-2 |  | 7 | [5 empty] | Water Supply & Sewerage Work Package 1-B | Ongoing Work | AMRUT | 1) 2) 3) 4) 5) 6) 7) 8) | 2) | Water Supply GI Pipe - 50 o/d House Connectioin Road Restoration Sewerage Main Sewer- House Connection Road Restoration | 9: 5.13 Km 0.30 Km 611 N os. 1 Jobs 27.66 Km 2.90 Km 2635 Nos 1 Job; 12: 12.67; 13: 81%; 14: 72%; 15: 10.05; 16: 04.03.20; 17: 31.08.23; JE 23: Work is in progress |  | 79.32%
10 | Shri. Amansher Singh (Shery Kalsi) | ਸ਼੍ਰੀ ਅਮਨਸ਼ੇਰ ਸਿੰਘ ਸ਼ੈਰੀਕਲਸੀ, 96150-00094 | Shri. Amansher Singh (Shery Kalsi) |  |  | Asr-2 |  | 7 | ਬਟਾਲਾ | 7- Batala | ਬਟਾਲਾ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Batala | Batala | Water Supply & Sewerage Work Package 1-C | Work Completed | AMRUT | 1) 2) 3) 4) 5) 6) 7) 8) 9) | 3) | Water Supply GI Pipe - 50 o/d House Connection Road Restoration Sewerage Main Sewer - House Connection Road Restoration Rehabilitation of RCC-Np3 | 9: 7.19 Km 0.50 Km 856 Nos. 1 Jobs 53.17 Km 8.05 Km 5065 Nos. 1 Jobs 800 mm i/d; 12: 25.31; 13: 100%; 14: 92%; 15: 23.55; 16: 04.03.20; 17: 31.03.23; JE 23: Work Completed |  | 93.05%
[6 empty] | Asr-2 |  | 7 | [5 empty] | Water Supply & Sewerage Work Package 1-D | Work Completed | AMRUT | 1) 2) 3) 4) 5) 6) 7) 8) | 4) | Water Supply GI Pipe - 50 o/d House Connection Road Restoration Sewerage Main Sewer -RCC - House Connection Road Restoration | 9: 4.69 KM 0.80 Km 558 Nos. 1 Jobs 17.79 Km 7.19 Km 1695 Nos. 1 Job; 12: 16.53; 13: 100%; 14: 88%; 15: 15.13; 16: 04.03.20; 17: 31.03.23; JE 23: Work Completed |  | 91.53%
[6 empty] | Asr-2 |  | 7 | [5 empty] | 7 Nos T/W | Work Completed | AMRUT | 1) | 5) | Tubewell | 9: 7 Nos.; 12: 1.57; 13: 100%; 14: 99%; 15: 1.47; 16: 24.06.20; 17: 23.06.21; JE 23: Work Completed |  | 93.63%
12 | Shri. Amansher Singh (Shery Kalsi) | ਸ਼੍ਰੀ ਅਮਨਸ਼ੇਰ ਸਿੰਘ ਸ਼ੈਰੀਕਲਸੀ, 96150-00094 | Shri. Amansher Singh (Shery Kalsi) |  |  | Asr-2 |  | 7 | ਬਟਾਲਾ | 7- Batala | ਬਟਾਲਾ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Batala | Batala | 30 MLD STP and MPS | Ongoing Work | AMRUT | 1) 2) 3) 4) 5) 6) 7) | 6) | 30 MLD STP 30 MLD MPS Sewerage Main Sewer RCC 1600mm I/D H. Conn. Road Restoration | 9: 1 Nos 1 No 5.71 Km 2.41 Km 299 Nos. 1 Jobs.; 12: 50.17; 13: 95%; 14: 76%; 15: 39.08; 16: 28.07.20; 17: 30.06.23; JE 23: Work is in progress |  | 77.9%
[6 empty] | Asr-2 |  | 7 | [5 empty] | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-2) | 1) 2) 3) 4) 5) | 1) | i. Water supply Distribution Line G.I Line Rising main OHSR (2.00 lac,0.50 lac) House Conn. | 9: 107.69KM 7822 mt 115 mt. 2 no 7049 nos.; 10: 87.59; JE 23: DPR under preparation stage
13 | Shri. Amarpal Singh | ਸ਼੍ਰੀ ਅਮਰਪਾਲ ਸਿੰਘ , 98561-00003 | Shri. Amarpal Singh |  | AAP | Asr-2 | Gurdaspur | 8 | ਸ਼੍ਰੀ ਹਰਗੋਬਿੰਦਪੁਰ | 8- Sri Hargobindpur | ਸ਼੍ਰੀ ਹਰਗੋਬਿੰਦਪੁਰ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Shri Hargobindpur | Shri Hargobindpur | Water Supply Work | Ongoing Work | HUDCO | 1) 2) 3) 4) | 1) | DI-K7 GI-Pipe 50mm RCC PI-300mm House Connection | 9.99 Km 0.81 Km 0.45 Km 1348 Nos. |  | 4.07 | 2.38 | 71% | 70% | 0.92 | 04.08.21 | 31.07.23 | PWSSB | W/S, Sew, STP | Er. Harpreet Singh (8360907229) | Er. Gurdeep Arora (8837600738) | Er. Jagbir Singh (9855915440) | Work is in progress |  | 38.66%
[6 empty] | Asr-2 |  | 8 | [5 empty] | 1 No. T/Well & Rising Main | Ongoing Work | HUDCO | 1) | 2) | Tubewell | 9: 1 No; 12: 0.25; 13: 10%; 14: 0%; 15: 0; 16: 20.10.22; 17: 31.09.23; JE 23: Work is in Progress |  | 0%
[6 empty] | Asr-2 |  | 8 | [5 empty] | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) | 1) 2) 3) |  | i. Water supply Distribution Line G.I Line House Conn. | 9: 5.66KM 0.34 km 377 nos.; 10: 2.9; 16: Tender Called; JE 23: DPR under preparation stage
14 | Shri. Tript Rajinder Singh Bajwa | ਸ਼੍ਰੀ ਤ੍ਰਿਪਤ ਰਾਜਿੰਦਰ ਸਿੰਘ ਬਾਜਵਾ, 98153-60061 | Shri. Tript Rajinder Singh Bajwa | ਸ਼੍ਰੀ ਬਲਵੀਰ ਸਿੰਘ ਪੰਨੂ, 9854000002 | INC | Asr-2 | Gurdaspur | 9 | ਫਤਿਹਗੜ੍ਹ ਚੂੜੀਆਂ | 09- Fatehgarh Churian | ਫਤਿਹਗੜ੍ਹ ਚੂੜੀਆਂ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Fatehgarh Churian | Fatehgarh Churian | 3.50 MLD STP | Ongoing Work | HUDCO |  | 1) | 3.5 MLD STP | 1 No |  | 13.94 | 5.85 | Work yet to be started |  | 0 | 30.09.21 | 31.12.23 | PWSSB | W/S, Sew, STP | Er. Harpreet Singh (8360907229) | Er. Gurjinder Singh (9915355229) | Er. Aman Kumar (8837796662) | Work yet to be started |  | 0%
[6 empty] | Asr-2 |  | 9 | [5 empty] | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line G.I Line Rising main House Conn. . T/W | 9: 18.26KM 2704 mt 0.15 km. 1021 nos. 1 No.; 10: 17.06; 16: Tender Called; JE 23: DPR under preparation stage
15 | Shri. Sukhjinder Singh Randhawa | ਸ਼੍ਰੀ ਸੁਖਜਿੰਦਰ ਸਿੰਘ ਰਧਾਵਾ, 98142-12518 | Shri. Sukhjinder Singh Randhawa | ਸ੍ਰੀ ਗੁਰਦੀਪ ਸਿੰਘ ਰੰਧਾਵਾ 98723-40863 | INC | Gsp | Gurdaspur | 10 | ਡੇਰਾ ਬਾਬਾ ਨਾਨਕ | 10- Dera Baba Nanak | ਡੇਰਾ ਬਾਬਾ ਨਾਨਕ (ਸ਼੍ਰੀ ਦਵਿਤੇਸ਼ ਵਿਰਦੀ, 87288-19080) | Dera Baba Nanak | Dera Baba Nanak | DPR for Prov.Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | T/well New Dist. Network House Connection | 9: 1 No 8.80 km 1954 No.; 10: 4.54; JE 23: DPR under preparation stage
16 | Shri Kuldeep Singh Dhaliwal | ਸ਼੍ਰੀ ਕੁਲਦੀਪ ਸਿੰਘ ਧਾਲੀਵਾਲ, 82848-76662 | Shri Kuldeep Singh Dhaliwal |  | AAP | Asr-2 | Amritsar | 11 | ਅਜਨਾਲਾ | 11-Ajnala | ਅਜਨਾਲਾ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Ajnala | Ajnala | Sewerage & MPS | Ongoing Work | HUDCO |  | 1) | Lateral S.W. pipe sewer MPS House Conn. | 12.68 Km 1 No 11 MLD 2000 Nos. |  | 16.85 | 4.88 | 92% | 46% | 2.62 | 12.10.16 | 31.07.23 | PWSSB | W/S, Sew, STP | Er. Harpreet Singh (8360907229) | Er. Harpreet Singh (8360907229) | Er. Aasdeep Singh (9878615500) | Work is in Progress |  | 53.69%
[6 empty] | Asr-2 |  | 11 | [5 empty] | STP | Ongoing Work | HUDCO |  | 2) | STP (4 MLD ) | 9: 1 No; 12: 6.25; 13: 68%; 14: 29%; 15: 2.24; 16: 13.05.21; 17: 30.09.23; JE 23: Work is in Progress |  | 35.84%
[6 empty] | Asr-2 |  | 11 | [5 empty] | DPR for Prov.Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line G.I Line House Conn T/W | 9: i. W/S 7.94KM 881 mt 313 nos. 1 No.; 10: 3.08; 16: Tender Called; JE 23: DPR under preparation stage
17 | Shri Kuldeep Singh Dhaliwal | ਸ਼੍ਰੀ ਕੁਲਦੀਪ ਸਿੰਘ ਧਾਲੀਵਾਲ, 82848-76662 | Shri Kuldeep Singh Dhaliwal |  |  | Asr-2 |  | 11 | ਅਜਨਾਲਾ | 11-Ajnala | ਰਾਮਦਾਸ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Ramdass | Ramdass | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line House Conn | 9: 3.51KM 350 nos.; 10: 12.92; 16: Tender Called; JE 23: DPR under preparation stage
[6 empty] | Asr-2 |  | 11 | [6 empty] | Proposed work | SBM-2.0 |  | 2) | ii. Sewearge Main Sewer Branch Sewer STP MPS (4 MLD) | 9: ii. Sewearge 0.74 Km 13.06 km 1 no. (1.20 MLD) 1 no. (4 MLD); 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
18 | Shri. Sukhbinder Singh Sarkaria | ਸ਼੍ਰੀ ਸੁਖਬਿੰਦਰ ਸਿੰਘ ਸਰਕਾਰੀਆ, 98140-50171 | Shri. Sukhbinder Singh Sarkaria | ਸ਼੍ਰੀ ਬਲਦੇਵ ਸਿੰਘ ਮਿਆਦੀਨ , 9988588088 | INC | Asr-2 | Amritsar | 12 | ਰਾਜਾ ਸਾਂਸੀ | 12- Raja Sansi | ਰਾਜਾ ਸਾਂਸੀ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Raja Sansi | Raja Sansi | Sewerage & MPS | Ongoing Work | HUDCO |  | 1) | Sewerage = 6.74 Km House Conn. = MPS 8 MLD = 1 No | 6.74 Km - 1 No.8 MLD |  | 28.13 | 5.91 | 60% | 60% | 2.57 | 04.01.22 | 30.09.23 | ULB | - | Er. Harpreet Singh (8360907229) | Er. Deepak Kumar (7986304602) | Er. Gurbhej Singh (9888515359) | Work of sewer stopped due to want of NOC from NHAI and work of MPS yet not started due to land emarcation/ access route not provided by MC Rajasansi |  | 43.49%
[6 empty] | Asr-2 |  | 12 | [5 empty] | STP | Ongoing Work | HUDCO |  | 2) | 2 MLD | 9: 1 No; 12: 2.63; 13: Work yet to be started; 15: 0; 16: 08.01.22; 17: 31.12.23; JE 23: Land demarcation/access route not provided by MC Rajasansi |  | 0%
[6 empty] | Asr-2 |  | 12 | [5 empty] | DPR for Prov.Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line House Conn | 9: 8.36KM 585 nos.; 10: 2.17; 16: Tender Called; JE 23: DPR under preparation stage
19 | Smt. Ganieve Kaur Majithia | ਸ਼੍ਰੀਮਤੀ ਗਨੀਵ ਕੌਰ ਮਜੀਠੀਆਂ | Smt. Ganieve Kaur Majithia | ਸ਼੍ਰੀ ਲਾਲੀ ਮਜੀਠੀਆਂ, - 9815157423 | SAD | Asr-2 | Amritsar | 13 | ਮਜੀਠਾ | 13- Majitha | ਮਜੀਠਾ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Majitha | Majitha | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line House Conn. Roads T/W | 4.94 KM 435 nos. - 1 no. | 11.38 | [5 empty] | Tender Called |  | PWSSB | W/S | Er. Harpreet Singh (8360907229) | Er. Pardeep Jain (9781649578) | Er. Parampreet Singh (9646011983) | DPR under preparation stage
[6 empty] | Asr-2 |  | 13 | [6 empty] | Proposed work | SBM-2.0 |  | 2) | i. Sewearge Main Sewer MPS STP Rising Main | 9: 1.05 Km 1 No.( 7 MLD) 1 No.( 2.50MLD) 100 mtr.; 16: DPR Under check at Head Office; JE 23: DPR under preparation stage
20 | Shri. Harbhajan Singh E.T.O | ਸ਼੍ਰੀ ਹਰਭਜਨ ਸਿੰਘ ਈ.ਟੀ.ਓ, 99157-43808 | Shri. Harbhajan Singh E.T.O |  | AAP | Asr-2 | Amritsar | 14 | ਜੰਡਿਆਲਾ | 14- Jandiala | ਜੰਡਿਆਲਾ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Jandiala | Jandiala | 1 No. T/Well & Rising Main | Ongoing Work | HUDCO |  | 1) | Tubewell | 1 No |  | 3.25 | 0.24 | 80% | 42% | 0 | 23.08.22 | 31.07.23 | PWSSB | W/S, Sew, STP | Er. Harpreet Singh (8360907229) | Er. Sandeep Singh (9877089027) | Er. Kulbir Singh (9501555066) | Work in Progress |  | 0%
[6 empty] | Asr-2 |  | 14 | [5 empty] | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line House Conn. Roads | 9: i. Water supply 9.07 KM 454 nos. 5203 sqm; 10: 4.92; 16: DPR's Prepared; JE 23: DPR under preparation stage
[6 empty] | Asr-2 |  | 14 | [6 empty] | Proposed work | SBM-2.0 |  | 2) | ii. Sewearge Main Sewer Branch Sewer House Conn. Roads MPS STP Rising Main | 9: ii. Sewearge 1.20 Km 20.03 Km 4007nos. 15143 sqm 1 No.16 MLD 1 No. 5.50MLD 500mtr.; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
21 | Shri. Kunwar Viajy Pratap Singh | ਸ਼੍ਰੀ ਕੁਵੰਰ ਵਿਜੈ ਪ੍ਰਤਾਪ ਸਿੰਘ , 98140-85205 | Shri. Kunwar Viajy Pratap Singh |  | AAP | Asr-1 | Amritsar | 15 | ਅੰਮ੍ਰਿਤਸਰ ਉੱਤਰ | 15- Amritsar North | ਅੰਮ੍ਰਿਤਸਰ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Amritsar | Amritsar | [6 empty] | ULB/ PWSSB 10: -; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
22 | Dr. Jasbir Singh Sandhu | ਡਾ. ਜਸਬੀਰ ਸਿੰਘ ਸੰਧੂ, 97813-50055 | Dr. Jasbir Singh Sandhu |  | AAP | Asr-1 | Amritsar | 16 | ਅੰਮ੍ਰਿਤਸਰ ਪੱਛਮ | 16- Amritsar West | ਅੰਮ੍ਰਿਤਸਰ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Amritsar | Amritsar | [6 empty] | ULB/ PWSSB 10: -; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
23 | Shri Ajay Gupta | ਸ਼੍ਰੀ ਅਜੇ ਗੁਪਤਾ , 98158-19606 | Shri Ajay Gupta |  | AAP | Asr-1 | Amritsar | 17 | ਅੰਮ੍ਰਿਤਸਰ ਸੈਨਟਰ | 17-Amritsar Central | ਅੰਮ੍ਰਿਤਸਰ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Amritsar | Amritsar | [6 empty] | ULB/ PWSSB 10: -; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
24 | Smt. Jeevan Jyot Kaur | ਸ਼੍ਰੀਮਤੀ ਜੀਵਨ ਜੋਤ ਕੌਰ, 98155-02009 | Smt. Jeevan Jyot Kaur |  | AAP | Asr-1 | Amritsar | 18 | ਅੰਮ੍ਰਿਤਸਰ ਪੂਰਬ | 18- Amritsar East | ਅੰਮ੍ਰਿਤਸਰ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Amritsa | Amritsa | [6 empty] | ULB/ PWSSB 10: -; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
25 | Shri. Inderbir Singh Nijjar | ਡਾ. ਇੰਦਰਬੀਰ ਸਿੰਘ ਨਿੱਝਰ, 98140-52212 | Shri. Inderbir Singh Nijjar |  | AAP | Asr-1 | Amritsar | 19 | ਅੰਮ੍ਰਿਤਸਰ ਦੱਖਣ | 19-Amritsar South | ਅੰਮ੍ਰਿਤਸਰ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Amritsar | Amritsar | Sewerage Work | Ongoing Work | HUDCO |  | 1) | Restoration of RCC Road H. Conn. | 27616 sqm 3356 nos. |  | 105.7 | 3.61 | 96% | 95% | 2.98 |  | 31.07.23 | PWSSB | MPS & STP | Er. Harpreet Singh (8360907229) | Er. Sandeep Singh (9877089027) | Er. Raminder Singh (7837303529) |  |  | 82.55%
26 | Shri. Jaswinder Singh | ਸ੍ਰੀ ਜਸਵਿੰਦਰ ਸਿੰਘ , 98146-49649 | Shri. Jaswinder Singh |  | AAP | Asr-1 | Amritsar | 20 | ਅਟਾਰੀ | 20- Attari | ਅਟਾਰੀ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Attari | Attari | [6 empty] | ULB/ PWSSB 10: -; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
27 | Dr. Kashmir Singh Sohal | ਡਾ. ਕਸ਼ਮੀਰ ਸਿੰਘ ਸੋਹਲ, 98157-83229 | Dr. Kashmir Singh Sohal |  | AAP | Asr-2 | Tarn Taran | 21 | ਤਰਨਤਾਰਨ | 21- Tarn Taran | ਤਰਨਤਾਰਨ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Tarn Taran | Tarn Taran | MPS | Ongoing Work | HUDCO |  | 1) | MPS IPS | 1 Job 14 MLD with machinery 1 Job 11 MLD |  | 18.47 | 1.76 | 98% | 98% | 1.74 | 13.12.19 | 31.07.23 | ULB | - | Er. Harpreet Singh (8360907229) | Er. Sukhraj Singh (9878004748) | Er. Amit Kumar (8427566255) | Work is in progress |  | 98.86%
[6 empty] | Asr-2 |  | 21 | [5 empty] | DPR for Prov.Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line House Conn. T/W . | 9: i. Water supply 18.58 KM 3302nos. 3 nos.; 10: 8.66; JE 23: DPR under preparation stage
28 | Shri. Sarvan Singh Dhun | ਸ਼੍ਰੀ ਸਰਵਣ ਸਿੰਘ ਧੁੰਨ, 99145-00006 | Shri. Sarvan Singh Dhun |  | AAP | Asr-2 | Tarn Taran | 22 | ਖੇਮਕਰਨ | 22- Khem Karan | ਖੇਮਕਰਨ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Khem Karan | Khem Karan | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Distribution Line House Conn. T/W G.I Line | 9: 14.65 KM 2767 nos. 1 no. 6000 mt; 10: 15.35; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: Sew; EE 12: Er. Harpreet Singh (8360907229); SDE 13: Er. Sukhraj Singh (9878004748); JE 14: Er. Amit Kumar (8427566255); JE 23: DPR under preparation stage
[6 empty] | Asr-2 |  | 22 | [6 empty] | Proposed work | SBM-2.0 |  | 2) | Main Sewer Branch Sewer House Conn Roads MPS STP Rising Main | 9: 0.22 Km 6.00 Km 400 nos. - 1 NO. (7 MLD) 1 NO.( 2MLD) 80mtr.; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
29 | Shri. Sarvan Singh Dhun | ਸ਼੍ਰੀ ਸਰਵਣ ਸਿੰਘ ਧੁੰਨ, 99145-00006 | Shri. Sarvan Singh Dhun |  |  | Asr-2 |  | 22 | ਖੇਮ ਕਰਨ | 22- Khem Karan | ਭਿੱਖੀਵਿੰਡ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Bhikiwind | Bhikiwind | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S Distribution Line House Conn. T/W | 9: 11.00 KM 1711 nos. 2 no.; 10: 31.42; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: Er. Harpreet Singh (8360907229); SDE 13: Er. Sukhraj Singh (9878004748); JE 14: Er. Amit Kumar (8427566255); JE 23: DPR under preparation stage
[6 empty] | Asr-2 |  | 22 | [6 empty] | Proposed work | SBM-2.0 |  | 2) | ii. Sewearge Main Sewer Branch Sewer House Conn. Roads MPS STP Rising Main | 9: ii. Sewearge 18.00 Km 6.00 Km 132+2520 nos 14284sqm 1 NO.( 14 MLD) 1 NO.(4MLD) 550mtr.; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
30 | Shri. Laljit Singh Bhullar | ਸ਼੍ਰੀ ਲਾਲਜੀਤ ਸਿੰਘ ਭੁੱਲਰ, 98777-77722 | Shri. Laljit Singh Bhullar |  | AAP | Asr-2 | Tarn Taran | 23 | ਪੱਟੀ | 23- Patti | ਪੱਟੀ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Patti | Patti | Sewerage Work | Ongoing Work | HUDCO |  | 1) | MPS 900 mm = | 1 NO.( 22 MLD) 0.36 Km |  | 21.8 | 1.99 | 95% | 93% | 1.79 | 05.04.21 | 31.07.23 | ULB | - | Er. Harpreet Singh (8360907229) | Er. Sukhraj Singh (9878004748) | Er. Rajiv Kumar (9779080100) | Work is in progress |  | 89.95%
[6 empty] | Asr-2 |  | 23 | [5 empty] | STP | Ongoing Work | HUDCO |  | 2) | STP | 9: 8 MLD - 1 No; 12: 9.47; 13: 43%; 14: 40%; 15: 3.24; 16: 09.03.21; 17: 30.09.23; JE 23: Work is in progress |  | 34.21%
[6 empty] | Asr-2 |  | 23 | [5 empty] | DPR for Prov.Water Supply, Sew, STP, Rising Work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | i. Water supply Distribution Line House Conn.. Roads T/W | 9: i. Water supply 13.33 KM 801 nos. 3605.44 sqm 3 no.; 10: 4.44; JE 23: DPR under preparation stage
31 | Shri. Manjinder Singh Lalpura | ਸ਼੍ਰੀ ਮਨਜਿੰਦਰ ਸਿੰਘ ਲਾਲਪੁਰਾ, 98788-51049 | Shri. Manjinder Singh Lalpura |  | AAP | Asr-2 | Tarn Taran | 24 | ਖਡੂਰ ਸਾਹਿਬ | 24- Khadoor Sahib | ਖਡੂਰ ਸਾਹਿਬ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Khadoor Sahib | Khadoor Sahib | [6 empty] | EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
32 | Shri. Dalbir Singh Tong | ਸ਼੍ਰੀ ਦਲਬੀਰ ਸਿੰਘ ਟੌਗ, 98159-87642 | Shri. Dalbir Singh Tong |  | AAP | Asr-2 | Amritsar | 25 | ਬਾਬਾ ਬਕਾਲਾ | 25- Baba Bakala | ਰਈਆ (ਸ਼੍ਰੀ ਹਰਪ੍ਰੀਤ ਸਿੰਘ, 83609-07229) | Rayya | Rayya | DPR for Prov. Sew, STP, Rising Work | Proposed work | SBM-2.0 |  | 1) | i. Sewearge Main Sewer MPS STP Rising Main | i. Sewearge 0.65 Km 1 NO.(13 MLD) 1 NO.(3.50MLD 200 mtr. | 13.64 | [5 empty] | DPR checked at HO & sent to SLTC |  | ULB | -- | -- | -- | -- | DPR under preparation stage
[6 empty] | Asr-2 |  | 25 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 2 | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 8.0 Km 774 Nos. 3.68 MLD 8.50 Km 2.50 KM; 10: 13.41; JE 23: DPR under preparation stage
33 | Shri. Sukhpal Singh Khaira | ਸ਼੍ਰੀ ਸੁਖਪਾਲ ਸਿੰਘ ਖਹਿਰਾ, 98153-33333 | Shri. Sukhpal Singh Khaira | ਸ.ਰਣਜੀਤ ਸਿੰਘ ਰਾਣਾ, 98150-14638 | INC | Jal-2 | Kapurthala | 26 | ਭੁਲੱਥ | 26- Bhulath | ਭੁਲੱਥ ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Bhulath | Bhulath | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Net Dist. | 4.68 km | 1.23 | [5 empty] | DPR approved by Technical Sub Committee/ SLTC |  | PWSSB | MPS/STP (Deposit work) | Pritpal Singh 8427399114 | Pardeep Chottani 9780277086 | Amandeep Singh 9646830830 | DPR under preparation stage
34 | [5 empty] | Jal-2 |  | 26 |  |  | ਬੇਗੋਵਾਲ ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Begowal | Begowal | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 2137 Nos. 2.54 MLD 8.00 Km 6.00 KM | 13.23 | [5 empty] | DNIT approved by Technical Sub Committee |  | PWSSB | MPS/STP (Deposit work) | Pritpal Singh 8427399114 | Pardeep Chottani 9780277086 | Amandeep Singh 9646830830 | DPR under preparation stage
35 | [5 empty] | Jal-2 |  | 26 |  |  | ਨਡਾਲਾ ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Nadala | Nadala | Water Supply, | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Net Dist. T/W OHSR | 47.08 km 2 No. 1 No. | 15.04 | [5 empty] | DNIT approved by Technical Sub Committee |  | ULB | -- | Pritpal Singh 8427399114 | Pardeep Chottani 9780277086 | Amandeep Singh 9646830830 | DPR under preparation stage
[6 empty] | Jal-2 |  | 26 | [5 empty] | Sewerage Scheme | Proposed work | SBM-2.0 |  | 2) | Net Sew Line MPS STP | 9: 1.35km 1No. 3 MLD 1 No. (1 MLD); 10: 13.38; 16: DPR checked at HO & sent to SLTC; SDE 13: Pardeep Chottani 9780277086; JE 14: Amandeep Singh 9646830830; JE 23: DPR under preparation stage
36 | Shri. Sukhpal Singh Khaira | ਸ਼ੀ ਸੁਖਪਾਲ ਸਿੰਘ ਖਹਿਰਾ, 98153-33333 | Shri. Sukhpal Singh Khaira | ਸ਼੍ਰੀ ਰਣਜੀਤ ਸਿੰਘ ਰਾਣਾ, 98150 14638 |  | Jal-2 |  | 26 | ਭੁਲੱਥ | 26- Bhulath | ਢਿਲਵਾਂ ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Dhilwan | Dhilwan | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 3.00 Km 3911 Nos. 2.09 MLD 4.0 Km 6.00 KM | 12.16 | [5 empty] | DNIT approved by Technical Sub Committee |  | ULB | -- | Pritpal Singh 8427399114 | Pardeep Chottani 9780277086 | Amandeep Singh 9646830830 | DPR under preparation stage
[6 empty] | Jal-2 |  | 26 | [5 empty] | Sewerage Scheme | Proposed work | SBM-2.0 |  |  | Main Sewer STP's MPS/IPS Rising Main | 9: 0.14 km 1 No. 2 MLD 1 No's 4.2 MLD 0.075 Kms; 10: 14.3; 16: DPR checked at HO & sent to SLTC; SDE 13: Pardeep Chottani 9780277086; JE 14: Amandeep Singh 9646830830; JE 23: DPR under preparation stage
37 | Shri. Rana Gurjeet Singh | ਸ਼੍ਰੀ ਰਾਣਾ ਗੁਰਜੀਤ ਸਿੰਘ , 98159-00901 | Shri. Rana Gurjeet Singh | ਮੰਜੂ ਰਾਣਾ, 88377-01780 | INC | Jal-2 | Kapurthala | 27 | ਕਪੂਰਥਲਾ | 27- Kapurthala | ਕਪੂਰਥਲਾ (ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Kapurthala | Kapurthala | MPS & 2 MLD STP at RCF Kapurthala | Ongoing Work | Deposit work |  | 1) | 1 No. STP MPS |  |  | 9.97 | 6.68 | 91% | 34% | 2.88 | 04.01.22 | 31.08.23 | ULB | -- | Pritpal Singh 8427399114 | Gourav 7696332923 | Gurpinder Singh 7302201994 Jasbir Singh 6239264278 | Work in progress |  | 43.11%
[6 empty] | Jal-2 |  | 27 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Net Dist. OHSR House connection | 9: 94.21 km 1 No. 9500 No.; 10: 34.46; SDE 13: Gourav 7696332923; JE 14: Gurpinder Singh 7302201994 Jasbir Singh 6239264278; JE 23: DPR under preparation stage
38 | Shri. Rana Inder Partap Singh | ਸ਼੍ਰੀ ਰਾਣਾ ਇੰਦਰਪ੍ਰਤਾਪ ਸਿੰਘ, 98159-00907 | Shri. Rana Inder Partap Singh | ਸ਼੍ਰੀ ਸਾਜਨ ਸਿੰਘ ਚੀਮਾ, 98785 00759 | Independent | Jal-1 | Kapurthala | 28 | ਸੁਲਤਾਨਪੁਰ ਲੋਧੀ | 28-Sultanpur Lodhi | ਸੁਲਤਾਨਪੁਰ ਲੋਧੀ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Sultanpur Lodhi | Sultanpur Lodhi | Sewerage | Ongoing Work | Smart Cities Mission |  | 1) | Rising Main 800mm i/d DI K-7 pipe - RCC NP3 pipe line - | 4250 mtr. 2373 mtr. |  | 42.14 | 5.25 | 90% | 79% | 4.07 | 09.03.21 | 31.08.23 | ULB | -- | Jatin Vasudeva 84276-63503 | Rajwinder Singh Gill 7589200410 | -- |  |  | 77.52%
[6 empty] | Jal-1 |  | 28 | [5 empty] | MPS & 4 MLD STP | Ongoing Work | Smart Cities Mission |  | 2) | STP MPS | 1 No. 4 MLD |  | 42.14 | 8.85 | 53% | 25% | 2.18 | 13.09.21 | 30.09.23 | [5 empty] | Liquidated damages compensation imposed on firm under Clause 46 of Contract Agreement. |  | 24.63%
[6 empty] | Jal-1 |  | 28 | [5 empty] | Water Supply & Sewerage | Proposed work | Smart Cities Mission |  | 1) | Net Dist. Net Sew Line | 9: 28.34 km 1.50 km; 10: 16.07; JE 23: DPR under preparation stage
39 | Shri. Balwinder Singh Dhaliwal | ਸ੍ਰੀ ਬਲਵਿੰਦਰ ਸਿੰਘ ਧਾਲੀਵਾਲ, 98729-07282 | Shri. Balwinder Singh Dhaliwal | ਸ਼੍ਰੀ ਜੋਗਿੰਦਰ ਸਿੰਘ ਮਾਨ, 98552 00813 | INC | Jal-2 | Kapurthala | 29 | ਫਗਵਾੜਾ | 29- Phagwara | ਫਗਵਾੜਾ (ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Phagwara | Phagwara | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Net Dist. T/W | 8.65 km 5 Nos. | 5.3 | -- | -- | -- | -- | -- | -- | -- | PWSSB | W/S and Sewerage | Pritpal Singh 8427399114 | Rajwinder Singh Gill 7589200410 | Sukhwinder Singh 9814160338 | DPR under preparation stage
40 | Shri. Vikramjit Singh Chaudhary | ਸ਼੍ਰੀ ਵਿਕਰਮਜੀਤ ਸਿੰਘ ਚੌਧਰੀ, 98726-56789 | Shri. Vikramjit Singh Chaudhary | ਸ਼੍ਰੀ ਪ੍ਰੇਮ ਕੁਮਾਰ, 9815415667 | INC | Jal-2 | Jalandhar | 30 | ਗੁਰਾਇਆ | 30- Phillaur | ਫਿਲੌਰ (ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Phillaur | Phillaur | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 4.0 Km 3118 Nos. 7.00 MLD 4.70 Km 7.90 KM; 10: 20.58; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S and Sewerage; EE 12: Pritpal Singh 8427399114; SDE 13: Rajwinder Singh Gill 7589200410; JE 14: Sukhwinder Singh 9814160338; JE 23: DPR under preparation stage
41 | [5 empty] | Jal-2 |  | 30 |  |  | ਗੁਰਾਇਆ (ਸ਼੍ਰੀ ਪ੍ਰਿਤਪਾਲ ਸਿੰਘ, 84273-99114) | Goraya | Goraya | MPS & 4 MLD STP | Ongoing Work | HUDCO |  | 1) | STP MPS | 1 No. 4 MLD |  | 27.12 | 7.44 | 91% | 48% | 4.35 | 17.05.21 | 31.08.23 | ULB | W/S and Sewerage | Pritpal Singh 8427399114 | Tilak Raj 9815396156 | Nirmal Singh 9876131972 | Liquidated damages compensation imposed |  | 58.47%
[6 empty] | Jal-2 |  | 30 | [5 empty] | Rising Main | Ongoing Work | HUDCO |  | 2) | RCC P1, Rising Main (450 mm i/d ) D.I.K-7 Pipe 150mm - | 2125 mtr. 81 mtr. |  | 27.12 | 1.5 | 46% | 3% | 0 | 26.10.2022 | 31.08.23 |  |  |  | Tilak Raj 9815396156 | Nirmal Singh 9876131972 | The work of laying of Rising Main has been stopped by nearby Villagers. |  | 0%
[6 empty] | Jal-2 |  | 30 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 1.85 Km 592 Nos. 4.09 MLD 4.00 Km 6.00 KM; 10: 12.63; 16: DNIT approved by Technical Sub Committee; SDE 13: Tilak Raj 9815396156; JE 14: Nirmal Singh 9876131972; JE 23: DPR under preparation stage
42 | Smt. Inderjit Kaur Mann | ਸ਼੍ਰੀਮਤੀ ਇੰਦਰਜੀਤ ਕੌਰ ਮਾਨ, 98153-20231 | Smt. Inderjit Kaur Mann |  | AAP | Jal-1 | Jalandhar | 31 | ਨਕੋਦਰ | 31-Nakodar | ਨਕੋਦਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Nakodar | Nakodar | Revsd. DPR100% Sew. Sch. at Nakodar | Ongoing Work | HUDCO |  | 1) | Sew. H. Conn. | 37.63 Km. 4703 Nos. |  | 54.33 | 16.66 | 97% | 73% | 13.05 | 22.07.16 | 31.07.23 | PWSSB | W/S , Sew, STP, MPS | Jatin Vasudeva 84276-63503 | Deepak Kumar 99887-53149 | Ajay Kumar 98146-95925 | Work in Progress. 2% LD imposed |  | 78.33%
[6 empty] | Jal-1 |  | 31 | [5 empty] | W/S lines | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Rehabitation of W/S , W/S H. Conn. | 9: 6.79 Km., 22.12 Km., 1843 Nos.,; 10: 10.23; JE 23: DPR under preparation stage
43 | [5 empty] | Jal-1 |  | 31 |  |  | ਨੂਰਮਹਿਲ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Nurmehal | Nurmehal | W/S Scheme | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S H.Conn. | 1.11 Km., 139 Nos. | 0.39 | -- | [6 empty] | ULB | -- | -- | -- | -- | DPR under preparation stage
44 | [5 empty] | Jal-1 |  | 31 |  |  | ਬਿਲਗਾ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Bilga | Bilga | Shifting of W/S | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S G.I.Pipe H.Conn. | 2.29 Km., 12.08 Km., 287 Nos. | 1.76 | -- |  |  |  |  | DNIT approved by Technical Sub Committee |  | ULB | -- | -- | -- | -- | DPR under preparation stage
[6 empty] | Jal-1 |  | 31 | [5 empty] | Sew. Scheme | Proposed work | SBM-2.0 |  | 2) | Sew H.Conn. MPS STP | 9: 29.02 Km., 3639 Nos., 1 No., 1 No.,; 10: 52.62; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
45 | Shri. Hardev Singh Laddi | ਸ਼੍ਰੀ ਹਰਦੇਵ ਸਿੰਘ ਲਾਡੀ, 98140-37387 | Shri. Hardev Singh Laddi | ਸ਼੍ਰੀ ਕੱਕਰ ਕੱਲਾ, 82840-02230 | INC | Jal-1 | Jalandhar | 32 | ਸ਼ਾਹਕੋਟ | 32- Shahkot | ਸ਼ਾਹਕੋਟ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Shahkot | Shahkot | Sew. Scheme | Ongoing Work | HUDCO |  | 1) | STP | 1 No. |  | 8.17 | 4.5 | 95% | 92% | 2.89 | 01.04.16 | 31.07.23 | PWSSB | STP, MPS (Deposit Work) | Jatin Vasudeva 84276-63503 | Deepak Kumar 99887-53149 | Ajay Kumar 98146-95925 | STP under Stabilization |  | 64.22%
[6 empty] | Jal-1 |  | 32 | [5 empty] | W/S Scheme | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S T/Well H.Conn. | 9: 1.81 Km., 1 No., 226 Nos.,; 10: 0.73; 16: DNIT approved by Technical Sub Committee; JE 23: DPR under preparation stage
46 | [5 empty] | Jal-1 |  | 32 |  |  | ਲੋਹੀਆਂ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Lohian | Lohian | W/S Scheme | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S | 5.06 Km. | 1.05 | -- | [6 empty] | ULB | - | .- | - | - | DPR under preparation stage
[6 empty] | Jal-1 |  | 32 | [5 empty] | Sew. Scheme | Proposed work | SBM-2.0 |  | 2) | Sew H.Conn. MPS STP R/Main Land | 9: 33.82 Km., 2415 Nos., 1 No., 1 No., 2.05 Km., 1.50 Acre,; 10: 54.57; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
47 | Shri. Hardev Singh Laddi | ਸ਼੍ਰੀ ਹਰਦੇਵ ਸਿੰਘ ਲਾਡੀ, 98140-37387 | Shri. Hardev Singh Laddi |  |  | Jal-1 |  | 32 | ਸ਼ਾਹਕੋਟ | 32- Shahkot | ਮਹਿਤਪੁਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Mehatpur | Mehatpur | W/S Scheme | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S G.I H.Conn. | 3.04 Km. 2.67 Km. 485 Nos. | 1.1 | -- | [6 empty] | ULB | - | - | - | - | DPR under preparation stage
[6 empty] | Jal-1 |  | 32 | [5 empty] | Sew. Scheme | Proposed work | SBM-2.0 |  | 2) | Sew H.Conn. MPS STP R/Main Land | 9: 37.28 Km. 3106 Nos. 1 No. 1 No. 1.56 Km. 1.50 Acre; 10: 56.22; 16: DPR Under check at Head Office; JE 23: DPR under preparation stage
48 | Shri Balkar Singh | ਸ਼੍ਰੀ ਬਲਕਾਰ ਸਿੰਘ, 98140-37387 | Shri Balkar Singh |  | AAP | Jal-1 | Jalandhar | 33 | ਕਰਤਾਰਪੁਰ | 33- Kartarpur | ਕਰਤਾਰਪੁਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Kartarpur | Kartarpur | 100% Sew. Sch. at Kartarpur | Ongoing Work | HUDCO |  | 1) | MPS R/ Main (DI K9 Pipe) | 1 No. 1.21 Km. |  | 6.82 | 1.05 | 95% | 52% | 0.51 | 21.08.19 | 31.07.23 | ULB | - | - | - | - | Work in Progress. |  | 48.57%
[6 empty] | Jal-1 |  | 33 | [6 empty] | Ongoing Work | HUDCO |  | 2) | STP | 9: 1 No. (4 MLD); 12: 3.63; 13: 53%; 14: 0%; 15: 0.25; 16: 08.07.21; 17: 30.09.23; JE 23: Work in Progress. 1% LD imposed |  | 6.887%
[6 empty] | Jal-1 |  | 33 | [5 empty] | W/S Scheme | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S H.Conn. | 9: 3.45 Km. 230 Nos.; 10: 1.19; JE 23: DPR under preparation stage
49 | Shri Sheetal Angural | ਸ਼੍ਰੀ ਸ਼ੀਤਲ ਅੰਗੁਰਾਲ, 78373-10000 | Shri Sheetal Angural |  |  | Jal-1 |  | 33 | ਜਲੰਧਰ ਪੱਛਮ | 34- Jalandhar West | ਜਲੰਧਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Jalandhar | Jalandhar | Prov. Bulk Surface Water Supply Sch. Const. of 275 MLD WTP, Jal. | Ongoing Work | AMRUT |  | 1) | W/S. WTP UGSR | 118.50 Km. 1 No. 5 Nos. |  | 862.69 | 465.2 | 40% | 23.75% | 278.5 | 10.09.20 | 09.09.23 | ULB | - | - | - | - |  |  | 59.87%
50 | Shri. Raman Arora | ਸ਼੍ਰੀ ਰਮਨ ਅਰੋੜਾ, 98786-54865 | Shri. Raman Arora |  | AAP | Jal-1 | Jalandhar | 35 | ਜਲੰਧਰ ਸੈਨਟਰ | 35- Jalandhar Central | ਜਲੰਧਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Jalandhar | Jalandhar | Shifting of damaged 42" i/d Sew. at Surya Enclave, Jal. | Ongoing Work | AMRUT |  | 1) | Sew. | 0.75 Km. |  | 1.88 | 1.32 | 98% | 45% | 1.09 | 26.11.21 | 31.07.23 | ULB | - | - | - | - | Work in Progress. |  | 82.58%
51 | Shri. Avtar Singh Junior | ਸ਼੍ਰੀ ਅਵਤਾਰ ਸਿੰਘ ਜੂਨੀਅਰ , 98888-69000 | Shri. Avtar Singh Junior | ਸ਼੍ਰੀ ਦਿਨੇਸ਼ ਧੱਲ, 98550-00060 | INC | Jal-1 | Jalandhar | 36 | ਜਲੰਧਰ ਉਤਰ | 36- Jalandhar North | ਜਲੰਧਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Jalandhar | Jalandhar | [6 empty] | ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: -; SDE 13: -; JE 14: -; JE 23: Presently no work ongoing by PWSSB
52 | Shri. Pargat Singh Powar | ਸ਼੍ਰੀ ਪਰਗਟ ਸਿੰਘ , 94635-00077 | Shri. Pargat Singh Powar | ਸ਼੍ਰੀ ਸੁਰਿੰਦਰ ਸਿੰਘ ਸੋਢੀ , 97798-00022 | INC | Jal-1 | Jalandhar | 37 | ਜਲੰਧਰ ਛਾਉਣੀ | 37-Jalandhar Cantt. | ਜਲੰਧਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Jalandhar | Jalandhar | Sew. Sch. of 12 Villages at Jalandhar | Ongoing Work | AMRUT |  | 1) | Sew. H. Conn. | 17.25 Km. 939 Nos. |  | 66.91 | 7.66 | 99% | 78% | 5.76 | 24.07.20 | 30.06.23 | ULB | - | - | - | - | Work in Progress. 0.5% LD imposed. |  | 75.2%
[6 empty] | Jal-1 |  | 37 | [5 empty] | Ext. of Storm Water Sewer | Ongoing Work | AMRUT |  | 2) | Sew. | 2.25 Km. |  | 67.29 | 15.49 | 99% | 86% | 13.4 | 31.12.20 | 30.06.23 | [5 empty] | Work in Progress. |  | 86.51%
[6 empty] | Jal-1 |  | 37 | [5 empty] | Ext. of Storm Water Sewer | Ongoing Work | AMRUT |  | 3) | Sew. | 9: 7.07 Km; 12: 37.8; 13: 98%; 14: 91%; 15: 33.93; 16: 31.12.20; 17: 30.06.23; JE 23: Work in Progress. |  | 89.76%
[6 empty] | Jal-1 |  | 37 | [5 empty] | W/S Scheme | Proposed work | AMRUT 2.0 |  | 1) | W/S T/Well OHSR (1.00 Lakh Gls Cap.) 1 No. (0.50 lakh Gls Cap.) H.Conn. | 9: 128.68 Km. 1 No. 2 Nos. 6773 Nos.; 10: 39.48; JE 23: DPR under preparation stage
[6 empty] | Jal-1 |  | 37 | [5 empty] | Balance work Sew. Scheme | Proposed work | AMRUT 2.0 |  | 2) | Sew H.Conn. W/S G.I line R/Main IPS | 9: 35.35 Km. 9753 Nos. 6.115 Km. 0.630 Km. 1 No.; 10: 34.94; JE 23: DPR under preparation stage
[6 empty] | Jal-1 |  | 37 | [5 empty] | Sew. Scheme 12 Village of H. Conn. | Proposed work | AMRUT 2.0 |  | 3) | Sew H.conn. | 9: 1.90 Km. 2081 Nos.; 10: 2.93; JE 23: DPR under preparation stage
[6 empty] | Jal-1 |  | 37 | [5 empty] | W/S at Ward No.6 & 7 at Malko | Proposed work | AMRUT 2.0 |  | 4) | W/S T/Well | 9: 3.62 Km. 1 No.; 10: 1.35; JE 23: DPR under preparation stage
53 | Shri. Sukhwinder Singh Kotli | ਸ਼੍ਰੀ ਸੁਖਵਿੰਦਰ ਸਿੰਘ ਕੋਟਲੀ, 98154-29615 | Shri. Sukhwinder Singh Kotli | ਸ਼੍ਰੀ ਜਿੱਤਲਾਲ ਭੱਟੀ, 98882-13737 | INC | Jal-1 | Jalandhar | 38 | ਆਦਮਪੁਰ | 38-Adampur | ਆਦਮਪੁਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Adampur | Adampur | Sew. Sch. including H. Conn | Ongoing Work | HUDCO |  | 1) | Sew. H. Conn. | 16.80 3733 Nos. |  | 10.44 | -- | -- | -- | 0 | -- | 1 year from date of start | ULB | - | - | - | - | The work could not be started due to non release of requisite funds by PIDB/ Punjab Govt. |  | #VALUE!
[6 empty] | Jal-1 |  | 38 | [5 empty] | Sew. Sch & STP. including H. Conn | Ongoing Work | HUDCO |  | 2) | Sew. H. Conn. | 7.94 Km. 794 Nos. |  | 17.25 | 3.03 | 87% | 66% | 2.4 | 29.10.21 | 30.09.23 | [5 empty] | Work in Progress. |  | 79.21%
[6 empty] | Jal-1 |  | 38 | [6 empty] | Ongoing Work | HUDCO |  | 2) | STP | 9: 1 No. (3 MLD); 12: 3.16; 13: 52%; 14: 5.36%; 15: 0.16; 16: 08.07.21; 17: 30.09.23; JE 23: Work in Progress. 1% LD imposed |  | 5.063%
[6 empty] | Jal-1 |  | 38 | [5 empty] | W/S Scheme | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S H.Conn. | 9: 3.83 Km. 479 Nos.; 10: 1.27; JE 23: DPR under preparation stage
54 | Shri. Sukhwinder Singh Kotli | ਸ਼੍ਰੀ ਸੁਖਵਿੰਦਰ ਸਿੰਘ ਕੋਟਲੀ, 98154-29615 | Shri. Sukhwinder Singh Kotli |  |  | Jal-1 | Jalandhar | 38 | ਆਦਮਪੁਰ | 38-Adampur | ਅਲਾਵਲਪੁਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Alawalpur | Alawalpur | W/S Scheme | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S H.Conn | 0.79 Km. 200 Nos. | 0.27 | -- | [6 empty] | ULB | - | - | - | - | DPR under preparation stage
[6 empty] | Jal-1 |  | 38 | [5 empty] | Sew. Scheme | Proposed work | SBM-2.0 |  | 2) | Sew H.Conn MPS STP R/Main. Land | 9: 17.48 Km. 2445 Nos. 1 No. 1 No. 0.10 Km. 1.00 Acre; 10: 24.87; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
55 |  | ਸ਼੍ਰੀ ਸੁਖਵਿੰਦਰ ਸਿੰਘ ਕੋਟਲੀ, 98154-29615 |  |  |  | Jal-1 |  | 38 | ਆਦਮਪੁਰ |  | ਭੋਗਪੁਰ (ਸ਼੍ਰੀ ਜਿਤਿਨ ਵਾਸੁਦੇਵਾ, 84276-63503) | Bhogpur | Bhogpur | Sew. Scheme | Ongoing Work | MDF |  | 1) | Sew. House Conn. | 4.69 Km. 250 Nos. |  | 57.98 | 3.68 | 20% | 5.51% | 0.2 | 10.11.21 | 31.07.23 | ULB | - | - | - | - | Work in Progress. |  | 5.435%
[6 empty] | Jal-1 |  | 38 | [5 empty] | W/S Scheme | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S H Conn. | 9: 1.75 Km. 70 Nos.; 10: 0.42; 16: DPR approved by Technical Sub Committee/SLTC; JE 23: DPR under preparation stage
[6 empty] | Jal-1 |  | 38 | [5 empty] | Sew. Scheme | Proposed work | SBM-2.0 |  | 2) | Sew H.Conn MPS STP R/Main | 9: 45.62 Km. 5703 Nos. 1 No. 1 No. 2.45 Km.; 10: 73.54; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
56 | Shri. Jangi Lal Mahajan | ਸ਼੍ਰੀ ਜੰਗੀ ਲਾਲ ਮਹਾਜਨ, 94172-44156 | Shri. Jangi Lal Mahajan | ਪ੍ਰੋ. ਮੁਲਤਾਨੀ, 80549 26505 | BJP | Hsp | Hoshiarpur | 39 | ਮੁਕੀਰਿਅਨ | 39- Mukerian | ਮੁਕੇਰਿਆਂ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Mukierian | Mukierian | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | 100mm i/d 150mm i/d 200mm i/d 250mm i/d Tubewell | 9: 33580 Mtr 4730 Mtr 1380 Mtr 100 Mtr 4 Nos; 10: 16.34; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: 5 MLD STP; EE 12: Er. Arvind Mehta Mob. No.9888861602; SDE 13: Er. Daljeet Kumar Bhandari Mob. No.9463852437; JE 14: Sh. Jaspreet Singh Mob. No.9915360058; JE 23: DPR under preparation stage
57 | Shri. Karambir Singh | ਸ਼੍ਰੀ ਕਰਮਬੀਰ ਸਿੰਘ, 98140-07599 | Shri. Karambir Singh |  | AAP | Hsp | Hoshiarpur | 40 | 40- Dasuya | 40- Dasuya | ਦਸੂਆ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Dasuya | Dasuya | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 40.0 Km 477 Nos. 6.50 MLD 5.00 Km 9.00 KM; 10: 40.94; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: -; SDE 13: -; JE 14: -; JE 23: DPR under preparation stage
58 | [5 empty] | Hsp |  | 40 |  |  | ਤਲਵਾੜਾ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Talwara | Talwara | UPVC/RCC NP-3 Pipe Sewer, | Ongoing Work | Special Assistance |  | 1) | Sewerage line | 11.46 Km |  | 28.51 | 5.88 | 46% | 40% | 4.45 | 24.12.21 | 30.09.23 | PWSSB | W/S | Er. Arvind Mehta Mob. No.9888861602 | Er. Daljeet Kumar Bhandari Mob. No.9463852437 | Sh. Jaskamal Singh Mob.No.9041672146 |  |  | 75.68%
[6 empty] | Hsp |  | 40 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 462 Nos. 4.60 MLD 2.00 Km 8.00 KM; 10: 15.23; JE 23: DPR under preparation stage
59 | Shri, Jasvir Singh Raja Gill | ਸ਼੍ਰੀ ਜਸਵੀਰ ਸਿੰਘ ਰਾਜਾ ਗਿੱਲ, 98544-00002 | Shri, Jasvir Singh Raja Gill |  | AAP | Hsp | Hoshiarpur | 41 | ਉਰਮਾਰ | 41- Urmar | ਟਾਂਡਾ ਉੜਮਾਰ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Tanda Urmar | Tanda Urmar | UPVC/RCC NP-3 Pipe Sewer, | Ongoing Work | Balance Work |  | 1) | Sewerage line | 7.42 Km |  | 8.56 | 3.04 | 95% | 68% | 2.08 | 10.11.21 | 31.07.23 | PWSSB | W/S, Sew, STP | Er. Arvind Mehta Mob. No.9888861602 | Er. Daljeet Kumar Bhandari Mob. No.9463852437 | Sh. Jaskamal Singh Mob.No.9041672146 |  |  | 68.42%
[6 empty] | Hsp |  | 41 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 2.0 Km 902 Nos. 6.18 MLD 15.00Km 13.00 KM; 10: 30.06; JE 23: DPR under preparation stage
[6 empty] | Hsp |  | 41 | [5 empty] | Sewerage | Proposed work | Deposit work |  | 1) | 200mm i/d 250mm i/d | 9: 230 Mtr 980 Mtr; 10: 2.25; JE 23: DPR under preparation stage
60 | Shri, Jasvir Singh Raja Gill | ਸ਼੍ਰੀ ਜਸਵੀਰ ਸਿੰਘ ਰਾਜਾ ਗਿੱਲ, 98544-00002 | Shri, Jasvir Singh Raja Gill |  |  | Hsp |  | 41 | ਉਰਮਾਰ | 41- Urmar | ਗੜ੍ਹਦੀਵਾਲਾ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Garhdiwala | Garhdiwala | UPVC/RCC NP-3 Pipe Sewer, | Ongoing Work | HUDCO |  | 1) | Sewerage line | 28.311 Km |  | 14.47 | 9.26 | 92% | 75% | 6.9 | 23.10.19 | 30.06.23 | PWSSB | Sew | Er. Arvind Mehta Mob. No.9888861602 | Er. Daljeet Kumar Bhandari Mob. No.9463852437 | Sh. Jaspreet Singh Mob. No.9915360058 |  |  | 74.51%
[6 empty] | Hsp |  | 41 | [5 empty] | STP | Ongoing Work | HUDCO |  | 2) | STP | 9: 1 No.; 12: 3.14; 13: 85%; 14: 62%; 15: 1.95; 16: 24.12.20; 17: 31.07.23 |  | 62.1%
[6 empty] | Hsp |  | 41 | [5 empty] | New Tubewell | Ongoing Work | HUDCO |  | 3) | Tubewell | 9: 1 No Tubewell; 11: 0.34; 12: 0.3; 13: 95%; 14: 61%; 15: 0.2; 16: 03.10.22; 17: 30.06.23
[6 empty] | Hsp |  | 41 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  |  | Tubewell House Connection | 9: 1 No. 180 Nos.; 10: 0.29; JE 23: DPR under preparation stage
61 | Dr. Ravjot Singh | ਡਾ. ਰਵਜੋਤ ਸਿੰਘ , 94634-70000 | Dr. Ravjot Singh |  | AAP | Hsp | Hoshiarpur | 42 | ਸ਼ਾਮਚੁਰਾਸੀ | 42-Sham Chaurasi | ਸ਼ਾਮਚੁਰਾਸੀ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Sham Chaurasi | Sham Chaurasi | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | 100mm i/d | 9: 2095 Mtr; 10: 0.48; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: -; SDE 13: -; JE 14: -; JE 23: DPR under preparation stage
62 | [5 empty] | Hsp |  | 42 |  |  | ਹਰਿਆਣਾ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Hariana | Hariana | STP 2 MLD | Ongoing Work | HUDCO |  | 1) | STP | 1 No. 2 MLD |  | 14 | 3.14 | 100% | 100% | 3.1 | 24.12.20 | 31.01.23 | PWSSB | 6 MLD MPS | Er. Arvind Mehta Mob. No.9888861602 | Er.Arun Kalyan Mob. No.8699373495 | Sh. Jaspreet Singh Mob. No.9915360058 | Work Completed |  | 98.73%
[6 empty] | Hsp |  | 42 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | 100mm i/d 150mm i/d | 9: 1600 Mtr 327 Mtr; 10: 0.8; JE 23: DPR under preparation stage
63 | Shri. Bram Shanker (Jimpa) | ਸ਼੍ਰੀ ਬ੍ਰ੍ਮ ਸੰਕਰ ਸ਼ਰਮਾ, 98774-90267 | Shri. Bram Shanker (Jimpa) |  | AAP | Hsp | Hoshiarpur | 43 | ਹੁਸ਼ਿਆਰਪੁਰ | 43-Hoshiarpur | ਹੁਸ਼ਿਆਰਪੁਰ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Hoshiarpur | Hoshiarpur | Tubewell | Ongoing Work | HUDCO |  | 1) | Tubewell | 1 No. |  | 0.34 | 0.3 | 100% | 81% | 0.22 | 16.11.22 | 15.02.23 | PWSSB | 30 MLD STP & MPS | Er. Arvind Mehta Mob. No.9888861602 | Er.Arun Kalyan Mob. No.8699373495 | Sh. Jaspreet Singh Mob. No.9915360058 | Work Completed |  | 73.33%
[6 empty] | Hsp |  | 43 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0 |  | 1) | 100mm i/d 160mm i/d | 9: 21447 Mtr 670 Mtr; 10: 7.18; JE 23: DPR under preparation stage
[6 empty] | Hsp |  | 43 | [5 empty] | Sewerage | Proposed work | AMRUT 2.0 |  | 2) | 160mm o/d 200mm o/d 250mm o/d 315mm o/d 800mm i/d 900mm i/d | 9: 11006 mtr 9928 mtr 1540 mtr 800 mtr 1700 mtr 1100 Mtr.; 10: 33.53; JE 23: DPR under preparation stage
[6 empty] | Hsp |  | 43 | [5 empty] | Sewerage | Proposed work | Deposit work |  | 3) | 315mm o/d 1200mm i/d | 9: 200 mtr 1800 mtr; 10: 4.71; JE 23: DPR under preparation stage
64 | Dr. Raj Kumar | ਡਾ. ਰਾਜ ਕੁਮਾਰ , 98157-44705 | Dr. Raj Kumar | ਹਰਮਿੰਦਰ ਸਿੰਘ ਸੰਧੂ 98550-56187 | INC | Hsp | Hoshiarpur | 44 | ਚੱਬੇਵਾਲ | 44-Chabbewal | ਚੱਬੇਵਾਲ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Chabbewal | Chabbewal | [6 empty] | ULB/ PWSSB 10: -; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
65 | Shri. Jai Krishan | ਸ਼੍ਰੀ ਜੈ ਕ੍ਰਿਸ਼ਨ ਸਿੰਘ, 95928-54542 | Shri. Jai Krishan |  | AAP | Hsp | Hoshiarpur | 45 | ਗੜ੍ਹਸ਼ੰਕਰ | 45-Garhshankar | ਗੜ੍ਹਸ਼ੰਕਰ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Garhshankar | Garhshankar | STP | Ongoing Work | HUDCO |  | 1) | STP | 1 No. 3 MLD |  | 13.39 | 5.23 | 20% | 0 |  | 10.10.22 | 30.09.23 | PWSSB | MPS | Er. Arvind Mehta .9888861602 | Sushil Bansal 8196087000 | Aman Deep Singh 9855019650 | Yet to be started |  | 0%
[6 empty] | Hsp |  | 45 | [5 empty] | Sewerage | Proposed work | SBM-2.0 |  | 1) | 160mm o/d - 400 mm i/d | 9: 9.827 KM; 10: 9.98; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage |  |  | 9827
[6 empty] | Hsp |  | 45 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 2) | 100mm i/d | 9: 2719 Mtr; 10: 0.6; JE 23: DPR under preparation stage
[6 empty] | Hsp |  | 45 |  |  | ਮਾਹਿਲਪੁਰ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Mahilpur | Mahilpur | Sewerage | Proposed work | SBM-2.0 |  |  | Main Sewer STP's MPS/IPS Rising Main | 1.26 Km 1 No's 2 MLD 1 No's 7 MLD (0.1 Kms | 8.64 | [5 empty] | DPR checked at HO & sent to SLTC |  | ULB | - | - | - | - | DPR under preparation stage
67 | Dr. Sukhwinder Kumar Sukhi | ਡਾ. ਸੁਖਵਿੰਦਰ ਕੁਮਾਰ ਸੁੱਖੀ, 98726-27998 | Dr. Sukhwinder Kumar Sukhi | ਸ਼੍ਰੀ ਕੁਲਜੀਤ ਸਰਹਾਲੀ, 99150 89377 | SAD | Hsp | SBS Nagar | 46 | ਬੰਗਾ | 46-Banga | ਬੰਗਾ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Banga | Banga | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 2.0Km 1940 Nos. 5.45 MLD 10.00 Km 5.00 KM; 10: 20.5; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S, Sew; EE 12: Er. Arvind Mehta .9888861602; SDE 13: Ranjit Singh 9855521730; JE 14: Balbir Singh 8463474850; JE 23: Presently no work ongoing by PWSSB
68 | Dr. Nachhatar Pal | ਡਾ. ਨਛੱਤਰ ਪਾਲ , 94631-80300 | Dr. Nachhatar Pal | ਸ਼੍ਰੀ ਬੱਲੂ ਪ੍ਰਧਾਨ ਪਾਠਕ, 98140 43655 | BSP | Hsp | Nawan Shahar | 47 | ਨਵਾਂ ਸ਼ਹਿਰ | 47-Nawan Shahr | ਰਾਹੋਂ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Rahon | Rahon | Sewerage | Work Completed | HUDCO |  | 1) | Sewerage line | 9: 6.864 Km; 11: 9.15; 12: 4.12; 13: 100%; 14: 100%; 16: 24.12.16; 17: Completed; JE 23: Work Completed |  | 0%
[6 empty] | Hsp |  | 47 | [5 empty] | STP | Ongoing Work | HUDCO |  | 2) | STP | 1 No. 3 MLD |  | 9.15 | 5.5 | 7% | 0% |  | 14.10.22 | 13.07.23 | ULB | - | - | - | - | Yet to be started |  | 0%
[6 empty] | Hsp |  | 47 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 3.0Km 1133 Nos. 3.81 MLD 10.00 Km 18.00 KM; 10: 30.21; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: -; SDE 13: -; JE 14: -; JE 23: DPR under preparation stage
[6 empty] | Hsp |  | 47 | [5 empty] | Sewerage | Proposed work | SBM-2.0 |  |  | STP | 1 No's 3 MLD | 8.82 | [5 empty] | DPR yet to be received in Head Office |  | ULB | - | - | - | - | DPR under preparation stage
69 | [5 empty] | Hsp |  | 47 |  |  | ਨਵਾਂ ਸ਼ਹਿਰ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | 2.Nawan Shahr | 2.Nawan Shahr | Sewerage | Ongoing Work | MDF |  | 1) | Sewerage line | 12.930 Km |  | 14.34 | 7.3 | 95% | 85% | 7.1 | 28.10.21 | 30.06.23 | PWSSB | Water Supply | Er. Arvind Mehta 9888861602 | Ranjit Singh 9855521730 | Mukhtiar Singh 8872939351 |  |  | 97.26%
[6 empty] | Hsp |  | 47 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 23.50 Km 751 Nos. 11.63 MLD 15.00 Km 05.00 KM; 10: 34.55; JE 23: DPR under preparation stage
70 | Smt. Santosh Kumari Katariaa | ਸ਼੍ਰੀਮਤੀ ਸੰਤੋਸ਼ ਕੁਮਾਰੀ ਕਟਾਰੀਆਂ, 98152-35235 | Smt. Santosh Kumari Katariaa |  | AAP | Hsp | SBS Nagar | 48 | ਬਲਾਚੌਰ | 48-Balachaur | ਬਲਾਚੌਰ (ਸ਼੍ਰੀ ਅਰਵਿੰਦ ਮਹਿਤਾ, 98888-61602) | Balachaur | Balachaur | STP | Ongoing Work | HUDCO |  | 1) | STP | STP 4 MLD |  | 18.94 | 6.23 | 80% | 60% | 2.1 | 05.07.19 | 31.07.23 | PWSSB | Water Supply | Er. Arvind Mehta 9888861602 | Ranjit Singh 9855521730 | Mukhtiar Singh 8872939351 |  |  | 33.71%
[6 empty] | Hsp |  | 48 | [5 empty] | W/S | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Dist.network House Connection OHSR (1.0 LG Capacity) | 9: 16.00 Km 1631 Nos. 1 Nos.; 10: 5.59; JE 23: DPR under preparation stage
71 | Shri Harjot Singh Bains | ਸ਼੍ਰੀ ਹਰਜੋਤ ਸਿੰਘ ਬੈਂਸ, 0172-270024 | Shri Harjot Singh Bains |  | AAP | Ropar | Roopnagar | 49 | ਆਨੰਦਪੁਰ ਸਾਹਿਬ | 49- Anandpur Sahib | ਆਨੰਦਪੁਰ ਸਾਹਿਬ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Anandpur Sahib | Anandpur Sahib | W/S, R/Main | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S Lines R/Main | 7.60 Kms. 1.30 Kms. | 2.67 | --- | --- | --- | --- | --- | --- | --- | DWSS | - | Pankaj Jain 8427663504 | Baljit Singh 8284914999 | Kulwinder Singh 9465077970 | DPR under preparation stage
72 | [5 empty] | Ropar |  | 49 |  |  | ਕੀਰਤਪੁਰ ਸਾਹਿਬ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Kiratpur Sahib | Kiratpur Sahib | Sewer, R/Main | Proposed work | SBM-2.0 |  | 1) | Sewer Lines IPS R/Main STP (2 MLd) | 20 Kms. 2 Nos. 2.00 Kms. 1No | 24.95 | --- | --- | --- | --- | --- | DPR checked at HO & sent to SLTC | --- | PWSSB | STP,WTP. MPS (Deposit work) | Pankaj Jain 8427663504 | Baljit Singh 8284914999 | Kulwinder Singh 9465077970 | DPR under preparation stage
[6 empty] | Ropar |  | 49 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 2) | T/Well- W/S House connt. | 1 No. 6.57 Kms 500 Nos. | 3.08 | --- | --- | --- | --- | --- |  |  |  |  | Pankaj Jain 8427663504 | Baljit Singh 8284914999 | Kulwinder Singh 9465077970 | DPR under preparation stage
73 | Shri Harjot Singh Bains | ਸ਼੍ਰੀ ਹਰਜੋਤ ਸਿੰਘ ਬੈਂਸ, 0172-270024 | Shri Harjot Singh Bains |  |  | Ropar |  | 49 | ਆਨੰਦਪੁਰ ਸਾਹਿਬ | 49- Anandpur Sahib | ਨੰਗਲ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Nangal | Nangal | Water Supply,Sewerage, Tubewell | Ongoing Work | Deposit work |  | 1) | W/S Lines - Sewer Lines - Tubewell - | 4.64 Km 6.27 Kms 2 Nos. |  | 4.83 | 3.93 | 50% | 6% | 0.13 | 14.12.21 | --- | PWSSB | STP,WTP (Deposit work) | Pankaj Jain 8427663504 | Tarun Gupta 9888607639 | Kulwinder Singh 9465077970 | Funds yet to be received from MC. |  | 3.308%
[6 empty] | Ropar |  | 49 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 2) | W/S Rehabilitation line House connt. Upgradation of WTP | 9: 8.00 Kms 800 Nos. 2 Nos.; 10: 8.84; JE 23: DPR under preparation stage
[6 empty] | Ropar |  | 49 | [5 empty] | WTP, Sewer, MPS, STP | Proposed work | Deposit work |  | 1) | WTP Sewer Lines IPS STP | 9: 1 No. 6.00 Kms. 1 No. 2 Nos.; 10: 24.8; JE 23: DPR under preparation stage
74 | Shri. Dinesh Kumar Chadha | ਸ਼੍ਰੀ ਦਿਨੇਸ਼ ਚੱਢਾ, 99155-77950 | Shri. Dinesh Kumar Chadha |  | AAP | Ropar | Roopnagar | 50 | ਰੂਪਨਗਰ | 50- Rupnagar | ਰੂਪਨਗਰ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Rupnagar | Rupnagar | Water Supply,Sewerage, IPS,Tubewell | Ongoing Work | MDF / MC Deposit work |  | 1) | W/S Lines - Sewer Lines - IPS - Tubewell - | 4.35 Kms 4.21 Kms 1 Nos 1 No. |  | 6.28 | 2.94 | 70% | 60% | 1.94 | 07.07.21 | 30.09.23 | PWSSB | STP, MPS,WTP (Deposit work) | Pankaj Jain 8427663504 | Rakesh Mehta 9216870070 | Pardeep Sharma 9465888557 | Land for IPS near NCC academy yet to be made available by MC. |  | 65.99%
[6 empty] | Ropar |  | 50 | [5 empty] | Raw Water pipeline | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Dist. Network House Connection Raw water pipeline | 9: 0.97 Km 150 Nos.; 10: 4.83; 16: DNIT approved by Technical Sub Committee; JE 23: DPR under preparation stage
75 | Shri. Charanjit Singh | ਡਾ. ਚਰਨਜੀਤ ਸਿੰਘ , 98153-60112 | Shri. Charanjit Singh |  | AAP | Ropar | Roopnagar | 51 | ਚਮਕੌਰ ਸਾਹਿਬ | 51-Chamkaur Sahib | ਚਮਕੌਰ ਸਾਹਿਬ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Chamkaur Sahib | Chamkaur Sahib | Water Supply, Sewerage, R/Main, Tubewell | Ongoing Work | MDF |  | 1) | W/S Lines Sewer Lines - R/Main - Tubewell - | 3.77 Kms 2.74 Kms. 0.54 Kms. 3 Nos. |  | 5.12 | 2 | 100% | 100% | 3.05 | 14.12.21 | 31.07.23 | PWSSB | Sew Scheme (Deposit work) | Pankaj Jain 8427663504 | Arvind Mehta 9888861602 | Pardeep Sharma 9465888557 | --- |  | 152.5%
[6 empty] | Ropar |  | 51 | [5 empty] | Surface Water Supply, OHSR, STP | Proposed work | MDF |  | 1) | STP | 9: 1 No.; 10: 17.57; JE 23: DPR under preparation stage
[6 empty] | Ropar |  | 51 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network OHSR House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 1.58 Km 1 No. 350 Nos. 3.59 MLD 0.20 Km 5.30 KM; JE 23: DPR under preparation stage
76 | Shri. Charanjit Singh | ਡਾ. ਚਰਨਜੀਤ ਸਿੰਘ , 98153-60112 | Shri. Charanjit Singh |  |  | Ropar | Roopnagar | 51 | ਚਮਕੌਰ ਸਾਹਿਬ | 51-Chamkaur Sahib | ਮੋਰਿੰਡਾ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Morinda | Morinda | Water Supply, Sewerage, Tubewell | Ongoing Work | MDF |  | 1) | W/S Lines - Sewer Lines - Tubewell - | 5.43 Kms 33.80 Kms. 2 Nos. |  | 40.34 | 23.86 | 80% | 67% | 16.03 | 14.12.21 | 30.09.23 | PWSSB | W/s, Sew, STP | Pankaj Jain 8427663504 | Tarun Gupta 9888607639 | Pardeep Sharma 9465888557 | --- |  | 67.18%
[6 empty] | Ropar |  | 51 | [5 empty] | Surface Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | WTP Transmission Lines | 9: 1 No. 1 Job; 10: 25.85; 16: Tender Called; JE 23: DPR under preparation stage
77 | [5 empty] | Ropar |  | 51 |  |  | ਘੜੂੰਆਂ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Gharuan | Gharuan | Sewer MPS STP | Proposed work | SBM-2.0 |  | 1) | Sewer Lines MPS STP | 35 Kms. 1 No. 1 No. | 42 | --- | --- | --- | --- | --- | DPR yet to be received in Head Office | --- | ULB | - | Pankaj Jain 8427663504 | Tarun Gupta 9888607639 | Pardeep Sharma 9465888557 | DPR under preparation stage
78 | Smt. Anmol Gagan Maan | ਸ਼੍ਰੀ ਅਨਮੋਲ ਗਗਨ ਮਾਨ, 98554-55561 | Smt. Anmol Gagan Maan |  | AAP | Ropar | SAS Nagar | 52 | ਖਰੜ | 52- Kharar | ਖਰੜ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Kharar | Kharar | Sewer, STP, Tubewell | Ongoing Work | Deposit work |  | 1) | Sewer Lines - STP (10 MLD) - Tubewell - | 1.35 Kms. 1 No. 2 Nos. |  | 17.47 | 14.63 | 5% | 3% | 0.48 | 07.12.21 | 31.03.24 | PWSSB | MPS/STP (Deposit work) | Pankaj Jain 8427663504 | Tarun Gupta 9888607639 | Pardeep Sharma 9465888557 | Land for Sewer and STP under clearance. |  | 3.281%
[6 empty] | Ropar |  | 52 | [5 empty] | Surface Water Supply Sewer MPS STP | Proposed work | MC Deposit |  | 1) | Transmission Lines UGSRs Sewer Lines MPS STP | 9: 1 Job 4 Nos. 15 Kms. 1 No. 1 No.; 10: 77.8; JE 23: DPR under preparation stage
[6 empty] | Ropar |  | 52 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.pipeline House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 23.00 Km 3500Nos. 33.60 MLD 0.50 Km 12.00 KM; 10: 117.04; 16: Tender Called; JE 23: DPR under preparation stage
79 | Smt. Anmol Gagan Maan | ਸ਼੍ਰੀ ਅਨਮੋਲ ਗਗਨ ਮਾਨ, 98554-55561 | Smt. Anmol Gagan Maan |  |  | Ropar | SAS Nagar | 52 | ਖਰੜ | 52- Kharar | ਨਯਾ ਗਾਓਂ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Naya Gaon | Naya Gaon | Sewer, MPS, STP | Proposed work | SBM-2.0 |  | 1) | Main Sewer MPS STP | 5.91 kms. 03 Nos. 01 No. | 34.07 | --- | --- | --- | --- | --- | DPR yet to be received in Head Office | --- | ULB | - | Pankaj Jain 8427663504 | Tarun Gupta 9888607639 | Pardeep Sharma 9465888557 | DPR under preparation stage
[6 empty] | Ropar |  | 52 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 2) | T/welll New Dist. Network House Connection Pump house | 9: 4 no. 4.60 km 600 Nos. 4 NO.; 10: 2.83; JE 23: DPR under preparation stage
80 | [5 empty] | Ropar |  | 52 |  |  | ਕੁਰਾਲੀ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Kurali | Kurali | Surface Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | WTP Transmission Lines | 1 No. 1 Job | 34.11 | --- | --- | --- | --- | --- | --- | --- | ULB | - | Pankaj Jain 8427663504 | Tarun Gupta 9888607639 | Pardeep Sharma 9465888557 | DPR under preparation stage
81 | Shri. Kulwant Singh | ਸ਼੍ਰੀ ਕੁਲਵੰਤ ਸਿੰਘ, 98150-00538 | Shri. Kulwant Singh |  | AAP | Ropar | SAS Nagar | 53 | ਐਸ ਏ ਐਸ ਨਗਰ | 53- S.A.S Nagar | ਐਸ ਏ ਐਸ ਨਗਰ, (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | S.A.S Nagar | S.A.S Nagar | With MC / DWSS |  | --- |  |  | --- |  |  | --- | --- | --- | --- | --- | --- | --- |  |  | Presently no work ongoing by PWSSB |  |  | Presently no work ongoing by PWSSB
82 | Shri. Rupinder Singh | ਸ੍ਰੀ ਰੁਪਿੰਦਰ ਸਿੰਘ ਹੈਪੀ, 95921-00303 | Shri. Rupinder Singh |  | AAP | P2 | Fatehgarh Sahib | 54 | ਬੱਸੀ ਪਠਾਣਾ | 54- Bassi Pathana | ਬੱਸੀ ਪਠਾਣਾ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Bassi Pathana | Bassi Pathana | Sewerage and STP Works | Ongoing Work | HUDCO |  | 1) | Sewer line H.C. (nos) Interlocking (sqm) CC Roads (nos) Street Lights (nos) MPS(Zone-1) MPS (Zone-2) STP(ZONE-1) STP (Zone-2) | 31.90 Km 3564 nos 22682 sqm 29000 328 nos 1 No 1 No. 1 No. 1 No. |  | 23.93 | 22.12 | 91% | 84% | 18.68 | 17.06.2016 | 31.10.23 | PWSSB | W/S, Sew, STP | Er. Jugal Kishor (84276-63501) | Er. Sukhpal Singh (94172-10109) | Er. Satinder Singh (84373-99894) |  |  | 84.45%
83 | [5 empty] | P2 |  | 54 |  |  | ਖਮਾਣੋਂ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Khamano | Khamano | W/S, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S WTP | 3.35 Km 1 No. | 31.56 | [5 empty] | Tender Called |  | ULB | - | Er. Jugal Kishor (84276-63501) | Er. Sukhpal Singh (94172-10109) | Er. Satinder Singh (84373-99894) | DPR under preparation stage
[6 empty] | P2 |  | 54 | [5 empty] | Sewr, STP | Proposed work | SBM-2.0 |  | 2) | Main Sewer STP | 9: 1.6Km 1 No.(3 MLD); 10: 16.05; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
84 | Shri. Lakhbir Singh Rai | ਸ਼ੀ ਲਖਵੀਰ ਸਿੰਘ ਰਾਏ, 97809-00010 | Shri. Lakhbir Singh Rai |  | AAP | P2 | Fatehgarh Sahib | 55 | ਫਤਿਹਗੜ੍ਹ ਸਾਹਿਬ | 55- Fatehgarh Sahib | ਸਰਹਿੰਦ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Sirhind | Sirhind | Sewerage and STP Works | Ongoing Work | HUDCO |  | 1) | Sewer Interlocking Tiles CC Roads MR.Roads H.C Street Lights MPS Zone - 2 MPS Zone -3 STP(ZONE-1) 4 MLD STP (Zone-2) 5 MLD STP (Zone-3) 2 MLD | 99.855 km 116840sqm 47000 cum 63395 sqm 12500 nos 508 nos 1 No's 1 No's 1 No's 1 No's 1 No's |  | 74.9 | 70.76 | 85% | 85% | 61.25 | 17.06.2017 | 31.10.23 | PWSSB | W/S, Sew, STP | Er. Jugal Kishor (84276-63501) | Er. Rajnish Panoli (98727-88675) | Er. Manish kumar Yadav (99885-36527) |  |  | 86.56%
[6 empty] | P2 |  | 55 | [5 empty] | Water Supply & Sewerage Work | Ongoing Work | MDF |  | 2 | Sewer House connection Water Supply House Connection Road | 9: 10.77 km 1135 nos. 6.0 km 1400 km 52163 sqm; 11: 30.81; 12: 10.6; 13: 82%; 14: 77%; 15: 8.27; 16: 21.10.2021; 17: 31.08.23 |  | 78.02%
| Shri. Lakhbir Singh Rai | ਸ਼ੀ ਲਖਵੀਰ ਸਿੰਘ ਰਾਏ, 97809-00010 | Shri. Lakhbir Singh Rai |  |  | P2 | Fatehgarh Sahib | 55 | ਫਤਿਹਗੜ੍ਹ ਸਾਹਿਬ | 55- Fatehgarh Sahib | ਸਰਹਿੰਦ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Sirhind | Sirhind | Water Supply & Sewerage Work | Ongoing Work | MDF |  | 3 | Sewer House connection Water Supply House Connection Road | 4.21 km 610 Nos 1.30 km 300 Nos. 19150 sqm |  |  | 3.91 | 61% | 42% | 1.65 | 07.12.2021 | 31.07.23 | PWSSB | W/S, Sew, STP | Er. Jugal Kishor (84276-63501) | Er. Rajnish Panoli (98727-88675) | Er. Manish kumar Yadav (99885-36527) |  |  | 42.2%
[6 empty] | P2 |  | 55 | [5 empty] | W/S, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S WTP | 9: 13.80 Km 1 No. (14.86 MLd); 10: 53.66; JE 23: DPR under preparation stage
86 | Shri, Gurinder Singh Garry Birring | ਸ਼੍ਰੀ ਗੁਰਿੰਦਰ ਸਿੰਘ ਗੈਰੀ ਬੜਿੰਗ, 84270-05354 | Shri, Gurinder Singh Garry Birring |  | AAP | P2 | Fatehgarh Sahib | 56 | ਅਮਲੋਹ | 56- Amloh | ਅਮਲੋਹ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Amloh | Amloh | Construction of 3 MLD (STP) | Ongoing Work | HUDCO |  | 1) | STP 3MLD | 1 No |  | 16.72 | 5.45 | 64% | 17% | 0.94 | 17.09.2021 | 31.12.23 | ULB | - | Er. Jugal Kishor (84276-63501) | Er. Sukhpal Singh (94172-10109) | Er. Satinder Singh (84373-99894) |  |  | 17.25%
[6 empty] | P2 |  | 56 | [5 empty] | Sewerage Work (part-1) | Ongoing Work | Special Assistance |  | 2) | Lateral Sewer H/C | 9: 7.185 KM 590 Nos.; 11: 9.17; 12: 2.41; 13: 54%; 14: 52%; 15: 1.26; 16: 03.01.23; 17: 31.08.23 |  | 52.28%
[6 empty] | P2 |  | 56 | [5 empty] | Sewerage work (part-2) | Ongoing Work | Special Assistance |  | 3) | Lateral Sewer H/C | 9: 7.192 KM 610 Nos.; 12: 2.36; 13: 63%; 14: 53%; 15: 3.06; 16: 03.01.23; 17: 31.08.23 |  | 129.7%
[6 empty] | P2 |  | 56 | [5 empty] | W/S, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S WTP | 9: 5.00km 1 No. (4.50 MLD; 10: 21.71; 16: DNIT approved by Technical Sub Committee; JE 23: DPR under preparation stage
87 | Shri, Gurinder Singh Garry Birring | ਸ਼੍ਰੀ ਗੁਰਿੰਦਰ ਸਿੰਘ ਗੈਰੀ ਬੜਿੰਗ, 84270-05354 | Shri, Gurinder Singh Garry Birring |  | AAP | P2 | Fatehgarh Sahib | 56 |  |  | ਮੰਡੀ ਗੋਬਿੰਦਗੜ੍ਹ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Mandi Gobindgarh | Mandi Gobindgarh | Water Supply Work (Part-1) | Ongoing Work | Deposit work |  | 1) | Water Supply Tubewell Lateral Sewer | 7994 mtr 1 No. 8544 Mtr |  | 13.36 | 4.68 | 80% | 65% | 3.06 | 05.01.2022 | 31.08.23 | PWSSB | STP (Deposit work) | Er. Jugal Kishor (84276-63501) | Er. Sukhpal Singh (94172-10109) | Er.Ashok Kumar 97791-81082 |  |  | 65.38%
[6 empty] | P2 |  | 56 | [5 empty] | Lateral Sewer and Water supply | Ongoing Work | Special Assistance |  | 3) | Water Supply H/C W/S Sewerage H/C Sew | 9: 7.962 Km 400 Nos. 5.670 Km 400 Nos.; 11: 5.01; 12: 3.5; 13: 33%; 14: 18%; 15: 0.74; 16: 10.02.23; 17: 09.10.23 |  | 21.14%
[6 empty] | P2 |  | 56 | [5 empty] | W/S, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S WTP | 9: 23 Km 1 No. (19.72 MLD); 10: 104.87; JE 23: DPR under preparation stage
88 | Shri. Tarunpreet Singh Sond | ਸ਼੍ਰੀ ਤਰੁਨਪ੍ਰੀਤ ਸਿੰਘ ਸੌਂਦ, 78148-05555 | Shri. Tarunpreet Singh Sond |  | AAP | Ludh | Ludhiana | 57 | ਖੰਨਾ | 57- Khanna | ਖੰਨਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Khanna | Khanna | W/Supply & Sewerage Scheme | Proposed work | AMRUT 2.0 |  | 1) | W/S Line DIK7 Tubewells OHSR ( 2.0 Lakh GLs.) W/S Connection Road Work Lateral Sewer Main Sewer Sewer Connection IPS ( 2 MLD ) Deposit work | 9: 58.02 KM. 2Nos. 1 No. 14195 Nos. One Job 27.17 KM. 8.67 KM 5858 Nos. 1 No. One Job; 10: 85.01; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: STP (Deposit work); EE 12: Parul Goel : 8968549955; SDE 13: ___; JE 14: Paramjit J.E : 9592300982; JE 23: DPR under preparation stage
89 | Shri. Jagtar Singh Diyalpura | ਸ਼੍ਰੀ ਜਗਤਾਰ ਸਿੰਘ ਦਿਆਲਪੁਰਾ, 62832-56155 | Shri. Jagtar Singh Diyalpura |  | AAP | Ludh | Ludhiana | 58 | ਸਮਰਾਲਾ | 58- Samrala | ਸਮਰਾਲਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Samrala | Samrala | Const. of 14 MLD MPS at Samrala | Ongoing Work | HUDCO |  | 1) | Main Sewer (Km) R/main (Km.) MPS 14MLD (No) | 0.76 Km 0.92 Km. 1 No |  | 22.81 | 2.3569 | 70% | 82% | 1.9338 | 17.06.20 | 31.07.23 | ULB | - | - | - | - | Work is in progress |  | 82.05%
[6 empty] | Ludh |  | 58 | [5 empty] | Const. of 4 MLD STP at Samrala | Ongoing Work | HUDCO |  | 2) | STP 4 MLD | 1 No. |  | 22.81 | 6.3 | 82% | 79% | 3.7687 | 30.12.20 | 31.07.23 | [5 empty] | Work is in progress |  | 59.82%
[6 empty] | Ludh |  | 58 | [5 empty] | Water Supply Scheme | Proposed work | AMRUT 2.0- (T-1) |  | 2) | W/S Line Rising Main Tubewells OHSR ( 1.0 Lakh GLs.) W/S Connection Road Work Rehiblitation of Existing W/S Deposit work | 9: 18.69 KM. 195 Mtr. 2Nos. 1 No. 1200 Nos. One Job 5.75 KM One Job; 10: 9.82; JE 23: DPR under preparation stage
[6 empty] | Ludh |  | 58 |  |  | ਮਾਛੀਵਾੜਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Machhiwara | Machhiwara | Water Supply Scheme | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network OHSR 1.50 lac capacity House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 11.22 Km 1No. 632 Nos. 6.45 MLD 5.00 Km 4.00 KM; 10: 21.05; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: -; SDE 13: -; JE 14: -; JE 23: DPR under preparation stage
91 | Shri. Hardeep Singh Mundian | ਸ਼੍ਰੀ ਹਰਦੀਪ ਸਿੰਘ ਮੁੰਡੀਆਂ, 84375-70000 | Shri. Hardeep Singh Mundian |  | AAP | Ludh | Ludhiana | 59 | ਸਾਹਨੇਵਾਲ | 59- Sahnewal | ਸਾਹਨੇਵਾਲ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Sahnewal | Sahnewal | Water Supply Scheme | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S Line Pumping Machinery of Tubewell W/S Connection Road Work Replacement/Rehbilitation of Existing W/S | 9: 9.37 KM. 1 Job 882 Nos. One Job 1.1; 10: 4.75; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: STP (Deposit work); EE 12: Parul Goel : 8968549955; SDE 13: ___; JE 14: Paramjit J.E : 9592300982; JE 23: DPR under preparation stage
92 | Shri. Daljit Singh Garewal (Bhola) | ਸ਼੍ਰੀ ਦਲਜੀਤ ਸਿੰਘ ਗਰੇਵਾਲ, 99155-00500 | Shri. Daljit Singh Garewal (Bhola) |  | AAP | Ludh | Ludhiana | 60 | 60- ਲੁਧਿਆਣਾ (ਪੂਰਬ) | 60- Ludhiana East | ਲੁਧਿਆਣਾ (ਪੂਰਬ) (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Ludhiana East | Ludhiana East | Buddha Nallah Project | Ongoing Work | AMRUT |  | 1) | Construction of 2 nos New STP’s 225 MLD 60 MLD | 98% 34% |  | 650 | 519 | 70% | 59% | 420 | 02.12.2020 | 31.07.23 | PWSSB | STP (Deposit work) | Parul Goel : 8968549955 | ___ | Inderjit Singh Sahote J.E : 7889146359 Jatinder Singh Ste Engineer : 9815827139 | Work is in progress |  | 80.92%
93 | Smt. Rajinder Pal Kaur | ਸ੍ਰੀਮਤੀ ਰਜਿੰਦਰਪਾਲ ਕੌਰ ਛੀਨਾ, 98761-25970 | Smt. Rajinder Pal Kaur |  | AAP | Ludh | Ludhiana | 61 | 61- ਲੁਧਿਆਣਾ ਦੱਖਣ | 61- Ludhiana South | ਲੁਧਿਆਣਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Ludhiana | Ludhiana |  | Ongoing Work |  |  | 2) | Construction of 6 nos. Intermediate Pumping Station 1) 12 MLD Tibba IPS 2) 8 MLD Sundar Ngr 3) 5 MLD Kundanpuri 4) 13 MLD UpkarNgr- 5) LMH IPS- 6) 1 No. IPS near Gaughat Gurudwara | 9: 89%, 88% 59% 59% 59% yet to be started |  | #DIV/0!
94 | Shri. Kulwant Singh Sidhu | ਸ਼੍ਰੀ ਕੁਲਵੰਤ ਸਿੰਘ ਸਿੱਧੂ, 97818-00002 | Shri. Kulwant Singh Sidhu |  | AAP | Ludh | Ludhiana | 62 | 62- ਆਤਮ ਨਗਰ | 62- Atam Nagar | ਲੁਧਿਆਣਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Ludhiana | Ludhiana |  | Ongoing Work |  |  | 3) | Rising main pipe line from Sundar Nagar IPS to Jamalpur STP | 9: Completed |  | #DIV/0!
95 | Shri. Ashok Parashar (Pappi) | ਸ਼੍ਰੀ ਅਸ਼ੋਕ ਪਰਾਸ਼ਰ, 98157-45554 | Shri. Ashok Parashar (Pappi) |  | AAP | Ludh | Ludhiana | 63 | 63- ਲੁਧਿਆਣਾ -ਸੈਂਟਰਲ | 63- Ludhiana central | ਲੁਧਿਆਣਾ- ਸੈਂਟਰਲ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Ludhiana central | Ludhiana central |  | Ongoing Work |  |  | 4) | Rising main pipe line from Upkar Nagar IPS to Balloke STP | 9: Completed |  | #DIV/0!
96 | Shri. Gurpreet Bassi Gogi | ਸ਼੍ਰੀ ਗੁਰਪ੍ਰੀਤ ਬੱਸੀ ਗੋਗੀ, 98147-06061 | Shri. Gurpreet Bassi Gogi |  | AAP | Ludh | Ludhiana | 64 | 64- ਲੁਧਿਆਣਾ ਪੱਛਮ | 64- Ludhiana West | ਲੁਧਿਆਣਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Ludhiana | Ludhiana |  | Ongoing Work |  |  | 5) | Rising main pipe line from Kundanpuri IPS to UPKAR nagar IPS | 9: Completed |  | #DIV/0!
97 | Shri Madan Lal Bagga | ਸ਼੍ਰੀ ਮਦਨ ਲਾਲ ਬੱਗਾ, 95921-1155 | Shri Madan Lal Bagga |  | AAP | Ludh | Ludhiana | 65 | 65- ਲੁਧਿਆਣਾ ਉੱਤਰ | 65- Ludhiana North | ਲੁਧਿਆਣਾ ਉੱਤਰ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Ludhiana North | Ludhiana North |  | Ongoing Work |  |  | 6) | Construction of 2 nos. Effluent Treatment Plant (ETP) of 2.25 & 3.75MLD capacity Tajpur road &Haibowal respectively. 2.25MLD 3.75MLD | 9: 8.0% 8.0%. |  | #DIV/0!
98 | Shri. Jiwan Singh Sangowal | ਸ਼੍ਰੀ ਜੀਵਨ ਸਿੰਘ ਸੰਗੋਵਾਲ, 98728-15397 | Shri. Jiwan Singh Sangowal |  | AAP | Ludh | Ludhiana | 66 | 66- ਗਿੱਲ | 66- Gill | ਗਿੱਲ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) |  |  |  | Ongoing Work |  |  | 7) | Rehabilitation of existing 2 nos STP 111MLD & 152 MLD at Bhattian & Balloke respectively 111 MLD 152 MLD | 9: 82% 24% |  | #DIV/0!
98 | [5 empty] | Ludh |  | 66 | [6 empty] | Ongoing Work |  |  | 8) | 2nos STP’s of 50MLD & 105MLD based on SBR technology at Bhattian & Balloke 50 MLD 105 MLD | 9: 100% 100% |  | #DIV/0!
98 | [5 empty] | Ludh |  | 66 | [6 empty] | Ongoing Work |  |  | 9) | Operation & Maintenance of the above components for 10 years after construction & 21 month during construction period. | 9: Going on since 01.03.2021 |  | #DIV/0!
99 | Shri. Manwinder Singh Giaspura | ਸ਼੍ਰੀ ਮਨਵਿੰਦਰ ਸਿੰਘ ਗਿਆਸਪੁਰਾ, 98720-99100 | Shri. Manwinder Singh Giaspura |  | AAP | Ludh | Ludhiana | 67 | 67- ਪਾਇਲ Payal | 67- Payal | ਮਲੌਦ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Malod | Malod | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 1.95 Km 200 Nos. 1.95 MLD 10.00 Km 5.00 KM; 10: 12.35; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S, Sew; EE 12: Parul Goel : 8968549955; SDE 13: ___; JE 14: Sukhdev Singh J.E : 9872577402; JE 23: DPR under preparation stage
100 | [5 empty] | Ludh |  | 67 |  |  | ਪਾਇਲ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Payal | Payal | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 2.40 Km 200 Nos. 2.22 MLD 10.00 Km 5.00 KM; 10: 13.67; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S; EE 12: Parul Goel : 8968549955; SDE 13: ___; JE 14: Sh. Kapil J.E : 8146463402; JE 23: DPR under preparation stage
101 | [5 empty] | Ludh |  | 67 |  |  | ਦੋਰਾਹਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Doraha | Doraha | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 5.0 Km 4123 Nos. 6.40 MLD 2.00 Km 7.00 KM; 10: 20.4; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: -; SDE 13: -; JE 14: -; JE 23: DPR under preparation stage
102 | Shri. Manpreet Singh Ayali | ਸ਼੍ਰੀ ਮਨਪ੍ਰੀਤ ਸਿੰਘ ਇਯਾਲੀ , 98140-46245 | Shri. Manpreet Singh Ayali |  | SAD | Ludh | Ludhiana | 68 | 68- ਦਾਖਾ | 68- Dakha | ਮੁੱਲਾਪੁਰ ਦਾਖਾ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Mullanpur Dakha | Mullanpur Dakha | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Disribution Lines Rising Main Tubewells OHRS(1.00 Lac Gls ) House Connections . | 9: 13.29 2.10 KM 2 Nos. 1 Nos. 764 Nos.; 10: 6.93; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S, Sew; EE 12: Parul Goel : 8968549955; SDE 13: ___; JE 14: Manjit Singh J.E : 9779349509; JE 23: DPR under preparation stage
103 | Shri. Hakam Singh Thekedar | ਸ਼੍ਰੀ ਹਾਕਮ ਸਿੰਘ ਠੇਕੇਦਾਰ , 98142-18091 | Shri. Hakam Singh Thekedar |  | AAP | Ludh | Ludhiana | 69 | 69- ਰਾਏਕੋਟ | 69- Raikot | ਰਾਏਕੋਟ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Raikot | Raikot | Water Supply & Sewerage Work | Ongoing Work | MDF |  | 1) | W/S= Lateral Sewer= RCC NP3 = | 5.74km 48.05km 1.43km |  | 17.07 | 14.9891 | 66% | 73% | 10.9488 | 05.03.21 | 30.09.23 | ULB | - | - | - | - | Work is in progress |  | 73.05%
103 | [5 empty] | Ludh |  | 69 | [5 empty] | Const. of 23MLD MPS at Raikot | Ongoing Work | HUDCO |  | 2) | Main Sewer (km) R/main (Km.) MPS 23 MLD (No) | 0.75 Km 1.79 Km. 1 No |  | 13.76 | 2.9285 | 72% | 71% | 2.07 | 8.11.19 | 30.09.23 | [5 empty] | Work is in progress |  | 70.68%
103 | [5 empty] | Ludh |  | 69 | [5 empty] | Const. of 7 MLD STP at Raikot | Ongoing Work | HUDCO |  | 3) | STP 7 MLD | 1 No. |  | 13.76 | 9 | 40% | 55% | 4.24 | 30.12.20 | 30.09.23 | [5 empty] | Work is in progress |  | 47.11%
[6 empty] | Ludh |  | 69 | [5 empty] | Balance Work (Part-2) Water Supply Scheme | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Distribution Lines W/S House Connt Road Work | 9: 13.03 Km 819 Nos. Road Work; 10: 2.17; JE 23: DPR under preparation stage
[6 empty] | Ludh |  | 69 | [5 empty] | Balance Work (PWD B&R and other Department ) for Balance Work of (Part-2) Water Supply Scheme | Proposed work | AMRUT 2.0- (T-1) |  | 3) | Road Cut of B&R , Forest Dept. and Mandi Board as per BT Bill | 10: 2.46; JE 23: DPR under preparation stage
104 | Smt. Saravjit Kaur Manuke | ਸ਼੍ਰੀਮਤੀ ਸਰਵਜੀਤ ਕੌਰ ਮਾਣੂੰਕੇ, 99887-77168 | Smt. Saravjit Kaur Manuke |  | AAP | Ludhiana | Ludhiana | 70 | 70- ਜਗਰਾਓਂ | 70- Jagraon | ਜਗਰਾਓਂ (ਸ਼੍ਰੀ ਪਾਰੂਲ ਗੋਇਲ, 89685-49955) | Jagraon | Jagraon | Water Supply Scheme | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Distribution Lines Tubewells (Against Failed Tubewell) House Connection . | 9: 21.93 Km 2 Nos. 420 Nos.; 10: 11.29; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: STP (Deposit work); EE 12: Parul Goel : 8968549955; SDE 13: ___; JE 14: Manjit Singh J.E : 9779349509; JE 23: DPR under preparation stage
105 | Shri. Manjit Singh Bilaspur | ਸ਼੍ਰੀ ਮਨਜੀਤ ਸਿੰਘ ਬਿਲਾਸਪੁਰ, 84278-33289 | Shri. Manjit Singh Bilaspur |  | AAP | Moga | Moga | 71 | 71- ਨਿਹਾਲ ਸਿੰਘ ਵਾਲਾ | 71- Nihal Singh Wala | ਨਿਹਾਲ ਸਿੰਘ ਵਾਲਾ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Nihal Singh Wala | Nihal Singh Wala | 1. Prov.S/s at Nihl Singh Wala (Part-A) | Proposed work | SBM-2.0 |  | 1) | Sewer MPS STP | 5.09Km 1 Job 1Job (3 MLD) | 23.87 | - | - | - | - | - | DPR checked at HO & sent to SLTC | - | ULB | W/s | Sh. Supuinder Singh 94171-59123 | Sh. Gurwinder Singh 98551-06239 | Sh. Gurpreet Singh | DPR under preparation stage
[6 empty] | Moga |  | 71 | [5 empty] | 2. Prov.S/s at Nihl Singh Wala (Part-B) | Proposed work | SBM-2.0 |  | 2) | Sewer H/C Road | 9: 30.153 Km 4036 Nos. 1 Job; 10: 33.63; JE 23: DPR under preparation stage
[6 empty] | Moga |  | 71 | [5 empty] | 3.Prov. W/s at Nihal Singh Wala | Proposed work | AMRUT 2.0- (T-1) |  | 3) | Distr. Line H/C Road | 9: 2.391 Km 320 Nos 1 Job; 10: 0.99; JE 23: DPR under preparation stage
106 | Shri. Manjit Singh Bilaspur | ਸ਼੍ਰੀ ਮਨਜੀਤ ਸਿੰਘ ਬਿਲਾਸਪੁਰ, 84278-33289 | Shri. Manjit Singh Bilaspur |  |  | Moga | Moga | 71 | 71- ਨਿਹਾਲ ਸਿੰਘ ਵਾਲਾ | 71- Nihal Singh Wala | ਬੱਧਨੀ ਕਲਾਂ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Badni kalan | Badni kalan | 1. Prov.S/s at Badhni Kalan (Part-A) | Proposed work | SBM-2.0 |  | 1) | Sewer MPS STP 3 MLD | 4.401 Km 1 Job 1 Job (3MLD) | 18.51 | [5 empty] | DPR checked at HO & sent to SLTC |  | PWSSB | W/s | Sh. Supuinder Singh 94171-59123 | Sh. Gurwinder Singh 98551-06239 | Sh. Gurpreet Singh 84274-66112 | DPR under preparation stage
[6 empty] | Moga |  | 71 | [5 empty] | 1. Prov.S/s at Badhni Kalan (Part-B) | Proposed work | SBM-2.0 |  | 2) | Sewer H/C Road | 9: 25.102 Km 3347 No. 1 Job; 10: 21.22; JE 23: DPR under preparation stage
[6 empty] | Moga |  | 71 | [5 empty] | 3 Prov. W/s Badhni Kalan | Proposed work | AMRUT 2.0- (T-1) |  | 3) | Distr. Line H/C Road | 9: 4.48 Km 59 Nos 1 Job; 10: 1.12; JE 23: DPR under preparation stage
107 | Shri. Amritpal Singh Sukhanand | ਸ਼੍ਰੀ ਅੰਮ੍ਰਿਤਪਾਲ ਸਿੰਘ ਸੁਖਾਨੰਦ, 97819-61432 | Shri. Amritpal Singh Sukhanand |  | AAP | Moga | Moga | 72 | 72- ਬਾਘਾ ਪੁਰਾਣਾ | 72- Bhagha Purana | ਬਾਘਾ ਪੁਰਾਣਾ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Bhagha Purana | Bhagha Purana | Specail Repair of STP | Proposed work | SBM-2.0 |  | 1) | Specail Repair of STP | 1 Job | 1.88 | - | - | - | - | - | DWSS Town | - | ULB | W/s | Sh. Supuinder Singh 94171-59123 | Sh. Gurwinder Singh 98551-06239 | Sh.Bhola Singh 83603-84595 | DPR under preparation stage
108 | Dr. Amandeep Kaur Arora | ਡਾ. ਅਮਨਦੀਪ ਕੌਰ ਅਰੋੜਾ, 98885-60650 | Dr. Amandeep Kaur Arora |  | AAP | Moga | Moga | 73 | 73- ਮੋਗਾ | 73- Moga | ਮੋਗਾ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Moga | Moga | W/s & Sew | Proposed work | AMRUT 2.0 |  | 1) | W/s Line Water Supply H/C T/well Sewer Road STP 30 MLD Rising Main Sewer H/C | 30.85 km 4110 No. 1 No 15.10 Km 1 Job 1 Job 2.60 Km 2012 Nos | 58.67 | - | - | - | - | - | - | - | PWSSB | STP (Deposit Work) | Sh. Supuinder Singh 94171-59123 | Sh. Gurwinder Singh 98551-06239 | Sh. Neeraj Goyal 98551-10788 | DPR under preparation stage
109 | Shri. Devinderjit Singh Laddi Dhose | ਸ਼੍ਰੀ ਦਵਿੰਦਰਜੀਤ ਸਿੰਘ, 91156-21009 | Shri. Devinderjit Singh Laddi Dhose |  | AAP | Moga | Moga | 74 | 74- ਧਰਮਕੋਟ | 74- Dharamkot | ਧਰਮਕੋਟ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Dharamkot | Dharamkot | Prov. W/s at Dharamkot | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Distr. Line H/C T/well | 9: 2.77 Km 370 Nos 1 No; 10: 1.07; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: STP,MPS (Deposit work); EE 12: Sh. Supuinder Singh 94171-59123; SDE 13: Sh. Gurwinder Singh 98551-06239; JE 14: Sh. Neeraj Goyal 98551-10788; JE 23: DPR under preparation stage
110 | [5 empty] | Moga |  | 74 |  |  | ਫਤਹਿਗੜ੍ਹ ਪੱਜਤੂਰ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Fathegarh Panjtoor | Fathegarh Panjtoor | Prov.S/s at Fatehgarh Panjtoor (Part-A) | Proposed work | SBM-2.0 |  | 1) | Sewer MPS STP 3 MLD | 4.421 Km 1 Job 1Job | 13.22 | [5 empty] | DPR checked at HO & sent to SLTC |  | ULB | W/s | Sh. Supuinder Singh 94171-59123 | Sh. Gurwinder Singh 98551-06239 | Sh. Neeraj Goyal 98551-10788 | DPR under preparation stage
[6 empty] | Moga |  | 74 | [5 empty] | Prov.S/s at Fatehgarh Panjtoor (Part-B) | Proposed work | SBM-2.0 |  | 2) | Sewer H/C Road | 9: 8.578 Km 1201 Nos. 1 Job; 10: 9.59; JE 23: DPR under preparation stage
[6 empty] | Moga |  | 74 | [5 empty] | Prov. W/s Fatehgarh Panjtoor | Proposed work | AMRUT 2.0- (T-1) |  | 3) | Distr. Line H/C Road | 9: 6.05 Km 354 Nos 1 Job; 10: 1.63; JE 23: DPR under preparation stage
111 | Shri. Devinderjit Singh Laddi Dhose | ਸ਼੍ਰੀ ਦਵਿੰਦਰਜੀਤ ਸਿੰਘ , 91156-21009 | Shri. Devinderjit Singh Laddi Dhose |  |  | Moga | Moga | 74 | 74- ਧਰਮਕੋਟ | 74- Dharamkot | ਕੋਟ ਈਸੇ ਖਾਂ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Kotisekhan | Kotisekhan | Prov.S/s at Kotisekhan (Part-A) | Proposed work | SBM-2.0 |  | 1) | Sewer MPS STP 3 MLD | 10.00 Km 1 Job 1Job | 29.93 | [5 empty] | DPR Under check at Head Office |  | ULB | W/s | Sh. Supuinder Singh 94171-59123 | Sh. Gurwinder Singh 98551-06239 | Sh.Bhola Singh 83603-84595 | DPR under preparation stage
[6 empty] | Moga |  | 74 | [5 empty] | Prov.S/s at Kotisekhan (Part-B) | Proposed work | SBM-2.0 |  | 2) | Sewer H/C Road | 9: 22.94 Km 2877 Nos 1 Job; 10: 21.82; JE 23: DPR under preparation stage
[6 empty] | Moga |  | 74 | [5 empty] | Prov. W/s Kotisekhan | Proposed work | AMRUT 2.0- (T-2) |  | 3) | Distr. Line H/C Road T/well OHSR 1.00 Lakh Gallon | 9: 4.72 Km 479 Nos 1 Job 2 Nos 1 No.; 10: 4.67; JE 23: DPR under preparation stage
112 | Shri. Naresh Kataria | ਸ਼੍ਰੀ ਨਰੇਸ਼ ਕਟਾਰੀਆ, 98780-92005 | Shri. Naresh Kataria |  |  | Fe | Firozepur | 74 | 75- ਜ਼ੀਰਾ | 75- Zira | ਜ਼ੀਰਾ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Zira | Zira | Water Supply | Ongoing Work | HUDCO |  | 1) | Tubewell Pump Chamber DiK9 Pipe Rising main | 3No. 3 No. 0.554 km |  |  | 0.67 | 60% | 50% | 0.39 | 30.09.21 | 30.09.23 | PWSSB | MPS & STP | Harsharanjeet Sinigh 96536-00048 | Ashok Maini 98159-91666 | Maninder Kumar 94646-03010 |  |  | 58.21%
[6 empty] | Fe |  | 74 | [5 empty] | DPR for Extension & Augmentation of W/S at Zira | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Distribution lines H/C Road Cutting & Restoration. | 9: 9.95 km 1200 Nos 1 Job; 10: 6.97; 16: DPR's Prepared; JE 23: DPR under preparation stage
113 | [5 empty] | Fe |  | 75 |  |  | ਮੱਖੂ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Makhu | Makhu | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Rehabilit. Of Dist. network Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 9.25 KM 1.10 Km 2125 Nos. 4.18 MLD 4.00 Km 2.00 KM; 10: 16.06; 16: DPR approved by Technical Sub Committee/SLTC; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: MPS & STP; JE 23: DPR under preparation stage
114 | Shri. Naresh Kataria | ਸ਼੍ਰੀ ਨਰੇਸ਼ ਕਟਾਰੀਆ, 98780-92005 | Shri. Naresh Kataria |  |  | Fe |  | 75 | 75- ਜ਼ੀਰਾ | 75- Zira | ਮੱਲਾਂਵਾਲਾ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Mallanwala | Mallanwala | DPR for Providing Sewerage, MPS & STP at Mallanwala | Proposed work | SBM-2.0 |  | 1) | Dismantling Roads Sewer Const of Main Hole House Connection STP 4 MLD, MPS . Rising Main 400 mm id | 57494 sq mtr 38.29 km 1400 Nos 6855 Nos 1 No 1 No. 0.30 km | 44.35 | [5 empty] | DPR checked at HO & sent to SLTC |  | PWSSB | Water Supply | Harsharanjeet Sinigh 96536-00048 | Gulshan Kumar 98148-01712 | Tarlochan Singh 96462-60020 | DPR under preparation stage
[6 empty] | Fe |  | 75 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 12.80 Km 2565 Nos. 4.27 MLD 10.00 Km 5.50 KM; 10: 24.38; JE 23: DPR under preparation stage
115 | Shri. Ranbir Singh | ਸ਼੍ਰੀ ਰਨਬੀਰ ਸਿੰਘ ਭੂੱਲਰ, 94177-00029 | Smt. Ranbir Singh |  | AAP | Fe | Firozepur | 76 | 76-ਫਿਰੋਜ਼ਪੁਰ ਸ਼ਹਿਰ City | 76- Firozepur City | ਫਿਰੋਜ਼ਪੁਰ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Firozepur | Firozepur | Providing Water Supply atFerozepur | Proposed work | AMRUT 2.0- (T-2) |  | 2) | T/W (Hand bore) Boundry wall Distribution Road Cutting & Restoration | 9: 3 No 0.639 Km 22.34 Km 1 Job; 10: 8.6; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S & Sew; EE 12: Harsharanjeet Sinigh 96536-00048; SDE 13: Gulshan Kumar 98148-01712; JE 14: Tarlochan Singh 96462-60020; JE 23: DPR under preparation stage
116 | Shri. Rajneesh Kumar Dahiya | ਸ਼੍ਰੀ ਰਜਨੀਸ਼ ਕੁਮਾਰ ਦਹੀਆ, 97100-00164 | Shri. Rajneesh Kumar Dahiya |  | AAP | Fe | Firozepur | 77 | 77- ਫਿਰੋਜ਼ਪੁਰ ਪੇਂਡੂ | 77- Firozpur Rural | ਤਲਵੰਡੀ ਭਾਈ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Talwandi Bhai | Talwandi Bhai | DPR for Providing Sewerage at Talwandi Bhai. | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Dismantling Roads Sewer House Connection | 9: 1 job 3.47 km 463 Nos; 10: 3.28; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: MPS & STP; EE 12: Harsharanjeet Sinigh 96536-00048; SDE 13: Gulshan Kumar 98148-01712; JE 14: Tarlochan Singh 96462-60020; JE 23: DPR under preparation stage
[6 empty] | Fe |  | 77 | [5 empty] | Providing Water Supply at Talwandi Bhai | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Distribution lines OHSR( 1.00 &,0.50 lac gln cap) T/W | 9: 1.82 km 2 No 2 Nos; 10: 2.58; SDE 13: Gulshan Kumar 98148-01712; JE 14: Tarlochan Singh 96462-60020; JE 23: DPR under preparation stage
117 | Shri. Rajneesh Kumar Dahiya | ਸ਼੍ਰੀ ਰਜਨੀਸ਼ ਕੁਮਾਰ ਦਹੀਆ, 97100-00164 | Shri. Rajneesh Kumar Dahiya |  |  | Fe |  | 77 | 77- ਫਿਰੋਜ਼ਪੁਰ ਪੇਂਡੂ | 77- Firozpur Rural | ਮੁਦਕੀ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Mudki | Mudki | Sewerage, MPS & STP | Proposed work | SBM-2.0 |  | 1) | Dismantling Roads Sewer Const of Main Hole House Connection STP = 2 MLD MPS Rising Main 400 mm id | 34896 sq mtr 28.64 km 941 Nos 3789 Nos 1 No. 1 No. 1.15 km | 24.98 | [5 empty] | DPR checked at HO & sent to SLTC |  | ULB | - | - | - | - | DPR under preparation stage
[6 empty] | Fe |  | 77 | [5 empty] | Water Supply line OHSR , water works and WTP of 0.50 MGD Capacity at Mudki | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Distribution lines OHSR WTP = 0.50 MGD H/C Road Cutting & Restoration. | 9: 27.60 km 1 No 1 No 3678 Nos 1 Job; 10: 14.38; JE 23: DPR under preparation stage
118 | Shri. Rajneesh Kumar Dahiya | ਸ਼੍ਰੀ ਰਜਨੀਸ਼ ਕੁਮਾਰ ਦਹੀਆ, 97100-00164 | Shri. Rajneesh Kumar Dahiya |  |  | Fe |  | 77 | 77- ਫਿਰੋਜ਼ਪੁਰ ਪੇਂਡੂ | 77- Firozpur Rural | ਮਮਦੋਟ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Mamdot | Mamdot | DPR for Providing Sewerage, MPS & STP at Mamdot | Proposed work | SBM-2.0 |  | 1) | Sewer H/c Rising Main STP 2 MLD | 29.34 km 342 Nos 2.80 km 1 No. | 29.3 | [5 empty] | DPR checked at HO & sent to SLTC |  | ULB | - | - | - | - | DPR under preparation stage
[6 empty] | Fe |  | 77 | [5 empty] | Providing Water Supply line Consturciton of OHSR at Mmdot | Proposed work | AMRUT 2.0- (T-2) |  | 2) | Distribution lines OHSR T/w H/C Road Cutting & Restoration. | 9: 22 km 1 No 2 No 2929 Nos 1 Job; 10: 8.88; JE 23: DPR under preparation stage
119 | Shri Fauja Singh Sarari | ਸ਼੍ਰੀ ਫੌਜਾ ਸਿੰਘ ਸਰਾਰੀ, 90561-22151 | Shri Fauja Singh |  | AAP | Abohar | Firozepur | 78 | 78- Guru Harsahai | 78- Guru Harsahai | ਗੁਰੂ ਹਰਸਹਾਏ (ਸ਼੍ਰੀ ਰਾਹੁਲ ਕੋਸ਼ਲ, 97800-16670) | Guru Harsahai | Guru Harsahai | Providing W/S & Sew. Scheme at Guruharsahai Town | Ongoing Work | HUDCO |  | 1) | Water Supply(mtr) OHSR (1 Lakh Gln) Sewerage (Mtr) House Connt Roads(Sqm) STP 1 MLD STP 4 MLD | 18532 1 36050 5000 114096 1 1 |  | 37.53 | 20.68 | 66% | 58% | 12.57 | 15.11.2016 | 31.07.23 | ULB | --- | Er. Rahul Kaushal 9780016670 | Er. Lakhpat Sachdeva 9878900252 | Er. Ranjodh Singh 9463604740 | Due to poor performance of agency, partial scope of withdrawn from agency in accordance with contract agreement which are allotted to other contractors / agencies |  | 60.78%
[5 empty] | AAP | Abohar |  | 78 | [5 empty] | Providing Sew. Scheme at Guruharsahai Town (Left out SPCPL) | Work Completed | HUDCO |  | 2) | Sewerage (Mtr) I.L. Paver Block (Sqm) | 500 7585 |  | 37.53 | 0.87 | 100% | 32% | 0 | 21.11.2022 | 30.04.23 | [5 empty] | Work Completed
[6 empty] | Abohar |  | 78 | [5 empty] | Water Supply Lines, Construction of WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Water Supply pipe line WTP ,Rising Main S&S Tank CWT Pump Chamber | 9: 8.53 Km, 1 No. 1 Job, 1 No., 2 Nos., 1 No.,; 10: 34.7; 16: Tender Called; JE 23: DPR under preparation stage
120 | Shri Jagdeep Kamboj | ਸ਼੍ਰੀ ਜਗਦੀਪ ਕੰਬੋਜ ਗੋਲਡੀ, 92163-00199 | Shri Jagdeep Kamboj |  | AAP | Abohar | Fazilka | 79 | 79- ਜਲਾਲਾਬਾਦ | 79- Jalalabad | ਜਲਾਲਾਬਾਦ (ਸ਼੍ਰੀ ਰਾਹੁਲ ਕੋਸ਼ਲ, 97800-16670) | Jalalabad | Jalalabad | Water Supply Lines, Construction of WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Water Supply pipe line WTP Rising Main S&S Tank CWT Pump Chamber | 9: 1.00 Km, 1 No., 1 Job, 1 No., 2 Nos., 1 No.; 10: 43.85; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: ---; EE 12: Er. Rahul Kaushal 9780016670; SDE 13: Er. Lakhpat Sachdeva 9878900252; JE 14: Er. Ranjodh Singh 9463604740; JE 23: DPR under preparation stage
121 | Shri Jagdeep Kamboj | ਸ਼੍ਰੀ ਜਗਦੀਪ ਕੰਬੋਜ ਗੋਲਡੀ, 92163-00199 | Shri Jagdeep Kamboj |  |  | Abohar |  | 79 | 79- ਜਲਾਲਾਬਾਦ | 79- Jalalabad | ਅਰਨੀਵਾਲਾ (ਸ਼੍ਰੀ ਰਾਹੁਲ ਕੋਸ਼ਲ, 97800-16670) | Arniwala | Arniwala | Water Supply works | Ongoing Work | HUDCO |  | 1) | Water Supply (in mtr) WTP Gravity Main RCC P-1 300 mm Connecting pipes DI Pipe K-9 (200- 500)mm | 8495 mtr 1 No 4283 mtr 513 mtr |  | 7.55 | 6.94 | 95% | 70% | 4.85 | 8.6.2021 | 31.07.23 | ULB | --- | Er. Rahul Kaushal 9780016670 | Er. Lakhpat Sachdeva 9878900252 | Er. Ranjodh Singh 9463604740 |  |  | 69.88%
[6 empty] | Abohar |  | 79 | [5 empty] | Water Supply Lines, Construction of OHSR | Proposed work | AMRUT 2.0- (T-2) |  | 1) | DI K-7 Water Supply pipe line, Rehabitation of Existing W/S, OHSR 1.50 Lac Gln , H/C., | 9: 14.35 Km, 10.53 Km 1 No.., 2550 Nos.,; 10: 9; JE 23: DPR under preparation stage
[6 empty] | Abohar |  | 79 | [5 empty] | Main Sewer, IPS, MPS and Sewage Treatment Plant at Arniwla Sheikh Subhan Distt. Fazilka. | Proposed work | SBM-2.0 |  | 2) | Main Sewer , IPS MPS STP Dismantlings of Road, Road Restoration, | 9: 5.23 Km, 1 No.. 1 No., 1 No. 1 Job; 10: 22.8; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
[6 empty] | Abohar |  | 79 | [5 empty] | Lateral Sewer, Sewer House Connections and Restoration of Roads at Arniwla Sheikh Subhan Distt. Fazilka | Proposed work | SBM-2.0 |  | 3) | Pipe Sewer IPS Dismantlings of Road, Road Restoration, Deposit Work ( PSPCL,PWD) | 9: 22.55 Km, 2No., 1 Job; 10: 22.69; JE 23: DPR under preparation stage
122 | Shri Narinder Pal Singh Sawna | ਸ਼੍ਰੀ ਨਰਿੰਦਰ ਪਾਲ ਸਿੰਘ ਸਵਨਾ, 97813-77710 | Shri Narinder Pal Singh Sawna |  | AAP | Abohar | Fazilka | 80 | 80- ਫਾਜ਼ਿਲਕਾ | 80- Fazilka | ਫਾਜ਼ਿਲਕਾ (ਸ਼੍ਰੀ ਰਾਹੁਲ ਕੋਸ਼ਲ, 97800-16670) | Fazilka | Fazilka | Construction of 13 MLD (STP) | Work Completed | MDF |  | 1) | 13 MLD STP (No) | 1 |  | 15.43 | 15.05 | 100% | 73% | 13.68 | 7.5.2021 | 31.01.23 | ULB | --- | Er. Rahul Kaushal 9780016670 | Er. Lakhpat Sachdeva 9878900252 | Er. Ranjodh Singh 9463604740 | Work Completed |  | 90.9%
[6 empty] | Abohar |  | 80 | [5 empty] | Water Supply Lines, Construction of WTP, at Fazilka Town Distt. Fazilka | Proposed work | AMRUT 2.0- (T-2) |  | 1) | DI K-7 Water Supply pipe line , WTP (1.50 MGD), Clear Water Tank Pump Chamber S&S Tank Boundary Wall , HSC , Rehablitation of Existing 2.50 MGD WTP, Internal Roads & Pathway of Water Works, Dismantlings of Road, | 9: 9.93 Km, 1 No., 1 No., 1 No., 1 No., 700 mtr., 1324 Nos., 1 Job 1 Job 1 Job; 10: 14.15; JE 23: DPR under preparation stage
123 | Sh. Sandeep Kumar Jakhar | ਸ਼੍ਰੀ ਸੰਦੀਪ ਜਾਖੜ, 97798-32712 | Sh. Sandeep Kumar Jakhar | ਸ੍ਰੀ ਕੁਲਦੀਪ ਕੁਮਾਰ ਕੰਬੋਜ, 91151-15505 | INC | Abohar | 81-Abohar | 81 | 81-ਅਬੋਹਰ | 81-Abohar | ਅਬੋਹਰ (ਸ਼੍ਰੀ ਰਾਹੁਲ ਕੋਸ਼ਲ, 97800-16670) | Abohar | Abohar | Providing W/S and Sewerage Scheme Phase-I | Ongoing Work | AMRUT |  | 1) | Water Supply (in mtr) Water Treatment Plant Sewerage (Mtr) Interlocking Roads | 8389 1 No. 76469 mtr 135627 sqm |  | 105.74 | 86.54 | 95% | 84% | 72.51 | 15.11.2016 | 31.07.23 | ULB | --- | Er. Rahul Kaushal 9780016670 | Er. Lovekesh Kumar 9876515693 | Er. Sahil Kumar 7009106140 | 5% L.D. has already been levied upon agency amounting to Rs. 595.80 Lakh out of which Rs. 365.10 Lakh has been recovered |  | 83.79%
[6 empty] | Abohar |  | 81 | [5 empty] | Providing Sewerage Scheme Left Out work of SPCPL | Ongoing Work | AMRUT |  | 2) | IL roads (Sqm) House Connt. (nos) | 9: 31122 987 Nos; 11: 82.69; 12: 3.3; 13: 95%; 14: 82%; 15: 2.71; 16: 10.6.2021; 17: 31.07.23 |  | 82.12%
[6 empty] | Abohar |  | 81 | [5 empty] | Providing Water Supply Scheme Phase-III and Sewerage Scheme Phase-II (Zone-1) | Work Completed | AMRUT |  | 3) | W/S Line (mtr) Sewerage (Mtr) IL Paver Block (Sqm) | 7127 / 7482 20214 / 23540 28593 |  | W/S 3.50 Cr S/S 33.05 Cr | 16.22 | 100% | 100% | 14.98 | 20.4.2021 | 28.02.23 | [5 empty] | Work Completed |  | 92.36%
[6 empty] | Abohar |  | 81 | [5 empty] | Providing Water Supply Scheme Phase-III and Sewerage Scheme Phase-II (Zone-2) | Work Completed | AMRUT |  | 4) | W/S Line (mtr) Sewerage (Mtr) CC Roads IL Paver Block (Sqm) | 9: 7272 15008 2909 15469; 12: 12.88; 13: 100%; 14: 100%; 15: 11.59; 16: 20.4.2021; 17: 30.06.23; JE 23: Work Completed |  | 89.98%
124 | Sh. Sandeep Kumar Jakhar | ਸ਼੍ਰੀ ਸੰਦੀਪ ਜਾਖੜ, 97798-32712 | Sh. Sandeep Kumar Jakhar |  |  | Abohar |  | 81 | 81-ਅਬੋਹਰ | 81-Abohar | ਅਬੋਹਰ (ਸ਼੍ਰੀ ਰਾਹੁਲ ਕੋਸ਼ਲ, 97800-16670) | Abohar | Abohar | Augmentation and Rehabilitation of Main Pumping Station at Abohar | Work Completed | AMRUT |  | 5) | Non-Clog Horizontal Pumping Set 11 KV VCB Panel 400 KVA 11/0.433 KV ONAN Outdoor Transformer 300 KVA Silent DG Set with AMF | 4 1 1 1 |  | 1.36 | 1.21 | 100% | 100% | 1.21 | 20.4.2021 | 31.03.23 | [5 empty] | Work Completed |  | 100%
[6 empty] | Abohar |  | 81 | [5 empty] | Water Supply pipe line,Construction of 2 No. RCC OHSR 2 & 3 lac gallon capacity, Clear Water Tank ,Pump Chamber, Boundary Wall, | Proposed work | AMRUT 2.0- (T-2) |  | 1) | DI K-7 Water Supply pipe line, OHSR (2 & 3 lac galn capacity), Clear Water Tank , Pump Chamber, UGSR ( 0.50 Gallon) , UGSR Pumps 0.50 Gallon , S&S Tank, | 9: - 2No. 1Job 1 Job 3 Nos, 3 Nos. 1 job; 10: 124.87; JE 23: DPR under preparation stage
125 | Shri. Amandeep Singh Musafir | ਸ਼੍ਰੀ ਅਨਮਦੀਪ ਸਿੰਘ ਗੋਲਡੀ ਮੁਸਫ਼ਿਰ, 95010-25445 | Shri. Amandeep Singh Musafir |  | AAP | Fe | Firozepur | 82 | 82- ਬੱਲੂਆਣਾ Balluana | 82- Balluana | ਬੱਲੂਆਣਾ (ਸ਼੍ਰੀ ਹਰਸ਼ਰਨਜੀਤ ਸਿੰਘ, 96536-00048) | Balluana | Balluana | [6 empty] | JE 23: Presently no work ongoing by PWSSB
126 | Shri Gurmeet Singh Khudian | ਸ਼੍ਰੀ ਗੁਰਮੀਤ ਸਿੰਘ | Shri Gurmeet Singh Khudian |  | AAP | B1 | Bathinda | 83 | 83-ਲੰਬੀ | 83- Lambi | ਲੰਬੀ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) | Lambi | Lambi | [6 empty] | EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
127 | Shri. Amarinder Singh Raja warring | ਸ਼੍ਰੀ ਅਮਰਿੰਦਰ ਸਿੰਘ ਰਾਜਾ ਵੜਿੰਗ, 95691-01122 | Shri. Amarinder Singh Raja warring | ਪ੍ਰਿਤਪਾਲ ਸਰਮਾ 78886-36991 | INC | B2 | Sri Muktsar Sahib | 84 | 84- ਗਿੱਦਰਬਾਹਾਂ | 84- Gidderbaha | ਗਿੱਦਰਬਾਹਾਂ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Gidderbaha | Gidderbaha | Rehabilitation of existing structure of water supply | Work Completed | MDF |  | 1) | Repair of S/S Tank - Repair of C.W.T Const. of Raw Water Well- Const. of Toilet Block- Boundary Wall - P/F 20 BHP Raw Water Motor/ Pump Set -2 Nos. | 1 Job -1 Job 1 Job 1 Job 600 mtr 2 Nos. |  | 3.04 | 2.26 | 100% | 70% | 2.37 | 09.12.2021 | 31.03.2023 | PWSSB | W/s, Sew. & STP | Er. Rahul Kaushal Mob. 97800-16670 | Er. Chhinderpal Singh Mob. 75894-06164 | Sh. Lakhwinder Singh Mob.94179-35129 Sh. Vikesh Kumar Mob. 80538-95006 | Work Completed |  | 104.9%
[6 empty] | B2 |  | 84 | [5 empty] | Water Supply Work | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/S DI K-7 pipe | 9: 11000 Mtr; 10: 3.5; JE 23: DPR under preparation stage
[6 empty] | B2 |  | 84 | [5 empty] | Sewer work | Proposed work | Untied |  | 2) | Sew | 9: 6500 mtr; 10: 5.5; JE 23: DPR under preparation stage
[6 empty] | B2 |  | 84 | [5 empty] | Replacement of Water supply | Proposed work | Deposit work |  | 3) | Water Supply line House Conn. | 9: 4550 mtr 90 Nos.; 10: 0.9; JE 23: DPR under preparation stage
128 | Dr. Baljit Kaur | ਡਾ. ਬਲਜੀਤ ਕੌਰ , 98145-39535 | Dr. Baljit Kaur |  | AAP | B2 | Sri Muktsar Sahib | 85 | 85- ਮਲੋਟ | 85- Malout | ਮਲੋਟ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Malout | Malout | Sewer work | Ongoing Work | Special Assistance |  | 1) | Main sewer Rising Main 500mm i/d Rising Main 600mm i/d RCC Collecting Tank . STP 10.00 MLD Machinery | 2.95 Km 3600 Mtr 1500 Mtr 1 No. 1 No. 1 Job | 35.2 | 34.47 | 5.07 | 25% | 25% | 1.34 | 11.02.23 | 10.07.23 | PWSSB | W/s, Sew. & STP | Er. Rahul Kaushal Mob. 97800-16670 | Er. Chhinderpal Singh Mob. 75894-06164 | Sh. Harjinder Singh Mob. 94179-35189 Sh. Gagandeep Singh Mob. 95010-32836 | Work in progress
[6 empty] | B2 |  | 85 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  | 2) | Rising Main 900mm i/d DI D/F pipe 250mm & 450mm i/d W/s DI-K-7 Pipe Boundary Wall Pumping Macherary Transformer 250 KVR Gen. Set 150 KVA Clear Water Tank Const. of Pump Chamber. | 9: 6970 Mtr 135 Mtr 16320 mtr 840 mtr 2 Nos. 1 No. 1 No. 1 No. 1 No.; 10: 23.02; JE 23: DPR under preparation stage
129 | Shri. Jagdeep Singh (Kaka Brar) | ਜਗਦੀਪ ਸਿੰਘ (ਕਾਕਾ ਬਰਾੜ) 98550-74003 | Shri. Jagdeep Singh (Kaka Brar) |  | AAP | B2 | Sri Muktsar Sahib | 86 | 86-ਸ਼੍ਰੀ ਮੁਕਤਸਰ ਸਾਹਿਬ | 86- Muktsar | ਬਰੀਵਾਲਾ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Bariwala | Bariwala | Sewer work | Proposed work | SBM-2.0 |  | 1) | STP 2.00 MLD Main Sewer Branch Sewer DI Rising Main MPS Rising Main Roads | 1 No. 0.04 Km 8.25 Km 7.79 Km 1 No. 2000 Mtr Job | 31.13 | [5 empty] | DPR checked at HO & sent to SLTC |  | PWSSB | W/s | Er. Rahul Kaushal Mob. 97800-16670 | Er. Chhinderpal Singh Mob. 75894-06164 | Sh. Rajwant Singh Mob. 99886-51168 | DPR under preparation stage
[6 empty] | B2 |  | 86 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  | 2) | W/S DI K-7 pipe Machinery | 9: 9000 Mtr 4 No.; 10: 3.5; JE 23: DPR under preparation stage
130 | [5 empty] | B2 |  | 86 |  |  | ਸ਼੍ਰੀ ਮੁਕਤਸਰ ਸਾਹਿਬ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Shri Muktsar Sahib | Shri Muktsar Sahib | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  | 1) | W/s Dist line OHSR (2 LG Capacity) S&S tank WTP Main City Area Replacement ofW/s Dist.line S&S tank OHSR (2LG) Rising main WTP | 9: 45 Km 1 No. 1 NO. 2.60 MLD 88.26 Km 4 NO. 3 no. 1 km 1.6 MGD; 10: 51.83; ULB/ PWSSB 10: ULB/ DWSS; Scope (W/S, Sew, STP) 11: ---; EE 12: Er. Rahul Kaushal Mob. 97800-16670; SDE 13: Er. Chhinderpal Singh Mob. 75894-06164; JE 14: Sh. Rajwant Singh Mob. 99886-51168; JE 23: Tender called due date of opening 23.01.23
131 | Shri. Gurdit Singh Sekhon | ਸ਼੍ਰੀ ਗੁਰਦਿੱਤ ਸਿੰਘ ਸੇਖੋਂ, 98769-12201 | Shri. Gurdit Singh Sekhon |  | AAP | Moga | Faridkot | 87 | 87- ਫਰੀਦਕੋਟ | 87- Faridkot | ਫਰੀਦਕੋਟ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Faridkot | Faridkot | Prov. S/s Faridkot | Ongoing Work | HUDCO LOAN / PIDB/ Specail Assistance |  | 1) | Sewer MPS STP Road | 94.52 Km 1 Job 1 Job 1 Job |  | 118.15 | 86.95 | 80% | 80% | 100.13 | 16.06.2016 | 30.09.2023 | ULB | W/s, Sew | Sh. Supuinder Singh 94171-59123 | Sh. Gurpal Singh 95010-10971 | Sh. Parvesh Babu 95921-06376 | Work in progress |  | 115.2%
[6 empty] | Moga |  | 87 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  |  | Risning Main New Dist. Network House connection OHSR S&S tank | 9: 4.00 Km 38.00 5911 Nos. 1 No. 1 No.; 10: 18.77; JE 23: DPR under preparation stage
132 | Shri Kultar Singh Sandhwan | ਸ਼੍ਰੀ ਕੁਲਤਾਰ ਸਿੰਘ ਸੰਧਵਾਂ , 92164-00457 | Shri Kultar Singh Sandhwan |  | AAP | Moga | Faridkot | 88 | 88- ਕੋਟਕਪੂਰਾ | 88- Kotkapura | ਕੋਟਕਪੂਰਾ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Kotkapura | Kotkapura | Prov. S/s Kotkapura | Ongoing Work | HUDCO |  | 1) | Sewer W/s MPS STP Road | 92.33 Km 9.90 Km 2 Job 2 Job 1 Job |  | 108.73 | 89.43 | 80% | 80% | 92.79 | 16.06.2016 | 31.08.23 | PWSSB | W/s, Sew STP | Sh. Supuinder Singh 94171-59123 | Sh. Gurpal Singh 95010-10971 | Sh. Harrai Singh 94177-20400 | Work in progress |  | 103.8%
[6 empty] | Moga |  | 88 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  |  | New Dist. Network House connection | 9: 29.50 3945 Nos.; 10: 10.14; JE 23: DPR under preparation stage
133 | Shri. Amolak Singh | ਸ਼੍ਰੀ ਅਮੋਲਕ ਸਿੰਘ , 98780-72608 | Shri. Amolak Singh |  | AAP | Moga | Faridkot | 89 | 89- ਜੈਤੋ | 89- Jaitu | ਜੈਤੋ (ਸ਼੍ਰੀ ਸੁਪਿੰਦਰ ਸਿੰਘ, 94171-59123) | Jaitu | Jaitu | Prov. S/s Jaitu | Ongoing Work | HUDCO |  | 1) | Sewer MPS STP Road | 44.50 Km 1 Job 1 Job 1 Job |  | 45.03 | 35.26 | 80% | 80% | 40.15 | 16.06.2016 | 31.08.23 | PWSSB | W/s, Sew STP | Sh. Supuinder Singh 94171-59123 | Sh. Gurpal Singh 95010-10971 | Sh. Sukhjit Singh 94630-93993 | Work in progress |  | 113.9%
[6 empty] | Moga |  | 89 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  |  | New Dist. Network House connection OHSR S&S tank | 9: 6.73 898 Nos. 1 No. 1 No.; 10: 10.88; JE 23: DPR under preparation stage
134 | Shri Balkar Singh Sidhu | ਸ਼੍ਰੀ ਬਲਕਾਰ ਸਿੰਘ ਸਿੱਧੂ , 98721-00008 | Shri Balkar Singh Sidhu |  | AAP | B2 | Bathinda | 90 | 90- ਰਾਮਪੁਰਾ ਫੂਲ | 90- Rampura Phul | ਰਾਮਪੁਰਾ ਫੂਲ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Rampura Phul | Rampura Phul | Water Supply work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | WTP Distribution S&S Tanks | 1 No. 8500 Mtr S&S Tanks | 33.4 | [5 empty] | DNIT approved by Technical Sub Committee |  | ULB | --- | Er. Rahul Kaushal Mob. 97800-16670 | Er. Anubhav Singla Mob. 79865-07079 | Sh. Sarabjit Singh Mob. 96530-00429 | DPR under preparation stage
[6 empty] | B2 |  | 90 | [5 empty] | Sewer work | Proposed work | Untied |  | 2) | Replacement of Rising main | 9: 7.2 Km; 10: 9.12; JE 23: DPR under preparation stage
135 | [5 empty] | B2 |  | 90 |  |  | ਭਾਈਰੂਪਾ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Bhairoopa | Bhairoopa | Sewer work | Proposed work | SBM-2.0 |  | 1) | STP 3.00 MLD Main sewer Branch Sewer MPS Rising main Roads | 1 No. 0.86 Km 28.43 Km 1 No. 600mtr 1 Job. | 35.82 | [5 empty] | DPR yet to be received in Head Office |  | DWSS | --- | Er. Rahul Kaushal Mob. 97800-16670 | Er. Anubhav Singla Mob. 79865-07079 | Sh. Sarabjit Singh Mob. 96530-00429 | DPR under preparation stage
[6 empty] | B2 |  | 90 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-1) |  | 2) | WTP - S&S tanks - W/s Line | 9: 1 No. 1Job 32 Km; 10: 34.83; 16: Tender Called; JE 23: DPR under preparation stage
136 | Shri Balkar Singh Sidhu | ਸ਼੍ਰੀ ਬਲਕਾਰ ਸਿੰਘ ਸਿੱਧੂ , 98721-00008 | Shri Balkar Singh Sidhu |  |  | B2 | Bathinda | 90 | 90- ਰਾਮਪੁਰਾ ਫੁੱਲ | 90- Rampura Phul | ਭਗਤਾ ਭਾਈਕਾ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Bhagta Baika | Bhagta Baika | Sewer work | Proposed work | SBM-2.0 |  | 1) | STP 3.00 MLD Main Sewer Branch Sewer MPS Rising Main Roads | 1 No. 1.78 Km 26.36 Km 1 No. 1500 Mtr 1 Job | 46.11. | [5 empty] | DPR yet to be received in Head Office |  | ULB | --- | Er. Rahul Kaushal Mob. 97800-16670 | Er. Anubhav Singla Mob. 79865-07079 | Sh. Sarabjit Singh Mob. 96530-00429 | DPR under preparation stage
[6 empty] | B2 |  | 90 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Const. of S&S Tank Distribution Line WTP 1.00MGD Machinery OHSR 1.00 Lac Gallon DG Set 100 KVA | 9: 1 Job 32.42 Km 1 Job 1 Job 1 Job 1 job; 10: 15.67; 16: DPR's Prepared; JE 23: DPR under preparation stage
137 | Shri Balkar Singh Sidhu | ਸ਼੍ਰੀ ਬਲਕਾਰ ਸਿੰਘ ਸਿੱਧੂ, 98721-00008 | Shri Balkar Singh Sidhu |  |  | B2 |  | 90 | 90- ਰਾਮਪੁਰਾ ਫੁੱਲ | 90- Rampura Phul | ਮਲੂਕਾ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Maluka | Maluka | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  | 1) | WTP - 0.50 MGD Water supply line (Additional scope being considered for AMRUT DPR) | 9: 1 No. 4 Km; 10: 2.66; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: ---; EE 12: Er. Rahul Kaushal Mob. 97800-16670; SDE 13: Er. Amanpreet Singh Mob. 94785-44437; JE 14: Sh. Sarabjit Singh Mob. 96530-00429; JE 23: DPR under preparation stage
[6 empty] | B2 |  | 90 | [5 empty] | Sewer work | Proposed work | SBM-2.0 |  | 2) | STP- 2.0 MLD | 9: 1 No.; 10: 2.49; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
138 | [5 empty] | B2 |  | 90 |  |  | ਕੋਠਾਗੁਰੂ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Kothaguru | Kothaguru | Sewer work | Proposed work | SBM-2.0 |  | 1) | STP 2.00 MLD Main sewer Branch Sewer MPS Rising Main Roads | 1 No. 1.30 Km 19.13 Km 1 No. 2500 Mtr 1 Job. | 28.22 | [5 empty] | DPR checked at HO & sent to SLTC |  | ULB | --- | Er. Rahul Kaushal Mob. 97800-16670 | Er. Anubhav Singla Mob. 79865-07079 | Sh. Sarabjit Singh Mob. 96530-00429 | DPR under preparation stage
[6 empty] | B2 |  | 90 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-1) |  | 2) | Const. of S&S Tank Distribution Line WTP 0.50MGD Machinery OHSR 1.00 Lac Gallon DG Set 62.50 KVA Rising Main House connections | 9: 1 Job 23.61 Km 1 Job 1 Job 1 Job 1 Job 2780 Mtr 2492 Nos.; 10: 9.35; 16: DPR's Prepared; JE 23: DPR under preparation stage
139 | [5 empty] | B2 |  | 90 |  |  | ਮਹਿਰਾਜ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Mehraj | Mehraj | [6 empty] | ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
140 | Shri. Jagsir Singh | ਸ੍ਰੀ ਮਾਸਟਰ ਜਗਸੀਰ ਸਿੰਘ, 94636-29980 | Shri. Jagsir Singh |  | AAP | B2 | Bathinda | 91 | 91- ਭੁੱਚੋ ਮੰਡੀ | 91- Bhucho Mandi | ਗੋਨਿਆਨਾ Goniana | Goniana | Goniana | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Repair of S&S Tank Distribution Line House connections Machinery | 9: 1 Job 4634 Mtr 466 Nos. 1 Job; 10: 2.17; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: ---; EE 12: Er. Rahul Kaushal Mob. 97800-16670; SDE 13: Er. Amanpreet Singh Mob. 94785-44437; JE 14: Sh. Sarabjit Singh Mob. 96530-00429; JE 23: DPR under preparation stage
[6 empty] | B2 |  | 91 | [5 empty] | Sewer work | Proposed work | Untied |  | 2) | STP 4.00 MLD Rising Main 600mm i/d | 9: 1 No. 6700 Mtr; 10: 17.58; JE 23: DPR under preparation stage
141 | [5 empty] | B2 |  | 91 |  |  | ਭੁੱਚੋ ਮੰਡੀ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Bucho mandi | Bucho mandi | Water Supply work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Const. of S&S Tank Distribution Line H/connections WTP 0.50 MGD Machinery | 9: 1 Job 7604 Mtr 490 Nos. 1 Job 1 Job; 10: 41.26; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: ---; EE 12: Er. Rahul Kaushal Mob. 97800-16670; SDE 13: Er. Vikramjit Singh Mob. 86992-08205; JE 14: Sh. Maninder Singh 97808-80615; JE 23: DPR under preparation stage
[6 empty] | B2 |  | 91 | [5 empty] | Sewer work | Proposed work | Untied |  | 2) | STP 4.00 MLD Rising Main | 9: 1 No. 6700 Mtr; 10: 24.26; JE 23: DPR under preparation stage
142 | [5 empty] | B2 |  | 91 | 91- ਭੁੱਚੋ ਮੰਡੀ | 91- Bhucho Mandi | ਨਥਾਣਾ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Nathana | Nathana | Water Supply work | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Const. of S&S Tank Distribution Line H/connections WTP 0.50MGD Machinery OHSR 0.50 Lac Gallon R/M DG Set 62.50 KVA | 1 Job 6704 Mtr 450 Nos. 1 Job 1 Job 1 Job 2000 Mtr 1 job | 6.69 | [5 empty] | Tender Called |  | DWSS | --- | Er. Rahul Kaushal Mob. 97800-16670 | Er. Amanpreet Singh Mob. 94785-44437 | Sh. Sarabjit Singh Mob. 96530-00429 | DPR under preparation stage
[6 empty] | B2 |  | 91 | [5 empty] | Sewer work | Proposed work | SBM-2.0 |  | 2) | STP 2.00 MLD Main sewer Branch Sewer MPS Rising Main Roads | 9: 1 No. 1.45 Km 24.04 Km 1 No. 12450 Mtr 1 Job.; 10: 40.14; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
143 | [5 empty] | B1 |  | 91 |  |  | ਲਹਿਰਾ ਮਹੱਬਤ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) | Lehra Mohabat | Lehra Mohabat | Sewer work | Proposed work | SBM-2.0 |  |  | Main Sewer STP's MPS/IPS Rising Main Restoration of Road | 1.18 Km 1 No's / 2 MLD 1 No's 6.15 MLD 5 Kms 10105 Sqm | 20.23 | [5 empty] | DPR Under DWSS |  | ULB | - | - | - | - | DPR under preparation stage
144 | Shri. Jagroop Singh Gill |  | Shri. Jagroop Singh Gill |  |  | B1 |  | 92 | 92- ਬਠਿੰਡਾ ਸ਼ਹਿਰੀ | 92- Bathinda Urban | ਬਠਿੰਡਾ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Bathinda | Bathinda | Sewerage Construction/repair of manholes | Ongoing Work | Deposit work |  | 1) | construction/Raising of manhole Prov. & fixing MH Cover and frame | 50 Nos 75 Nos |  | 0.37 | 0.34 | 60% | 20% | 0.07 | 04.06.2021 | 31.07.23 | PWSSB | Sew | Sh. Maninder Singh (95306-34035) |  |  | work completed |  | 20.59%
[6 empty] | B1 |  | 92 | [5 empty] | Sewerage Scheme (Package 1-A) | Ongoing Work | AMRUT |  | 2) | UPVC pipe 200-315mm i/d RCC NP3 HDPE lining 400-600mm i/d PT Sewer 760 mm House connection | 51.98 Km 1.31 2.004 Km 5199 Nos |  | 48.53 | 20.2 | 85% | 69% | 13.82 | 13.11.2019 | 31.07.23 |  |  |  | Sh. Surinder Singh (70877-15814) | Sh. Om Parkash (97807-05961) | 85% work completed. 2 Km main sewer work not started due to non clearance by Railway deptt. |  | 68.42%
[6 empty] | B1 |  | 92 | [5 empty] | Sewerage Scheme ) | Ongoing Work | AMRUT |  | 3) | DI K-9 Pipe 350-1200 mm | 14.33 KM |  | 48.53 | 13.8 | 85% | 75% | 10.96 | 13.11.2019 | -- |  |  |  | Sh. Ashwani Kumar (94172-78866) | Sh. Manish Kumar (95015-35500) | 85% work completed. Balance work of 500 mm dia pipe line stopped by farmers |  | 79.42%
[6 empty] | B1 |  | 92 | [5 empty] | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  |  | Rehabilitation of Dist. network Distribution Line H/connections OHSR (2 LG) | 9: 47 Km 16 Km 12000 Nos. 2 No; 10: 35.98; JE 23: DPR under preparation stage |  |  | 14.33
145 | Shri. Jagroop Singh Gill | ਸ਼੍ਰੀ ਜਗਰੂਪ ਸਿੰਘ ਗਿੱਲ, 94174-27749 | Shri. Jagroop Singh Gill |  | AAP | B1 | Bathinda | 92 | 92- ਬਠਿੰਡਾ ਸ਼ਹਿਰੀ | 92- Bathinda Urban | ਬਠਿੰਡਾ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) |  |  | Water Supply & Sewerage Work | Ongoing Work | AMRUT/HUDCO/Deposit work |  | 4) | Main Sewer in Lateral Sewer MPS (Across sirhind canal MPS Kheta Singh Basti STP (4.5 MLD) Rehab. Of existing sewer DI Rising Main 20" i/d (Km) MPS & rising Main along sullage carrier Outlay sullage gravity 1200 mm dia Rising Main Storm Sewer Storm Sewer (Km) House connection Sewer Street Lights | 6.45 Km 93.47 Km 1 No. 1 No 1 No. 14 Km 6 Km 1 No. 12.48 Km 1.30 Km 2.30 Km 19350 (No) 1000 No |  | W/s Sewer = 50.04 Cr. Sewer = 149.53 Cr. | 150.15 | 80% | 51% | 76.15 | 03.06.2015 | -- | PWSSB | W/s | Sh. Maninder Singh (95306-34035) | Sh. Ashwani Kumar (94172-78866) Sh. Surinder Singh (70877-15814) | Sh. Om Parkash 9780705961 Abhisek Kumar 9815335817 Sh. Gurpreet Singh 7986505156 Sh. Kuldeep Sing 8360472929 Sh. Resham Singh 8054007651 | 80% work completed. Futher work heldup by the firm. Firm has gone to the arbitration and case is under hearing |  | 50.72%
[6 empty] | B2 |  | 92 | [5 empty] | OHSR of 5.00 lac gallons capacity | Ongoing Work | HUDCO |  | 5) | OHSR | 1 No |  | 50.04 | 2.92 | 89% | 50% | 1.5 | 20.04.2022 | 30.09.23 |  |  | Er. Rahul Kaushal Mob. 97800-16670 | Er. Vikramjit Singh Mob. 86992-08205 | Sh. Maninder Singh 97808-80615 Sukhwinder Singh 83605-07101 Sh. Ankush Kumar Mob. 88375-41312 | work in progress |  | 51.37%
[6 empty] | B2 |  | 92 | [5 empty] | Water Supply work | Proposed work | Untied |  | 2) | TW Rising Main Rehabilitation of Dist. Network New w/s line New Dist. Network HC | 9: 5 Nos, 2.65 Km., 80.90 Km., 59.35 Km 59.35 Km., 6756 Nos.; 10: 63.19; JE 23: DPR under preparation stage
[6 empty] | B2 |  | 92 | [5 empty] | Water Supply work | Proposed work | Deposit work |  | 3) | Clear water Sump well Raw Water Sump well CWT Baoundary wall Pump Chambers | 9: 1 Job 1 Job 1 Job 1 Job 1 Job; 10: 2.15; JE 23: DPR under preparation stage
146 | Smt. Amit Rattan Kotfatta | ਸ਼੍ਰੀ ਅਮੀਤ ਰਤਨ, 98767-00090 | Smt. Amit Rattan Kotfatta |  | AAP | B2 | Bathinda | 93 | 93- ਬਠਿੰਡਾ ਪੇਡੂ | 93- Bathinda Rural | ਕੋਟ ਫੱਤਾ (ਸ਼੍ਰੀ ਬਲਜੀਤ ਸਿੰਘ, 82849-14999) | Kot fatta | Kot fatta | Water Supply work | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Rehab. Od Dist. Network New Dist. Network HC Repair of S&S tank | 9: 2.33 Km 2.10 Km 691 Nos. 1 nos; 10: 3.07; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/s, Sew and STP; EE 12: Er. Rahul Kaushal Mob. 97800-16670; SDE 13: Er. Amanpreet Singh Mob. 94785-44437; JE 14: Sh. Amar Singh Mob. 84279-40992; JE 23: DPR under preparation stage
[6 empty] | B2 |  | 93 | [5 empty] | Sewer work | Proposed work | Untied |  | 2) | STP upgradation on SBR technology - 3.00 MLD Sewer Line | 9: 1 NO. 15 Km; 10: 12; JE 23: DPR under preparation stage
147 | [5 empty] | B1 |  | 93 |  |  | ਸੰਗਤ ਮੰਡੀ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) | Sangat Mandi | Sangat Mandi | [6 empty] | ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S, Sew; EE 12: Sh. Maninder Singh 9530634035; SDE 13: Sh. Ashwani Kumar (94172-78866); JE 14: Sh. Manish Kumar (95015-35500)
148 | [5 empty] | B1 |  | 93 |  |  | ਕੋਟ ਸਮੀਰ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) | Kot Shamir | Kot Shamir | Providing 100% W/s, Sewerage and STP | Proposed work | SBM-2.0 |  | 1) | Sewer MPS, STP=(2 MLD) and Main Sewer & Rising Main | 1 No. 1 No. 7.5 Km | 30 | [5 empty] | DPR checked at HO & sent to SLTC |  | ULB | - | Sh. Maninder Singh (95306-34035) | Sh. Surinder Singh (70877-15814) | Sh. Gurpreet Singh (79865-05156) | DPR under preparation stage
149 | Smt. Baljinder Kaur | ਸ਼੍ਰੀਮਤੀ ਬਲਜਿੰਦਰ ਕੌਰ, 98555-64264 | Smt. Baljinder Kaur |  | AAP | B1 | Talwandi Saboo | 94 | 94- ਤਲਵੰਡੀ ਸਾਬੋ | 94- Talwandi Sabo | ਤਲਵੰਡੀ ਸਾਬੋ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) | Talwandi Saboo | Talwandi Saboo | Sewerage Work | Ongoing Work | MDF |  | 1) | DI Pipe line 600 mm dia HDPE pipe sewer | 10500 mtr 1139 mtr |  | 17.94 | 12.78 | 73% | 30% | 3.86 | 14.10.22 | 30.09.23 | ULB | - | Sh. Maninder Singh 9530634035 | Sh. Rajinder Singh (75081-48318) | Sh. Manish Kumar (95015-35500) | Inspection of 1500 Mtr. DI pipe done and material is likely to be reached at site within 3-4 days |  | 30.2%
150 |  |  |  |  | AAP | B1 | Talwandi Saboo | 94 |  |  | ਰਾਮਾਂ ਮੰਡੀ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) | Raman Mandi | Raman Mandi | 5 MLD Sewage Treatment Plant | Ongoing Work | HUDCO |  | 1) | 5 MLD STP | 1 No. |  | 6.93 | 7.29 | 40% | 31% | 2.25 | 17.12.21 | 31.07.23 | ULB | - | Sh. Maninder Singh 9530634035 | Sh. Ashwani Kumar (94172-78866) | Sh. Manish Kumar (95015-35500) | Work heldup by the firm for the last 7 months. Bank Guranttee released by EE.1No.Bathinda. |  | 30.86%
[6 empty] | B1 |  | 94 | [5 empty] | Raman Providing W/s | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Water Supply W/s WTP OHSR = 1.5 Glsn | 9: 17.5 Km 1 MGD 1 No.; 10: 48.15; JE 23: DPR under preparation stage
151 | Shri. Sukhveer Singh Maiserkhana | ਸ਼੍ਰੀ ਸੁਖਵੀਰ ਸਿੰਘ ਮਾਈਸਰਖਾਨਾ, 94171-59642 | Shri. Sukhveer Singh Maiserkhana |  | AAP | B1 | Bathinda | 95 | 95- ਮੋੜ | 95- Maur | ਮੋੜ (ਸ਼੍ਰੀ ਮਨਿੰਦਰ ਸਿੰਘ, 95306-34035) | Maur | Maur | Maur Providing W/s | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Water Supply W/s Aug. of WTP | 9: 42.5 Km 1 MGD; 10: 46.44; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S, Sew; EE 12: Sh. Maninder Singh 9530634035; SDE 13: Sh. Amanpreet (94785-44437); JE 14: Sh. Manish Kumar (95015-35500); JE 23: DPR under preparation stage
152 | Dr. Vijay Singla | ਡਾ. ਵਿਜੈ ਸਿੰਗਲਾ, 98761-27161 | Dr. Vijay Singla |  | AAP | Mansa | Mansa | 96 | 96- ਮਾਨਸਾ | 96- Mansa | ਮਾਨਸਾ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Mansa | Mansa | Prov. W/S & Sew., Roads, Street lights at Mansa (Cluster tender) | Ongoing Work | HUDCO |  | 1) | W/S W/s connection Water meter Sewer lines Sew Connection Const. of Road Street light Desilting by super sucker 16"= 32"= | 6.54 Km 1430 Nos. 15014 Nos. 10.79 Km 2466 No. 43472 sqm 120 Nos. 16"=2000mtr 32"=1730 mtr |  | 13.48 | 12.48 | 90% | 70% | 9.6 | 10.05.16 | 31.07.23 | PWSSB | W/S, Sew & STP | Er. Amandeep Singh 9646166990 | Er. Raj Kumar 9872343483 | Er. Sourav Jain 8847254873 Er. Narinder Sharma 9041788003 |  |  | 76.92%
| Dr. Vijay Singla | ਡਾ. ਵਿਜੈ ਸਿੰਗਲਾ, 98761-27161 | Dr. Vijay Singla |  |  | Mansa | Mansa | 96 | 96- ਮਾਨਸਾ | 96- Mansa | ਮਾਨਸਾ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Mansa | Mansa | Water supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Rehabilit.of Distribution network HSC Replacement of Filter media in WTP Repair of S & S Tank Road cutting and Restoration. Replacement of W/S line | 9: 28.910 km. 3260 Nos. 1 Job 1Job 1 Job 1.04 km; 10: 8.72; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S, Sew & STP; EE 12: Er. Amandeep Singh 9646166990; SDE 13: Er. Raj Kumar 9872343483; JE 14: Er. Sourav Jain 8847254873 Er. Narinder Sharma 9041788003; JE 23: DPR under preparation stage
154 | Dr. Vijay Singla | ਡਾ. ਵਿਜੈ ਸਿੰਗਲਾ, 98761-27161 | Dr. Vijay Singla |  |  | Mansa | Mansa | 96 | 96- ਮਾਨਸਾ | 96- Mansa | ਭੀਖੀ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Bhikhi | Bhikhi | Prov. W/S & Sew., Roads, Street lights at Bhikhi (Cluster tender) | Ongoing Work | HUDCO |  | 1) | W/S = W/s connection.= Water meter= Sewer lines Sew. Connection.. Const. of Road Street light | 3.55 Km 641 Nos. 3000Nos. 1.37 Km 316 Nos. 4919 sqm =40Nos. |  | 2.93 | 2.66 | 90% | 76% | 2.02 | 10.05.16 | 31.07.23 | PWSSB | W/S, Sew & STP | Er. Amandeep Singh 9646166990 | Er. Lalit Mittal 9872730032 | Er. Ramnik 9872690521 |  |  | 75.94%
154 | [5 empty] | Mansa | Mansa | 96 | [5 empty] | Prov. W/S & Sew. Line | Ongoing Work | HUDCO |  | 1) | UPVC Pipe 200 mm o/d DI K7 pipe 100mm i/d Const. of Road | 9: 2520 Mtr 4534 Mtr 1682 Sqm; 11: 3.33; 12: 1.86; 13: 98%; 14: 75%; 15: 1.4; 16: 13.01.21; 17: 31.07.23 |  | 75.27%
[6 empty] | Mansa |  | 96 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Distribution network HSC Road cutting and Restoration | 9: 2.296 km. 250 nos. 1 Job; 10: 0.45; JE 23: DPR under preparation stage
155 | Dr. Vijay Singla | ਡਾ. ਵਿਜੈ ਸਿੰਗਲਾ, 98761-27161 | Dr. Vijay Singla |  |  | Mansa |  | 96 | 96- ਮਾਨਸਾ | 96- Mansa | ਜੋਗਾ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Joga | Joga | Water supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Dist.network HSC | 9: 3.3 km. 360 nos.; 10: 0.65; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: Er. Amandeep Singh 9646166990; SDE 13: Er. Raj Kumar 9872343483; JE 14: Er. Sourav Jain 8847254873 Er. Narinder Sharma 9041788003; JE 23: DPR under preparation stage
[6 empty] | Mansa |  | 96 | [5 empty] | Sewer | Proposed work | SBM-2.0 |  | 2) | Sewer line R/M 300 mm i/d R/M 400 mm i/d | 9: 5285 mtr 100mtr 100mtr; 10: 18.29; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
156 | Shri. Gurpreet Singh Banawali | ਸ਼੍ਰੀ ਗੁਰਪ੍ਰੀਤ ਸਿੰਘ ਬਣਾਂਵਾਲੀ, 98159-24007 | Shri. Gurpreet Singh Banawali |  | AAP | Mansa | Mansa | 97 | 97- ਸਰਦੂਲਗੜ੍ਹ | 97- Sardulgarh | ਸਰਦੂਲਗੜ੍ਹ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Sardulgarh | Sardulgarh | Prov. W/S & Sew., Roads, Street lights at Sardulgarh (Cluster tender) | Ongoing Work | HUDCO |  | 1) | W/S W/s connection Water meter Sewer lines Sew. Connection Const. of Road Street light Desilting by super sucker 16" 32" | 2.40 Km 526 Nos. 3870Nos. 3.78 Km 1323 Nos. =15968 sqm =30Nos. 16" 32" |  | 5.61 | 4.53 | 90% | 74% | 3.38 | 10.05.16 | 31.07.23 | PWSSB | W/S, Sew & STP | Er. Amandeep Singh 9646166990 | Er. Raj Kumar 9872343483 | Er. Davinder Kumar 9872595044 Er. Deepak Saini 9034207889 |  |  | 74.61%
[6 empty] | Mansa | Mansa | 97 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Dist.Network HSC Road cutting & Restoration. | 9: 14.653 Km. 509 Nos. 1Job; 10: 3.16; SDE 13: Er. Raj Kumar 9872343483; JE 14: Er. Davinder Kumar 9872595044 Er. Deepak Saini 9034207889; JE 23: DPR under preparation stage
157 | Shri. Budh Ram | ਪ੍ਰਿੰਸੀਪਲ ਬੁੱਧ ਰਾਮ, 98159-37418 | Shri. Budh Ram |  | AAP | Mansa | Mansa | 98 | 98- ਬੁਢਲਾਡਾ | 98- Budhlada | ਬੁਢਲਾਡਾ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Budhlada | Budhlada | Prov. W/S & Sew., Roads, Street lights at Budhlada(Cluster tender) | Ongoing Work | HUDCO |  | 1) | W/S W/s connection Water meter OHSR WTP Sewer lines Sew. Connection Const. of Road Street light (Nos.) | 17.42 Km 2500 Nos. 15014 Nos. 1 No. 1 Nos. =32.96 Km =4800 No. =102121 sqm 223Nos. |  | 31.98 | 28.5 | 91% | 90% | 24.91 | 10.05.16 | 31.07.23 | PWSSB | W/S, Sew & STP | Er. Amandeep Singh 9646166990 | Er. Lalit Mittal 9872730032 | Er. Sukhwinder Singh 9888776152 |  |  | 87.4%
[6 empty] | Mansa |  | 98 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | Rising main New Dist.network HSC Road cutting and Restoration. UPVC overflow pipe | 9: 1.18 km. 17.743 km. 2500 Nos. 1 job 250 mtr; 10: 7.29; EE 12: Er. Amandeep Singh 9646166990; SDE 13: Er. Lalit Mittal 9872730032; JE 14: Er. Sukhwinder Singh 9888776152; JE 23: DPR under preparation stage
[6 empty] | Mansa |  | 98 | [5 empty] | W/S and Sew. | Proposed work | Special Assistance |  | 2) | W/S W/S House connection Sewer Sewer House Connt | 9: 22.24 km 2500 Nos. 14.43 Km 1466 Nos.; 10: 24.24; 13: 35%; 14: 10%; EE 12: Er. Amandeep Singh 9646166990; SDE 13: Er. Lalit Mittal 9872730032; JE 14: Er. Sukhwinder Singh 9888776152; JE 23: DPR Approved Tender Called & Opened on 27.01.2023
158 | Shri. Budh Ram | ਪ੍ਰਿੰਸੀਪਲ ਬੁੱਧ ਰਾਮ, 98159-37418 | Shri. Budh Ram |  |  | Mansa |  | 98 | 98- ਬੁਢਲਾਡਾ | 98- Budhlada | ਬਰੇਟਾ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Baretta | Baretta | Prov. W/S & Sew., Roads, Street lights at Baretta(Cluster tender) | Ongoing Work | HUDCO |  | 1) | W/S W/s connection OHSR Water meter Sewer lines Sew. Connection. Const. of Road Street light | 2.66 Km 582 Nos. 1 No. 3147 Nos. 3.07 Km 706 Nos. 14559 sqm =45Nos. |  | 4.5 | 4.71 | 90% | 63.69% | 3 | 10.05.16 | 31.07.23 | PWSSB | W/S, Sew & STP | Er. Amandeep Singh 9646166990 | Er. Lalit Mittal 9872730032 | Er. Ramnik 9872690521 |  |  | 63.69%
[6 empty] | Mansa |  | 98 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Distribution network OHSR - (0.50 LG) HSC Road cutting and Restoration S& S tank- | 9: 9.265 km. 1 No 1000 nos. 1 Job 1 No.; 10: 5.28; SDE 13: Er. Lalit Mittal 9872730032; JE 14: Er. Ramnik 9872690521; JE 23: DPR under preparation stage
[6 empty] | Mansa |  | 98 | [5 empty] | W/S and Sew. | Proposed work | Special Assistance |  | 3) | W/S W/S House connection Sewer Sewer House Connection | 9: 12.67km 1274 Nos. 8.37 Km 900 nos.; 10: 12.57; SDE 13: Er. Lalit Mittal 9872730032; JE 14: Er. Ramnik 9872690521; JE 23: DPR under preparation stage
159 | Shri. Budh Ram | ਪ੍ਰਿੰਸੀਪਲ ਬੁੱਧ ਰਾਮ, 98159-37418 | Shri. Budh Ram |  |  | Mansa |  | 98 | 98- ਬੁਢਲਾਡਾ | 98- Budhlada | ਬੋਹਾ (ਸ਼੍ਰੀ ਅਮਨਦੀਪ ਸਿੰਘ, 96461-66990) | Boha | Boha | Prov. Sew., Roads, Street lights at Boha (Cluster tender) | Ongoing Work | HUDCO |  | 1) | Sewer lines Sew. Connections STP =1No. MPS =1 No. Water meter Street light Const. of Road | 31.73 Km 4930 No. STP =1No. MPS =1 No. 1800Nos. =335Nos. =103493 sqm |  | 34.09 | 25.84 | 92% | 89% | 23 | 10.05.16 | 31.07.23 | PWSSB | W/S | Er. Amandeep Singh 9646166990 | Er. Raj Kumar 9872343483 | Er. Davinder Kumar 9872595044 Er. Deepak Saini 9034207889 |  |  | 89.01%
[6 empty] | Mansa |  | 98 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Dist.Network HSC WTP (0.75 MGD) OHSR (1 Lacs glns) Road cutting & Restoration. | 9: 11.54 Km. 450 Nos. 1 No. 1 No. 1Job; 10: 7.7; SDE 13: Er. Raj Kumar 9872343483; JE 14: Er. Davinder Kumar 9872595044 Er. Deepak Saini 9034207889; JE 23: DPR under preparation stage
160 | Shri. Barinder Kumar Goyal Vakeel | ਸ਼੍ਰੀ ਬਰਿੰਦਰ ਕੁਮਾਰ ਗੋਇਲ, 98886-22550 | Shri. Barinder Kumar Goyal Vakeel |  | AAP | S | Sangrur | 99 | 99-ਲਹਿਰਾ | 99- Lehra | ਲਹਿਰਾਗਾਗਾ, (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Lehragagga | Lehragagga | Rising Main Work | Ongoing Work | Deposit work |  | 1) | R/Main 400mmi/d Hatch Box Pumping station | 2000 mtr. 10 No. 1no. |  | 1.78 | 0.96 | 40% | - | - | 30.12.2021 | 30.09.2022 | PWSSB | STP (Deposit Work) | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Gurpreet Singh 96461-51496 | Sh. Tajinder Garg 96468-88325 | Work Halted due to Funds not Received. |  | #VALUE!
[6 empty] | S |  | 99 | [5 empty] | Storm Water Drainage system | Ongoing Work | Deposit work |  | 2) | 160mmi/d 315mmi/d | 120 mtr. 1212 mtr. |  | 0.91 | 0.65 | - | - | 0 | 31.12.2021 | 30.09.2022 | [5 empty] | Material Procured on site but work not started due to funds not received |  | 0%
161 | [5 empty] | S |  | 99 |  |  | ਮੂਨਕ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Moonak | Moonak | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 7.37 Km 1600 Nos. 4.63 MLD 0.10 Km 1.20 KM; 10: 12.66; 16: DPR approved by Technical Sub Committee/SLTC; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: STP, MPS (Deposit Work); JE 23: DPR under preparation stage
162 | [5 empty] | S |  | 99 |  |  | ਖਨੌਰੀ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Khanauri | Khanauri | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - Clear Water Pipeline | 9: 5.20 Km 1100 Nos. 3.59 MLD 1.20 Km 0.10 KM; 10: 11.18; 16: DNIT approved by Technical Sub Committee; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: WS/Sew/ STP; JE 23: DPR under preparation stage
163 | Shri. Harpal Singh Cheema | ਸ਼੍ਰੀ ਹਰਪਾਲ ਸਿੰਘ ਚੀਮਾ, 98149-15357 | Shri. Harpal Singh Cheema |  | AAP | S | Sangrur | 100 | 100- ਦਿੜਬਾ | 100- Dirba | ਦਿੜਬਾ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Dirba | Dirba | STP 3 MLD | Ongoing Work | HUDCO |  | 1) | 1 no. STP | 3 MLD |  | 7.62 | 5.25 | 50% | 50% | 2.69 | 17.12.2021 | 16.09.23 | PWSSB | W/S , SEW | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Gurpreet Singh 96461-51496 | Sh. Simranjeet singh 94642-61461 | Work in Progress . |  | 51.24%
[6 empty] | S |  | 100 | [5 empty] | Sew Work & R/Main and H.C and MPs at Dirba | Ongoing Work | Special Assistance |  | 1) | Sew R /Main H.C MPS | 9: 11.585 Km. 0.600 Km 800 no. 1 No.; 10: 10; 11: 0; 12: 6.64; 13: 30%; 14: 15%; 15: 0.92; JE 23: Work in Progress .
[6 empty] | S |  | 100 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - | 9: 19.99 Km 2500 Nos. 4.31 MLD 7.50 Km; 10: 21.64; JE 23: DPR under preparation stage
164 | Shri. Aman Arora | ਸ਼੍ਰੀ ਅਮਨ ਅਰੋੜਾ, 93570-55555 | Shri. Aman Arora |  | AAP | S | Sangrur | 101 | 101- ਸੁਨਾਮ | 101- Sunam | ਚੀਮਾ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Cheema | Cheema | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Rehabilit of Dist Network Dist.network House Connection WTP Raw Water Pipeline - | 14.50 Km 4.00 Km 1000 Nos. 2.95 MLD 6.50 Km | 17.37 | [5 empty] | DNIT approved by Technical Sub Committee |  | PWSSB | Sew, W/S, STP | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Gurpreet Singh 96461-51496 | Sh. Simranjeet singh 94642-61461 | DPR under preparation stage
[6 empty] | S |  | 101 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | STP's (1 No's / 2 MLD) Rising Main (6.40 Km) | 9: 1 No. 2 MLd 6.40 Km; 10: 14.31; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
165 | [5 empty] | S |  | 101 |  |  | ਸੁਨਾਮ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Sunam | Sunam | Sew Work & R/Main and H.C at sunam | Proposed work | CM Annoucement |  | 1) | Sew- R/Main H.C - | 6.330 Km 1.300 Km 1500 no. | 6.34 |  | 4.04 | 40% | 25% | 1.04 | 10.02.23 | 09.11.23 | PWSSB | MPS/STP (Deposit work) | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Gurpreet Singh 96461-51496 | Sh. Simranjeet singh 94642-61461 | Financial bid open under process
[6 empty] | S |  | 101 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Rehabilit of Dist Network House Connection WTP Raw Water Pipeline - | 9: 15.97 Km 6080 Nos. 16.50 MLD 14.00 Km; 10: 47.98; JE 23: DPR under preparation stage
166 | [5 empty] | S |  | 101 |  |  | ਲੋਗੋਵਾਲ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Longowal | Longowal | 5 MLD STP at Longowal | Ongoing Work | HUDCO |  | 1) | 5 MLd STP | 1 no. |  | 14.1 | 8.2 | 52% | 48 | 3.96 | 10.07.2020 | 30.09.23 | PWSSB | W/S , SEW | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Bhavesh Bansal 94174-94131 | Sh. Simranjeet singh 94642-61461 | LD Imposed 1% |  | 48.29%
[6 empty] | S |  | 101 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - | 9: 1.83 Km 2700 Nos. 6.40 MLD 8.50 Km; 10: 21.01; JE 23: DPR under preparation stage
167 | Shri. Labh Singh Ugoke | ਸ਼੍ਰੀ ਲਾਭ ਸਿੰਘ ਉਗੋਕੋ, 98552-05290 | Shri. Labh Singh Ugoke |  | AAP | S | Barnala | 102 | 102- ਭਦੋੜ | 102- Bhadaur | ਤਪਾ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Tappa | Tappa | 5 MLD STP at Tappa | Ongoing Work | MDF |  | 1) | 5 MLD STP | 1 no. |  | 13.02 | 8.2 | 70% | 37 | 3.02 | 10.07.2020 | 30.09.23 | ULB | ULB | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Gurpreet Singh Talwandi 82830-11782 | Sh. Gurjinder Singh 9417046798 | LD Imposed 1% |  | 36.83%
[6 empty] | S |  | 102 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - | 9: 3.00 Km 2020 Nos. 6.68 MLD 15.00 Km; 10: 26.41; JE 23: DPR under preparation stage
168 |  |  |  |  | AAP | S | Barnala | 102 |  |  | ਭਦੋੜ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Bhadaur | Bhadaur | 3 MLD STP at Bhadaur | Ongoing Work | HUDCO |  | 1) | 3 MLD sTP | 1 no. |  | 11.85 | 5.25 | 15% | 7% | 0.4 | 17.12.2021 | 30.09.23 | PWSSB | WS,Sew., MPS | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Gurpreet Singh Talwandi 82830-11782 | Sh. Gurjinder Singh 9417046798 | LD Imposed 1% amounting Rs. 5,25,000/- |  | 7.619%
[6 empty] | S |  | 102 | [5 empty] | R/Main and 3 MLD STP at Bhadaur | Proposed work | Special Assistance |  | 1) | R/Main STP | 9: 3.250 Km 1 no.; 10: 7.89; 13: 10%; 14: 5%; 15: 0.23; JE 23: Technical bid open under process
[6 empty] | S |  | 102 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - | 9: 4.60Km 1000 Nos. 4.68 MLD 8.00 Km; 10: 35.75; JE 23: DPR under preparation stage
169 | Shri. Gurmeet Singh Meet Hayer | ਸ਼੍ਰੀ ਗੁਰਮੀਤ ਸਿੰਘ ਮੀਤ ਹੇਅਰ, 97800-00971 | Shri. Gurmeet Singh Meet Hayer |  | AAP | S | Barnala | 103 | 103- ਬਰਨਾਲਾ | 103- Barnala | ਬਰਨਾਲਾ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Barnala | Barnala | [6 empty] | ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: WS,Sew, MPS; EE 12: Sh. Satwinder Singh Dhillon 97800-14399; SDE 13: Sh. Gurpreet Singh Talwandi 82830-11782; JE 14: Sh. Gurjinder Singh 9417046798; JE 23: Presently no work ongoing by PWSSB
170 | [5 empty] | S |  | 103 |  |  | ਧਨੋਲਾ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Dhanaula | Dhanaula | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - | 9: 6.50 Km 1500 Nos. 4.90 MLD 8.00 Km; 10: 15.51; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: STP; JE 23: DPR under preparation stage
[6 empty] | S |  | 103 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | Main Sewer STP's MPS/IPS Rising Main | 9: 0.20 Km 1 No's / 3 MLD 1 No's / 8 MLD) 0.400 Km; 10: 10.64; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
171 | [5 empty] | S |  | 103 |  |  | ਹੰਡਿਆਇਆ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Handiaya | Handiaya | Sew Work & R/Main | Ongoing | Special Assistance |  | 1) | Sew R/Main H.C | 3.830 Km 3.100 Km 750 no. | 6.01 |  | 4.02 | 15% | 15% | 0.62 |  |  | PWSSB | W/S, Sew. | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Gurpreet Singh Talwandi 82830-11782 | Sh. Gurjinder Singh 9417046798 | Work in progress
[6 empty] | S |  | 103 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-2) |  |  | Dist Network House Connection | 9: 5.70 Km 1000 Nos; 10: 2.05; 16: DNIT approved by Technical Sub Committee; JE 23: DPR under preparation stage
[6 empty] | S |  | 103 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | Main Sewer STP's MPS/IPS Rising Main | 9: 0.40 Km 1 No's / 2 MLD 1 No's / 6 MLD 0.05 Km; 10: 6.75; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
172 | Smt. Mahammad Jamil Ur Rahman | ਡਾ. ਮੁਹੰਮਦ ਜਮੀਲ ਉਰ ਰਹਿਮਾਨ, 98142-52012 | Smt. Mahammad Jamil Ur Rahman |  | AAP | S | Malerkotla | 105 | 105- ਮਲੇਰਕੋਟਲਾ | 105- Malerkotla | ਮਲੇਰਕੋਟਲਾ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Malerkotla | Malerkotla | 22 MLD STP at Malerkotla | Ongoing Work | AMRUT |  | 1) | 22 MLD STP | 1 No. |  | 41.54 | 24.9 | 70% | 53% | 13.26 | 29.07.2020 | 30.09.23 | ULB | ULB | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Rajinder Kumar Garg 95010-75088 |  | LD Imposed 1% |  | 53.25%
[6 empty] | S |  | 105 | [5 empty] | Storm Water Drainge System | Ongoing Work | AMRUT |  | 2) | Sewer liine(mtr) DIK7 600mm Pumpset- 2no. | 7770 mtr 600mtr. 2 no. |  | 26.7 | 3.58 | 60% | 46 | 1.65 | 08.12.2020 | 30.09.23 | [5 empty] | Work in Progress. LD Imposed 5% |  | 46.09%
[6 empty] | S |  | 105 | [5 empty] | Sewerage and disilting work | Ongoing Work | MDF |  | 3) | RCC NP3 800mmid- RCC NP3 900mmid- RCC NP31200mmid- | 1230 mtr 900 mtr 3990 mtr |  | 18.05 | 13.6 | 55% | 55% | 5.66 | 11.10.2021 | 30.09.23 | [5 empty] | Work in progress. LD Imposed 3% |  | 41.62%
[6 empty] | S |  | 105 | [5 empty] | Sewerage Work | Ongoing Work | AMRUT |  | 1) | L-Sew Main Sew- Sew. H. conn. | 9: 15198 mtr. 2939 mtr. 1447 no.; 11: 11.71; 12: 8.79; 13: 85%; 14: 85%; 15: 7.94; 16: 17.12.2021; 17: 30.09.23 |  | 90.33%
173 | Prof. Jaswan Singh Gajjan Majra | ਪ੍ਰੋ. ਜਸਵੰਤ ਸਿੰਘ ਗੱਜਣ ਮਾਜਰਾ., 94912-98000 | Prof. Jaswan Singh Gajjan Majra |  | AAP | S | Malerkotla | 106 | 106- ਅਮਰਗੜ੍ਹ | 106- Amargarh | ਅਹਿਮਦਗੜ੍ਹ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Ahmedgarh | Ahmedgarh | 5 MLD STP at Ahmedgarh | Ongoing Work | HUDCO |  | 1) | 1 no. STP | 5MLD |  | 10.16 | 8.2 | 45% | 37% | 2.28 | 10.07.2020 | 30.09.23 | ULB | ULB | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Rajinder Kumar Garg 95010-75088 | Sh. Piyush Garg 90412-28138 | LD Imposed 1% |  | 27.8%
[6 empty] | S |  | 106 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - | 9: 2.64 Km 496 Nos. 7.35 MLD 0.10 Km; 10: 12.84; JE 23: DPR under preparation stage
174 | [5 empty] | S |  | 106 |  |  | ਅਮਰਗੜ੍ਹ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Amargarh | Amargarh | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Dist.network House Connection WTP Raw Water Pipeline - | 19.26 Km 4200 Nos. 1.95 MLD 2.50 Km | 7.9 | [5 empty] | DPR's Prepared |  | ULB | ULB | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Parminder Singh 80544-79795 | Sh. Tajinder Garg 96468-88325 | DPR under preparation stage
[6 empty] | S |  | 106 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | STP's Rising Main | 9: 1 No's / 2 MLD 0.05 Kms; 10: 5.45; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
175 | Shri. Bhagwant Mann | ਸ਼੍ਰੀ ਭਗਵੰਤ ਮਾਨ | Shri. Bhagwant Mann |  | AAP | S | Sangrur | 107 | 107- ਧੂਰੀ | 107- Dhuri | ਧੂਰੀ , (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Dhuri | Dhuri | Sewerage work | Ongoing Work | MDF |  | 1) | UPVC Pipe Sew 160mm/id - 200mm i/d- 250 mmi/d- Inter locking - House conn- | 5819 mtr 5911 mtr 590 mtr 40588 sqm 1700 no |  | 0.15 | 8.01 | 80% | 66% | 5.29 | 28.09.2021 | 30.09.23 | PWSSB | W/S , Sew. | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Parminder Singh 80544-79795 | Sh. Tajinder Garg 96468-88325 | Work in Progress. Notice Issued to speed up progress vide EE letter no.4335 dt. 04.10.2022 |  | 66.04%
[6 empty] | S |  | 107 | [5 empty] | Water Supply and Sewerage work at Dhuri. | Ongoing Work | HUDCO |  | 2) | Main Sewer (km ) Lateral Sewer (km) House Conn. (No) STP 5MLD (No) 6 MLD (No) Interlocking Tiles (Sqm) Bitumen Roads (Sqm) | 1.17 km 47.92 km 10817 No STP 1 No. 1 No. 107047 Sqm 54589 Sqm |  | 91.2 | 9.45 | 75% | 72 | 0 | 17.06.2016 | 30.09.23 | [5 empty] | LD Imposed 2% |  | 0%
[6 empty] | S |  | 107 | [5 empty] | Sewerage and STP Works | Ongoing Work | HUDCO |  | 3) | Main Sewer (km ) Lateral Sewer (km) House Conn. (No) STP 5MLD (No) 6 MLD (No) Interlocking Tiles (Sqm) Bitumen Roads (Sqm) | 1.17 km 47.92 km 10817 No STP 1 No. 1 No. 107047 Sqm 54589 Sqm |  | 50 | 42.31 | 75% | 63% | 31.58 | 17.06.2016 | 30.09.23 | [5 empty] | Work in Progress LD Imposed 1% |  | 74.64%
[6 empty] | S |  | 107 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Rehabilt of Dist.network House Connection WTP Raw Water Pipeline - | 9: 5.50 Km 1473 Nos. 14.13 MLD 3.70 Km; 10: 33.39; JE 23: DPR under preparation stage
[6 empty] | S |  | 107 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | STP's MPS/IPS Rising Main | 9: 1 No's / 6 MLD 1 No's / 20 MLD 100 Km; 10: 18.7; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
[6 empty] | S |  | 107 | [5 empty] | Sew Work & H.C and Roads Work at Dhuri | Ongoing Work | CM Annoucement |  | 1) | Sew H.C | 13.61 Km 2177 no. | 14.24 |  | 7.69 | 50% | 19% | 1.49 | 10.02.23 | 09.02.24 | [5 empty] | Work in progress
176 | Smt. Narinder Kaur Bharaj | ਸ਼੍ਰੀ ਨਰਿੰਦਰ ਕੌਰ ਭਰਾਜ, 90411-85923 | Smt. Narinder Kaur Bharaj |  | AAP | S | Sangrur | 108 | 108- ਸੰਗਰੂਰ | 108- Sangrur | ਸੰਗਰੂਰ (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Sangrur | Sangrur | 6 no. T/w at Sangrur | Ongoing Work | MDF |  | 1) | T/Well - | 6 no |  | 9.34 | 1.26 | 30% | 30% | 0.45 | 17.11.2021 | 30.09.23 | PWSSB | WS, Sew | Sh. Satwinder Singh Dhillon 97800-14399 | Er. Lalit Mittal 9872730032 | Sh. Tajinder Garg 96468-88325 & Sh. Simranjeet singh 94642-61461 | 2 no. Completed 4 no. sites to be given by MC Sangrur. |  | 35.71%
[6 empty] | S |  | 108 | [5 empty] | WS Work at Sangrur | Ongoing Work | MDF |  | 2) | 100 mmi/d- 150mmi/d- WS H/conn.- Interloking- | 21400 mtr 3450 mtr 5000 no 15536 sqmt |  | 11.36 | 6.55 | 50% | 83% | 5.47 | 24.12.2021 | 30.09.23 | [5 empty] | Work in progress |  | 83.51%
[6 empty] | S |  | 108 | [5 empty] | Sewerage Work at Sangrur | Ongoing Work | HUDCO |  | 3) | UPVc pipe sew. - RCC Pipe Sew. - Sew H/conn .- IPS - | 30.59km 1.64km 7500 no 1 no |  | 28.09 | 16.25 | 80% | 55% | 9.01 | 24.12.2021 | 30.09.23 | [5 empty] | Work in progress |  | 55.45%
[6 empty] | S |  | 108 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | Rehabilt of Dist.network House Connection WTP Raw Water Pipeline - | 9: 10.00 Km 1000 Nos. 22.32 MLD 12.00 Km; 10: 51.63; JE 23: DPR under preparation stage
[6 empty] | S |  | 108 | [5 empty] | R/Main & 11 MLD STP | Proposed work | Special Assistance |  | 1) | R/Main STP | 9: 1.72 Km 1 no.; 10: 16.82; JE 23: Tender opening 10.02.2023
[6 empty] | S |  | 108 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | STP's MPS/IPS Rising Main | 9: 1 No's / 11 MLD 1 No's / 30 MLD 1.728 Km; 10: 29.06; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
177 | Smt. Narinder Kaur Bharaj | ਸ਼੍ਰੀ ਨਰਿੰਦਰ ਕੌਰ ਭਰਾਜ, 90411-85923 | Smt. Narinder Kaur Bharaj |  |  | S |  | 108 | 108- ਸੰਗਰੂਰ | 108- Sangrur | ਭਵਾਨੀਗੜ੍ਹ, (ਸ਼੍ਰੀ ਸਤਵਿੰਦਰ ਢਿਲੋਂ, 97800-14399) | Bhawanigarh | Bhawanigarh | Prov. Interloking tiles | Ongoing Work | HUDCO |  | 1) | Interlocking tiles | 115648 sqm |  | 13.37 | 9.4549 | 85% | - | 8.76 | 11.12.2020 | 30.09.23 | PWSSB | STP (Deposit work) | Sh. Satwinder Singh Dhillon 97800-14399 | Sh. Bhavesh Bansal 94174-94131 | Sh. Tajinder Garg 96468-88325 & Sh. Simranjeet singh 94642-61461 | Notice Issued to speed up progress vide EE letter no. 4343 dt.04.10.22 |  | 92.65%
[6 empty] | S |  | 108 | [5 empty] | Water supply & Sewerage Work at bhawanigarh | Ongoing Work | MDF |  | 2) | WS Pipe- UPVC Pipe - WS H/conn.- Sew. H/Conn. - IPS - | 20.88 km 15.09km 1000 no 2000 no 1 no |  | 15.68 | 9.79 | 75% | 82 | 8.07 | 28.09.2021 | 30.09.23 | [5 empty] | Notice Issued to speed up progress vide EE letter no. 4347 dt.04.10.22 |  | 82.43%
[6 empty] | S |  | 108 | [5 empty] | Water supply | Proposed work | AMRUT 2.0- (T-1) |  |  | House Connection WTP Raw Water Pipeline - | 9: 1523 Nos. 5.68 MLD 7.50 Km; 10: 19; JE 23: DPR under preparation stage
178 | Shri. Gurdev Singh Dev Maan | ਸ਼੍ਰੀ ਗੁਰਦੇਵ ਸਿੰਘ ਦੇਵ ਮਾਨ, 98783-86581 | Shri. Gurdev Singh Dev Maan |  | AAP | Pat-1 | Patiala | 109 | 109- ਨਾਭਾ | 109- Nabha | ਨਾਭਾ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Nabha | Nabha | Contruction of MPS and STP of 12 MLD | Ongoing Work | HUDCO |  | 1) | MPS (No) STP (No) = 1 No. 12 MLD | 1 No 1 No. 12 MLD |  | 21.88 | 16.82 | 90% | 71% | 10.03 | 09.07.2020 | 31.07.23 | ULB | - | Er.Vikas Kumar 98887-28887 | Er. Hanish Kumar 98886-70800 | Er. Ravi Narula 70091-32001 | LD impossed which is held in abeyance by S.E., Patiala. |  | 59.63%
[6 empty] | Pat-1 |  | 109 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S lines WTP | 9: 5.50 km 3.70 MGD; 10: 37.78; 16: DNIT approved by Technical Sub Committee; SDE 13: -DO-; JE 14: -DO-; JE 23: DPR under preparation stage
179 | [5 empty] | Pat-1 |  | 109 |  |  | ਭਾਦਸੋਂ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Bhadson | Bhadson | Sewerage Work | Work Completed | HUDCO |  | 1) | Revised Sewer lines = | 1.40 Km. |  | 13.77 | 3.01 | 100% | 35.97% | 1.08 | 24.12.21 | 31.12.2022 |  |  | Er.Vikas Kumar 98887-28887 | Er. Hanish Kumar 98886-70800 | Er. Amrinder Singh 98885-50606 | Work Completed |  | 35.88%
[5 empty] | AAP | Pat-1 |  | 109 | [5 empty] | Sewerage Works | Ongoing Work | Special Assistance |  | 2) | 200 mm- 600mm Sewline | 1.98 Km |  | 14.79 | 1.13 | 81% | 28% | 0.32 | 18.01.23 | 31.07.23 | ULB | - | [5 empty] | 28.32%
[6 empty] | Pat-1 |  | 109 | [5 empty] | Sewerage Works | Ongoing Work | Special Assistance |  | 3) | MPS = 200-400 mm Sew Line | 9: 1 No. 4.242 KM; 12: 3.19; 13: 68%; 14: 30%; 15: 0.98; 16: 16.01.23; 17: 31.07.23 |  | 30.72%
[6 empty] | Pat-1 |  | 109 | [5 empty] | Water Supply & WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | Rehab. Of W/S lines OHSR WTP | 9: 10.00 km 1 No. 0.74 MGD; 10: 22.03; 16: Tender Called; JE 23: DPR under preparation stage
[6 empty] | Pat-1 |  | 109 | [5 empty] | STP | Proposed work | SBM-2.0 |  | 2) | STP (2MLD) | 9: 1No.; 10: 4.25; 16: DPR checked at HO & sent to SLTC; JE 23: DPR under preparation stage
180 | Shri. Dr. Balbir Singh | ਡਾ. ਬਲਬੀਰ ਸਿੰਘ, 97795-33515 | Shri. Dr. Balbir Singh |  | AAP | Pat-1 | Patiala | 110 | 110- ਪਟਿਆਲਾ ਪੇਡੂਂ | 110- Patiala Rural | ਪਟਿਆਲਾ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Patiala | Patiala | 24X7 Canal Water Supply Project | Ongoing Work | AMRUT |  | 1) | Water Treatment Plant S&S Tank Clear Water Reservoir Raw Water inlet pipe Pump House Clear Water Rising Main Rehab of existing W/S Rehab of existing W/S with GI pipe (Over Ground) Construction of new OHSRs Repair of Existing OHSR Construction of UGSRs l Rehab of existing House Connection House service connections. | 115 MLD 236 ML 19.75ML 900m 1 No. Each 35.59 km. 312.55 km. 20km. 12 Nos. 13 Nos. 15 Ml 31430 Nos. 68830 No. |  | 588.42 | 342 | 54% | 31% | 90.89 | 13.10.20 | 12.10.23 | ULB | - | Er.Vikas Kumar 98887-28887 | Er. Sanjay Jindal 99883-10260 | Er. Vikash Kumar 80592-32486 | 54% Work Completed |  | 26.58%
181 | Shri. Ajit Pal Singh Kohli | ਸ਼੍ਰੀ ਅਜੀਤਪਾਲ ਸਿੰਘ ਕੋਹਲੀ , 98785-98785 | Shri. Ajit Pal Singh Kohli |  | AAP | Pat-1 | Patiala | 115 | 115- ਪਟਿਆਲਾ ਸ਼ਹਿਰੀ | 115- Patiala urban | ਪਟਿਆਲਾ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Patiala | Patiala | Rejuvenation of Chotti & Baddi Nadi Patiala | Ongoing Work | NCRPB & AMRUT (PDA) |  | 1) | Chotti Nadi Sewer- Baddi Nadi- MPS- 2 No. STP- 2 No. & ETP | 4.0 Km, -6.7 km, 2 No. (50 MLD & 80 MLD), 2 No. (15 MLD & 26 MLD) 1 N0. (2.5 MLD) |  | 208.33 Cr.PWSSB Part 91.18 Cr. | 87.64 | 47% | 23% | 19.94 | 22.10.2020 | 21.10.23 | ULB | - |  | -DO- | -DO- | 47% Work completed. |  | 22.75%
182 | Smt. Neena Mittal | ਸ਼੍ਰੀਮਤੀ ਨੀਨਾ ਮਿੱਤਲ, 80540-39645 | Smt. Neena Mittal |  | AAP | Pat-1 | Patiala | 111 | 111- ਰਾਜਪੁਰਾ | 111- Rajpura | ਰਾਜਪੁਰਾ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Rajpura | Rajpura | Sewerage work (Part-C) | Ongoing Work | MDF |  | 1) | Sewer Lines Revised HC | 19.04 kms. 13.00 Km 650 Nos. |  | 40.06 | 7.01 | 92% | 80% | 5.6 | 16.09.21 | 31.05.23 | PWSSB | W/S , Sew, STP | Er.Vikas Kumar 98887-28887 | Er. Karandeep Singh 85560-05353 | Er. Dinesh Sabharwal 96465-40600 | Work held up due to pending approval of forest department. Case for the same has been applied by this office. |  | 79.89%
[6 empty] | Pat-1 |  | 111 | [5 empty] | Water Supply and Sewerage work (Part A) | Work Completed | MDF |  | 2) | Water Supply Water Supply HC Sewerage Sewer H.C. | 9: 9.9 Kms. 1035 Nos. 19.68 Kms. 1500 Nos.; 12: 8.74; 13: 100%; 14: 90%; 15: 7.85; 16: 28.09.21; 17: 30.04.23; JE 23: Work Completed |  | 89.82%
[6 empty] | Pat-1 |  | 111 | [5 empty] | Water supply ,OHSR and Sewerage works (Part B) | Work Completed | MDF |  | 3) | Water Supply Water Supply H.C. Sewerage Sewer H.C. OHSR 2lac Gallon | 9: 15.01kms 1350 Nos. 10.10 kms 800 Nos. 01 nos; 12: 10.29; 13: 100%; 14: 91%; 15: 9.37; 16: 18.11.2021; 17: 30.04.23; JE 23: Work Completed |  | 91.06%
[6 empty] | Pat-1 |  | 111 | [5 empty] | P/I of Pumps sets at Work works , P/I of 2 Nos. T/Wells at Rajpura | Ongoing Work | MDF |  | 4 | Pump Sets Transformer T/Well | 9: 3 Nos. 1 No. 2 Nos.; 12: 1.52; 13: 0%; 14: 0%; 15: 0; 16: 25.04.23; 17: 24.07.23 |  | 0%
[6 empty] | Pat-1 |  | 111 | [5 empty] | Providing Water Supply line for replacement of existing old water supply lines at Rajpura | Ongoing Work | Deposit work |  | 4) | Water Supply system 100 mm i/d W/S House Connections | 4218 mtr. 440 Nos. |  | 1 | 0.84 | 60% | 63.86% | 0.54 | 15.12.21 | 31.07.23 | [5 empty] | Work in progress.. |  | 64.29%
[6 empty] | Pat-1 |  | 111 | [5 empty] | Providing w/s and construction of SV chamber Mirch Mandi at Rajpura . | Ongoing Work | Deposit work |  | 5) | Water Supply system 1. 100 mm i/d DIK7 2. 150 mm i/d W/S House connections | 1814 mtr. 1748 Mtr. 200 Nos. |  | 1.5 | 0.74 | 95% | 84.02% | 0.62 | 27.04.2022 | 30.06.23 | [5 empty] | Work in progress.. |  | 83.78%
183 | Smt. Neena Mittal | ਸ਼੍ਰੀਮਤੀ ਨੀਨਾ ਮਿੱਤਲ, 80540-39645 | Smt. Neena Mittal |  |  | Pat-1 |  | 111 | 111- ਰਾਜਪੁਰਾ | 111- Rajpura | ਰਾਜਪੁਰਾ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Rajpura | Rajpura | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | WTP 3.15 MGD = S&S tanks new , Clear Water tank new Rising Main 1000mm i/d UGSR new Rehabilitation of existing OHSR New Dist. network incl. rehabilitation W/s House Connections Railway Crossings National Highway crossings | 9: 1No. 4 Nos, 1 Nos 1.80 Kms 13 Nos 16 Nos 180.97 Kms 25000 Nos 3 Nos 3 No; 10: 176; ULB/ PWSSB 10: PWSSB; Scope (W/S, Sew, STP) 11: W/S , Sew, STP; EE 12: Er.Vikas Kumar 98887-28887; SDE 13: Er. Karandeep Singh 85560-05353; JE 14: Er. Dinesh Sabharwal 96465-40600; JE 23: DPR under preparation stage
184 |  |  |  |  | AAP | Ropar | SAS Nagar | 111 |  |  | ਬਨੂੜ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Banur | Banur | Water Supply, Sewerage | Ongoing Work | Deposit work |  | 1) | W/S Lines Sewer Lines | 0.69 Kms 0.92 Kms. |  | 0.43 | 0.35 | 60% | 40% | 0.14 | 27.12.21 | 30.09.23 | PWSSB | T/well, STP (Deposit work) | Pankaj Jain 8427663504 | Rakesh Mehta 9216870070 | Jasbir Singh 9501500501 | --- |  | 40%
[6 empty] | Ropar |  | 111 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  |  | New Distribution network House connection T/Well | 9: 4.50 km 600 Nos. 3 Nos.; 10: 2.17; JE 23: DPR under preparation stage
[6 empty] | Ropar |  | 111 | [5 empty] | Tubewell, W/S, R/Main | Proposed work | Deposit work |  | 1) | Tubewell W/S Lines R/Main | 9: 2 Nos. 3.81 Kms. 1.1 Kms.; 10: 5.83; JE 23: DPR under preparation stage
185 | Shri. Kuljit Singh Randhawa | ਸ਼੍ਰੀ ਕੁਲਜੀਤ ਸਿੰਘ ਰੰਧਾਵਾ 99142-26095 | Shri. Kuljit Singh Randhawa |  | AAP | Ropar | SAS Nagar | 112 | 112-ਡੇਰਾਬੱਸੀ | 112- Dera bassi | ਡੇਰਾਬੱਸੀ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Dera bassi | Dera bassi | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Distribution network House connection T/Well | 5.50 km 800 Nos. 3 Nos. | 2.98 | --- | --- | --- | --- | --- | --- | --- | PWSSB | Sew Scheme (Deposit work) | Pankaj Jain 8427663504 | Rakesh Mehta 9216870070 | Jasbir Singh 9501500501 | DPR under preparation stage
[8 empty] | 112 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | Main Sewer STP's MPS/IPS Rising Main Restoration of Road | 9: 8.6 Km 5 No's / 3,3,2,1, 0.35 MLD 2 No's 15 MLD 4.68 Kms 18000 Sqm; 10: 43.36; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
186 | [5 empty] | Ropar |  | 112 |  |  | ਜੀਰਕਪੁਰ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Zirakpur | Zirakpur | Sewer, MPS, STP | Ongoing Work | Deposit work |  | 1) | Sewer | 5.14 Kms. |  | 3.54 | 2.63 | 75% | 62% | 1.64 | 27.08.21 | 30.09.23 | PWSSB | STP, MPS (Deposit work) | Pankaj Jain 8427663504 | Rakesh Mehta 9216870070 | Jasbir Singh 9501500501 | --- |  | 62.36%
[6 empty] | Ropar |  | 112 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Distribution network House connection T/Well | 9: 3.00 km 650 Nos. 2 Nos.; 10: 1.79; JE 23: DPR under preparation stage
[6 empty] | Ropar |  | 112 | [5 empty] | Sewer, MPS, STP | Proposed work | Deposit work |  | 1) | Sewer MPS STP | 9: 27.00 Kms. 1 No. 1 No.; 10: 85; JE 23: DPR under preparation stage
187 | [5 empty] | Ropar |  | 112 |  |  | ਲਾਲੜੂ (ਸ਼੍ਰੀ ਪੰਕਜ ਜੈਨ, 84276-63504) | Lalru | Lalru | Main Sewer, MPS, STP | Ongoing Work | GMADA / Urban Mission |  | 1) | Sewer MPS STP | 1 .00 Kms. 1 No. 1 No.(1 MLD) |  | 6.02 | 3.87 | 25% | 8% | 0.29 | 07.07.21 | 31.10.23 | ULB | - | Pankaj Jain 8427663504 | Rakesh Mehta 9216870070 | Jasbir Singh 9501500501 | Site for MPS yet to be provided by MC. |  | 7.494%
[6 empty] | Ropar |  | 112 | [5 empty] | Sewerage work | Proposed work | SBM-2.0 |  |  | Main Sewer STP's MPS/IPS Rising Main | 9: 6.5 Km 3 No's / 3.5,2,1 MLD 5 No's 75 MLD 8.5 Kms; 10: 37.77; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
[6 empty] | Ropar |  | 112 | [5 empty] | Water Supply | Proposed work | AMRUT 2.0- (T-2) |  | 1) | New Distribution network House connection T/Well | 9: 6.00 km 800 Nos. 2 Nos.; 10: 2.8; JE 23: DPR under preparation stage
188 | Shri. Gurlal Ghanaur | ਸ਼੍ਰੀ ਗੁਰਲਾਲ ਸਿੰਘ ਘਨੌਰ, 98153-52145 | Shri. Gurlal Ghanaur |  | AAP | Pat-1 | Patiala | 113 | ਘਨੌਰ | 113- Ghanaur | ਘਨੌਰ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Ghanaur | Ghanaur | STP 2 MLD at Ghanaur under HUDCO shceme | Ongoing Work | HUDCO |  | 1) | STP - 1 No. 2 MLD | 1 No. 2 MLD |  | 9.76 | 2.23 | 66% | 6% | 0.13 | 24.12.2021 | 30.09.23 | PWSSB | W/S , Sew, MPS | Er.Vikas Kumar 98887-28887 | Er. Hanish Kumar 98886-70800 | Er. Ravi Narula 70091-32001 | Work in progress.. |  | 5.83%
[6 empty] | Pat-1 |  | 113 | [5 empty] | Water Supply & WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S lines WTP | 9: 10.78 km 0.40 MGD; 10: 9.68; 16: Tender Called; JE 23: DPR under preparation stage
189 | Shri. Harmit Singh Pathanmajra | ਸ਼੍ਰੀ ਹਰਮੀਤ ਸਿੰਘ ਪਠਾਨਮਾਜਰਾ, 98762-61101 | Shri. Harmit Singh Pathanmajra |  | AAP | Pat-1 | Patiala | 114 | ਸਨੌਰ | 114- Sanour | ਸਨੌਰ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Sanour | Sanour | Water Supply, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S lines WTP | 76.00 km 1.21 MGD | 41.19 | - | - | - | - | - | DPR approved by Technical Sub Committee/SLTC | - | ULB | - | Er.Vikas Kumar 98887-28887 |  |  | DPR under preparation stage
[6 empty] | Pat-1 |  | 114 | [5 empty] | MPS,STP, Main Sewer | Proposed work | SBM-2.0 |  | 2) | Main Sewer STP MPS Rising Main const. of Roads | 9: 11.18 km 1 No 1 No. 3.44 km 24480 sqm; 10: 29.84; 16: DPR yet to be received in Head Office; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; JE 23: DPR under preparation stage
190 | Shri. Harmit Singh Pathanmajra | ਸ਼੍ਰੀ ਹਰਮੀਤ ਸਿੰਘ ਪਠਾਨਮਾਜਰਾ 98762-61101 | Shri. Harmit Singh Pathanmajra |  |  | Pat-1 |  | 114 | ਸਨੌਰ | 114- Sanour | ਦੇਵੀਗੜ੍ਹ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) | Devigarh | Devigarh | Sewer, MPS & STP | Proposed work | SBM-2.0 |  | 1) | Main Sewer STP MPS IPS & Rising Main | 9: 10.85 Km, 1 No., 1 No., 3 No. 2.95 Km; 10: 14.33; 16: DPR yet to be received in Head Office; ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: Er.Vikas Kumar 98887-28887; JE 23: DPR under preparation stage
191 | Shri. Ajit Pal Singh Kohli | ਸ਼੍ਰੀ ਅਜੀਤਪਾਲ ਸਿੰਘ ਕੋਹਲੀ , 98785-98785 | Shri. Ajit Pal Singh Kohli |  | AAP | Pat-1/2 | Patiala | 115 | 115- ਪਟਿਆਲਾ ਸ਼ਹਿਰੀ | 115- Patiala urban | ਪਟਿਆਲਾ ਸ਼ਹਿਰੀ (ਸ਼੍ਰੀ ਵਿਕਾਸ ਧਵਨ, 98887-28887) (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Patiala urban | Patiala urban | [6 empty] | ULB/ PWSSB 10: ULB; Scope (W/S, Sew, STP) 11: -; EE 12: Presently no work ongoing by PWSSB; JE 23: Presently no work ongoing by PWSSB
192 | Shri. Chetan Singh Jouramajra | ਸ਼੍ਰੀ ਚੇਤਨ ਸਿੰਘ ਜੌੜਾਮਾਜਰਾ, 83609-94511 | Shri. Chetan Singh Jouramajra |  | AAP | P2 | Patiala | 116 | ਸਮਾਣਾ | 116- Samana | ਸਮਾਣਾ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Samana | Samana | Water Supply & Sewerage Work | Ongoing Work | PUEIP |  | 1) | DI-K7 Pipe H C (WS) Sewer Line H C (Sew) IPS Roads | 22053 mtr 900 Nos. 29100 mtr 900 Nos. 1 No 137075 Sqm |  | 29.98 | 22.42 | 77% | 80% | 17.83 | 21.10.2021 | 31.08.23 | PWSSB | STP, Sew,WS | Er. Jugal Kishor (84276-63501) | Er. Arvinder Singh (73409-17952) | Er. Pardeep Singh (84270-02262) |  |  | 79.53%
[6 empty] | P2 |  | 116 | [5 empty] | New Route 800 mm i/d Sewer | Ongoing Work | Special Assistance |  | 2) | RCC Sewer | 9: 3.95 Km; 11: 11.98; 12: 4.48; 13: 100%; 14: 100%; 15: 3.06; 16: 03.01.23; 17: 31.08.23 |  | 68.3%
[6 empty] | P2 |  | 116 | [5 empty] | W/S, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S WTP | 9: 16.66 Km 1 no.(13.68 MLD ); 10: 59.62; JE 23: DPR under preparation stage
193 | Shri. Kulwant Singh Bazigar | ਸ਼੍ਰੀ ਕੁਲਵੰਤ ਸਿੰਘ ਬਾਜ਼ੀਗਰ, 96150-00094 | Shri. Kulwant Singh Bazigar |  | AAP | P2 | Patiala | 117 | ਸ਼ੁਤਰਾਣਾ | 117- Shutrana | ਪਾਤੜਾਂ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | 1. Patran | 1. Patran | W/S, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S WTP | 14.65 Km 1 no.(7.27MLD ) | 4.94 | [5 empty] | DPR's Prepared |  | PWSSB | STP (Deposit work) | Er. Jugal Kishor (84276-63501) | Er. Arvinder Singh (73409-17952) | Er. Pardeep Singh (84270-02262) | DPR under preparation stage
[6 empty] | P2 |  | 117 |  |  | ਘੱਗਾ (ਸ਼੍ਰੀ ਜੁਗਲ ਕਿਸ਼ੋਰ, 84276-63501) | Ghagga | Ghagga | W/S, WTP | Proposed work | AMRUT 2.0- (T-1) |  | 1) | W/S WTP | 7.80 Km 1 No.(2.6 MLD) | 16.88 | [5 empty] | Tender Called |  | ULB | - | Er. Jugal Kishor (84276-63501) | Er. Arvinder Singh (73409-17952) | Er. Pardeep Singh (84270-02262) | DPR under preparation stage
[6 empty] | P2 |  | 117 | [5 empty] | Main Sewer, STP | Proposed work | SBM-2.0 |  | 2) | Main Sewer STP | 9: 10.88 Km 1 no. (3MLD); 10: 36.81; 16: DPR yet to be received in Head Office; JE 23: DPR under preparation stage
1) 2)